## Sheet1
HEADGATE AND CYLINDER DELIVERIES |  |  |  | Date: | 2026-07-29 10:02
ITEM | Quantity | Projected | Actual | Location | Notes
|  | Delivery | Delivery | Delivered
|  | Date | Date
HEADGATES
PH 1
| 12 | 2003-06-23
PH 2
Main Unit | 1 | 2001-10-01 | 2001-12-18 | PH 2
HEADGATE BEAM COMPONENTS
Baseplates and Saddles(52) |  |  |  |  | Based on Number of Baseplates. Multiply by 2 to get number of saddles provided
Partial Shipment | 4 | ? | ? | Warehouse | These have been received
Partial Shipment | 44 | ? | 2002-08-29 | Warehouse
Partial Shipment | 4 | ? | 2002-09-30 | Warehouse
Cover Plates(52)
Partial Shipment | 8 | ? | ? | Warehouse | These have been received
Partial Shipment | 44 | ? | 2002-11-07 | Warehouse
Reinforcing Bar A(96)
Partial Shipment | 8 | ? | ? | Warehouse | These have been received
Partial Shipment | 88 | ? | 2002-11-07 | Warehouse
Reinforcing Bar B (96)
Partial Shipment | 8 | ? | ? | Warehouse | These have been received
Partial Shipment | 88 | ? | 2002-11-07 | Warehouse
Reinforcing Ring(48)
Partial Shipment | 4 | ? | ? | Warehouse | These have been received
Partial Shipment | 44 | ? | 2002-11-07 | Warehouse
CYLINDERS
Main Unit (54)
Partial Shipement | 2 | 2002-06-27 | 2002-07-16 | PH 2
Partial Shipement | 4 | 2002-07-12 | 2002-07-16 | PH 2
Partial Shipement | 12 | 2003-01-15 | 2003-01-14 | PH 2 | Cylinders are currently being stored on tailrace deck, North end adjacent to fish ladder. Will be moved when new building is erected
Partial Shipement | 6 | 2003-11-01
Partial Shipement | 6 | 2004-11-01
Partial Shipement (Final) | 24 | 2006-11-01
Fish Unit(6) | 6 | 2005-11-01
SS Plugs for Cycle ports | 120 | 2002-12-10 | 2002-12-10 | Warehouse/KPP | Given to Steve C on 12/10
Headgate Latching Cylinders | 33 |  |  | Warehouse
Anodes |  | 2002-07-31 | 2002-07-31 | Warehouse
Partial Shipment (For first 12 cyl) | 191 | 2002-07-31 | 2002-07-31 | Warehouse
Partial Shipment | 1 | ? | 2002-09-03 | KPP Desk | One anode was sent directly to KPP on 3 Sep. He handed it to Steve C.
Partial Shipment
Spare Parts | Lot
Other(For first 6 cylinders)
Locktite | Lot | 2002-06-03 | 2002-06-03 | Warehouse
Pins | 6 | 2002-06-03 | 2002-06-03 | Warehouse
Sleeve Bushings | 12 | 2002-06-03 | 2002-06-03 | Warehouse
Rod End Bearings | 2 | 2002-06-20 | 2002-06-25 | Warehouse
Rod End Bearings | 4 +2 | 2002-07-20 | 2002-07-23 | Warehouse | An extra 2 bearings (for a total of 6) were provided and transferred to EC-DM, not part of contract
Notes
1. Once cylinders arrived, OP-B is required to fill them with oil. We have up to 6 months on this but it should occur ASAP to limit any oxidation inside the cylinders. OP-B is required to exercise (extend and retract approx. 1 foot) stored cylinders annually to keep seals lubed. Contractor will provide direction on this.
2. For the first six headgates, the rod end and cylinder end bushings described above are to be installed by OP-B. For the remaining headgates, the contractor will ship them installed on the cylinders.
3. For all headgates, the cylinder anodes shall be installed by OP-B. Anodes are shipped separately
4. Headgate cylinders weigh around 9,000lbs/piece. They are around 55 feet long.