## Sheet1
Fish Passage Facility Priority Listing
Bonneville 1st Powerhouse | [8 empty] | Importance
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY11 | FY 12 | High | Medium | Low
Dredge Bradford Island Ladder Exit | 145 | FY02 | bar: FY 08
Rem. Obstructions from Turb. Envir. | 91 | Ongoing | bar: FY 07 to FY 08
Bradford/Cascade Fishway Report Phase 2 | bar: FY 08 to FY 09
Replace diffuser valves | bar: FY 08; FY 10
Remove FV 3-8 | 191 | bar: FY 09
FV3-7 AWS conduit leak | bar: FY 10
PLC/programming for Brad. Is/Cascades Is. | bar: FY 08
Spalling/erosion in Brad/Cascades Is. | bar: FY 10; FY 12
Fill PH1 collection channel diffuser pits | bar: FY 10; FY 12
Replace diffuser gratings (3/4 inch) | bar: FY 10 to FY 12
Small Cap |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY11 | FY 12
Replace PH1 Leaking Bulkheads (wooden) | 145 | FY09 | bar: FY 08 to FY 09
Bonneville 2nd Powerhouse
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Dredge Forebay | 144 | FY 07 | bar: FY 09
Bass Lake Chum Salmon Habitat Plan/Imp | bar: FY 08 to FY 11
Replace SMF switchgate seals | bar: FY 09
Repair N Shore Monolith Expansion Joint | bar: FY 09
Repair/Replace Fishway Diffusion Valves | bar: FY 09
Automated Raking System | bar: FY 09
SMF - Avian Cannon Pipe Replacement | bar: FY 08
Repair Fish Ladder Channel Exit Bulkhead | bar: FY 09
Replace diffuser gratings (3/4 inch) | bar: FY 10 to FY 12
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Rehabilitate TIES | bar: FY 09 to FY 11
Corner collector hoist | bar: FY 09
TIE Crane
The Dalles | [8 empty] | Importance
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12 | High | Medium | Low
Replace East Shore Diffuser Gratings | 144 | FY 05 | [7 empty] | x | bar: FY 07 to FY 09
Hydraulic Eval Adult Fishway | 120 | FY 06 | [7 empty] | x | bar: FY 09 to FY 10
Install SCADA Fishway Control | 145 | FY 04 | [6 empty] | x | bar: FY 07 to FY 09
New entrance weir | [8 empty] | x | bar: FY 07
North dewater pump replace | [9 empty] | x | bar: FY 07
Spare diffuser valve | [9 empty] | x | bar: FY 07
Count station HVAC | [8 empty] | x | bar: FY 07
Small Cap |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Procure and Install Diffuser Valves | 144 | FY06 | [7 empty] | x | bar: x FY 07
Automate Aux. Water Supply System | 145 | FY 04 | [6 empty] | x | bar: x FY 09
John Day
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
STS Refurbishment | [8 empty] | x | bar: FY 07 to FY 12
Install Count Station Brush | [9 empty] | x | bar: FY 09
Fill SE1 Wall Diffuser or rehab so functional | [9 empty] | x | bar: FY 09
Decision Document on N. Fish Count St | [8 empty] | x | bar: FY 08
Small Cap |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Install Penstock Isolation Valve | 145 | FY 05 | [8 empty] | x | bar: x FY 09 to x FY 11
Spare SE1 Weir | 145 | FY 05 | [7 empty] | x | bar: x FY 09 to x FY 11
EW3 concrete bulkhead or wall | [9 empty] | x
Fishway auto upgrade | [8 empty] | x
North pump rehab | [8 empty] | x
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Construct Repaint Facility | 144, 145 | FY 04 | [6 empty] | x | bar: FY 09
Rebuild So. Shore AWS Fish Pumps | 145 | FY 05 | [6 empty] | x | bar: FY 07 to FY 09
New North Shore Fish Count Station | 191 | FY 05 | [6 empty] | x | bar: FY 10 to FY 11
McNary | [8 empty] | Importance
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12 | High | Medium | Low
AFEP (Transport Study) | 45 | FY 02 | bar: FY 07 to FY 12
Fish Facility Spare Parts | 121145 | FY 02 | bar: FY 07 to FY 08; FY 11 to FY 12
ESBS Overhaul | 6, 144, 145 | FY 04 | bar: FY 07 to FY 09
Fish Pump 1 Overhaul | 6, 144, 146 | FY09 | bar: FY 09
VBS Mesh Replacement | 6, 144, 145 | FY 04 | bar: FY 08 to FY 09
Small Cap |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Fish Pumphouse HVAC | Action? | FY 05 | bar: x FY 08
Fish Ladder Exit Control to Control Rm. | Action? | FY 05 | bar: x FY 08
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Rehab Tilting Weirs | 6, 144, 145 | FY 05 | bar: FY 07 to x FY 09
Rehab Fishway Entrances | 6, 144, 145 | FY 06 | bar: x FY 08 to x FY 10
Repair S. Shore Diffuser Valves | 6, 144, 145 | FY 08 | bar: x FY 08 to x FY 09
Rehab South Shore Rotovalves | 6, 144, 145 | FY 05 | bar: x FY 08
Ice Harbor
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Fish Facility Spare Parts | 121, 145 | FY 02 | bar: FY 07 to FY 08; FY 11 to FY 12
Repair Fishway Diffuser Valves | 145 | FY 06 | bar: FY 09
Overhaul STS | 145 | FY 07 | bar: FY 07 to FY 08
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Rehab S S Fish Pumps | 6144145 | FY 02 | bar: x FY 08 to x FY 12
Adult Fishway Control System | 6144145 | FY 06 | bar: x FY 09 to x FY 10
Lower Monumental
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Fish Facility Spare Parts | 121, 145 | FY 02 | bar: FY 07 to FY 08; FY 11 to FY 12
Overhaul STS | 145 | FY 07 | bar: FY 07 to FY 08
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Adult Fishway Control System | 6, 144, 145 | FY 05 | bar: x FY 10 to x FY 11
Rehab Adult Entrances and Hoists | 6, 144, 145 | FY 08 | bar: x FY 09 to x FY 11
Little Goose | [8 empty] | Importance
Non-Routine Fish |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12 | High | Medium | Low
AFEP (Steelhead Kelt Study) | 109 | FY 02 | bar: FY 07
Fish Facility Spare Parts | 121, 145 | FY 02 | bar: FY 07 to FY 08; FY 11 to FY 12
ESBS Overhaul | 6, 144, 145 | FY 05 | bar: FY 07 to FY 08
Large Capital |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Rehab Fish Pumps | 6, 144, 145 | FY 06 | bar: x FY 09 to x FY 12
Lower Granite
Non-Routine Items: |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
AFEP (Steelhead Kelt Study) | 109 | FY 02 | bar: FY 07
Fish Facility Spare Parts | 121, 145 | FY 02 | bar: FY 07 to FY 08; FY 11 to FY 12
ESBS Overhaul | 6, 144, 145 | FY 05 | bar: FY 07 to FY 08
Large Capital Items: |  |  | FY 07 | FY 08 | FY 09 | FY 10 | FY 11 | FY 12
Replace Two 2000 Series Barges | 40 | FY 04 | bar: x FY 07 to x FY 09
Rehab Fish Pumps | 6, 144, 145 | FY 08 | bar: x FY 10 to x FY 12
Automate Fish Pump Bulkheads | 144 | FY 08 | bar: x FY 10 to x FY 11
Note on A12: g0pddpao: Need Justification of why this is small cap