##### Construction

McNary:

- Turbine units 1 and 2 out of service March 9 – 12 in support of Transformer 1 Doble Tests.  Otherwise, all 14 turbine units currently available for service.

Ice Harbor:

- All 6 turbine units are in service.

- Turbine unit 6: out of service March 4-6  and March 10 – 13 in support of RSW dives.

Lower Monumental:

- All 6 turbine units are in service.

- Turbine unit 4: out of service March 4 -5 to clean brush rigging.

Little Goose:

- Turbine units 5 and 6 are out of service in support of TSW installation and trash shear boom relocation.

- Full flow PIT tag detector mostly in place.  Detector components, wiring and shields currently being installed.  Wet test expected later this week.

- TSW high crest weir tested March 5 and 11.  Balloon tag injury tests delayed as forebay is near full pool.

- Flow Deflectors have been installed in spill bays 1 and 8, some minor work remains.

- New Dewaterer downwell construction in progress.  Old downwell coupling bolts and seals are being repaired to permit another season of use.

Lower Granite:

- All 6 turbine units are in service.

Operations and Maintenance - Juvenile Fish Facilities

McNary:

- Facility out of service for winter maintenance.

- ESBS installations are to begin April 6.

- Facility sample holding tanks now have juvenile lamprey-friendly out flow screens.

Ice Harbor:

- Facility out of service for winter maintenance.  Bypass start tentatively set for March 16.

- STSs deployment tentatively scheduled for March 23 – 31.

Lower Monumental:

- STSs currently undergoing winter maintenance.  Deployments to begin week of March 16.

- Bypass to begin March 16.

Little Goose:

- Facility out of service for winter maintenance.

- ESBSs are currently in stored positions.

Lower Granite:

- Facility out of service for winter maintenance,

- ESBSs deployments to begin the third week of March.

- Primary Bypass slated to begin March 20. Sampling activities are to begin March 25.

Operations and Maintenance - Adult Fish Facilities

Note: Except for Lower Granite and Bonneville dams, all count stations are out of service at this

time.  Video counts at Lower Granite dam began March 1.

McNary:

- Oregon Ladder:  Returned to service from winter maintenance on February 28.

- Washington Ladder: Unwatered for 4 hours on February 27 to remove log jams in orifices.  Otherwise only above water maintenance performed this winter due to ladder exit bulkheads not meeting safety requirements for personnel entry into fishway.

- PUD Turbine unit placed back in service February 28, had 52 minute interruption in service on March 5.  Bypass system operated well during outage.

- Fish Pumps: Pumps #1 & #2 are in service, both had breakers replaced March 2.  Fish Pump #3 currently unwatered and out of service for oil leak repairs.

Ice Harbor:

- North Shore Ladder unwatered January 5 and returned to service January 21.

- South Shore Ladder unwatered January 26 and returned to service February 25.

- North Shore Fish Pumps: Fish pumps #1 & #2 in service.  Fish pump #3 currently removed and taken off site for repairs.  Reinstallation tentatively set for March 23.

- South Shore Fish Pumps: all available for service.

Lower Monumental:

- North Ladder in service.

- South Ladder: Returned to service March 2.

- Fish Pumps 1 & 2 in service.  Fish Pump #3 out of service for diffuser assembly repairs and bearing housing replacement.  Fish pump 3 is “bulkheaded off” to improve efficiency of 2 pump operation.

Little Goose:

- Ladder watered up and returned to service February 4.

- All three fish pumps returned to service March 2.

Lower Granite:

- Fish pumps 1 and 3 started operation March 2, but both pumps developed mechanical problems the same day.  Fish pump 3 returned to service March 3 after a leaking oil reducer repaired.  A second pump was placed in service the same day.

- Fish Ladder viewing window developed a severe leak February 24, forcing a ladder unwatering.  Although window repairs were completed February 26, window adhesive curing delayed rewatering of the ladder until March 2.

Other

Ice Harbor:

- RSW: Currently in stowed position for repairs to seals, fish tracking antennae installation and other minor work.  Antenna installations to take place March 23.

Lower Monumental:

- Lamprey mortalities: 140 dead juvenile lamprey were discovered during the cleaning of turbine cooling water strainers.  3 live juvenile lampreys were recovered and released into the tailrace.  The lampreys accumulated over a period of 2 months.

- The RSW was successfully lowered to the stowed position and redeployed on March 4.  Hydro-acoustic being installed in support of upcoming research.

- RSW debris spill set for March 13 or 14.

Little Goose:

- Direct injury study was to being March 13, but has been delayed due to high pool elevations and late award of research contract.

Lower Granite:

- Adult trap operations resumed March 3 with sample rates of 10%. Permits prior to start of trap operation.  Adult fish trap water supply tests conducted March 5.