Draft2

JOHN DAY DAM FISHWAYS’ DEWATER SCHEDULE

WINTER ‘09/’10

## North Fish Ladder				-Dewater	Nov 16, ’09 – Mar 15, ‘10

## JDNFL construction support

- PM count station  and exit hydraulic weirs (JDM,JDE)

- Remove count station ¾” grating for south installation (?)

- Shim picket leads up 1” (JDS) – done?

- Check welds on debris guard

## North Entrance				-Dewater	Dependent on dist. visit

- PM entrance weirs (JDM, JDE)

- JDNFL district site visit support

- Measure weir chain (TJF)

## Juvenile Bypass System			-Dewater	Dec 15, ’09

- Repair flume spalling

- Repair SMF separator tub rust

- Inspect conduit (Engineering)

- PM all SMF equipment and tainter gate (JDM, JDE)

South Turbine Bulkhead Install		-ROV	         	Jan 11

- Inspect seal and south turbine intake for debris

- Inspect south pump stilling basin trashrack

- Inside penstock inspect – done last yr?

## South Fish Ladder                             	- Dewater    	Jan 12 -21, ‘10

- Repair broke welds on debris guard boom

- PM count station equipment and exit sills (JDM,JDE)

- Expansion joint repair exit (JDS)

## South Entrance, Collection channel	- Dewater     	Jan 25 – 28, ‘10

- PM SE1, NE1/2 entrance weirs (JDM, JDE)

- SE1 wall diffuser – seal off (JDM, Engineering)

- PM NE3 spare gearbox (JDM)

- Inspect diffuser valves (JDM, Engineering)

- Taillog install for south turbine rehab #2

- Measure weir chain (TJF)

## South fish turbine trashrack install	-ROV 		Jan 29, ‘10

- Inspect sill

- Inspect forebay north and south diffuser intakes