Draft2

# THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER ‘09/’10

## East Fish Ladder				-Dewater	Dec 2, ’09 – Jan 27, ‘10

## Repaint 1’ mark on weir 158-9 (TJF)

- Install new rubber on 158-9 side plates (TDS)

- PM weirs 154-9 and CS equip (TDS,TDM,TDE)

- Eng inspect 154-9 weirs

- Repair FB staff gauge #s (TDS)

- Clean staff gages and pickets (TJF)

- Lamprey mods; d/s count station, 180 bend, last ladder weir (Eng contract)

- Repair Expansion joints (Eng)

- Re-floor/repaint count stations and new roof east station  (TDM, Eng)

- Full range operation tests all weirs (TDS, TJF)

- Remove/inspect fish unit trashrack (TDS)

East, West and South Ent, Junct Pool, Collection and Trans Chan									-Dewater	Dec 7, ’09

- Install replacement diffuser grating where needed– Eng inspect. (TDS)

- PM entrance weirs (TDM, TDE)

- Full range opertion test (TDS, TJF)

- Lamprey mod; south entrance pool (Eng contract)

## North Fish Ladder				- Dewater	Feb 8 - 26, ‘10

- PM CS equipment and PUD radial (PUD provide labor)

- Remove brush from fish ladder walls (TJF)

- Repair loose guide and install rubber gaps of debris guard (TDS)

- Replace count station diffuser grating – (Eng)

- Full range operation test (TDS, TJF)

- Re-floor/repaint count station (TDM)

- Repair loose rail on exit debris guard and install rubber seal.(TDS)

- Fabricate debris guard PUD intake (Eng and TDS) determine need

North Entrance 				- Dewater	Feb 9. ‘10

- PM weir N1 (TDM, TDS)

- Full range operation test (TDS, TJF)

- Lamprey ramp; north entrance pool (contract)

ROV inspect PUD intake trashrack 	-ROV		Feb 18, ’09

Project ROV