# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER FISHWAY MAINTENANCE 2010/2011.

- This is a working document detailing Bonneville Dam winter fishway maintenance, 2010/2011.  Reviewers can expect changes as we approach the winter maintenance season.

- ADULT FISHWAYS

  - Fish Unit Outages

    - Fish Unit 1: 1 Dec 10 – 28 Feb 11, annual overhaul.

    - Fish Unit 2: 15 Nov 10 – 28 Feb 11, annual overhaul.

    - Fish Unit bulkhead installation  15 Nov 10

  - Adult Fish Facility (01 Nov 10 – 1 Apr 11)

    - Go to orifice flow on 01 Nov 10

    - Dewater exit section on 03 Nov 10

    - Dewater entrance on 04 Nov 10

    - Install FERL bulkhead afternoon of the 03 Dec 10

    - Routine maintenance.

    - PM bridge crane.  Replace wire rope.

    - Repair broken gate cranks and pulleys.

    - Inspect and repair weir doors.

    - Clean fish viewing window.  (Painters)

    - Inspect AFF valves 1, 2, and 3. (Mechanics)

    - Replace sample flume rubber lining (Mechanics)

    - Pressure wash the lab and handrails. (Painters)

    - Inspect/Replace silicone around the anesthetic tank bottom.  (Painters)

    - Secure bottom of temperature probe stillwell.  (Electricians)

    - Replace broken timbers in exit section with bulkhead.  (Riggers)

    - Repair/Replace netting over flumes. (Project Fisheries)

    - Relocate bridle storage rack (Riggers)

  - Cascades Island Ladder and UMT  (03 Dec 10 – 28 Feb 11)

    - Go to orifice flow on 01 Dec 10

    - Drain ladder to tailwater on 03 Dec 10

    - Install screen pit bulkheads on 17 Jan 11

    - Install entrance bulkheads and drain below tailwater  17 Jan 11

    - Dewater and fish salvage diffuser pools on 18 Jan 11

    - Diffusion valve inspection and repair (Riggers)

    - Remove large vegetation around fishways (blackberry bushes). (Garage)

    - Pressure wash algae and moss in and around fishway (Painters)

    - Inspect/repair fishway exit trashrack (Riggers/Painters)

    - Clean crowder. (Painters)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Slot filler hanger installation (Riggers)

    - Inspect FV5-3 conduit (Riggers/Tech staff)

    - Replace/repair research equipment (U of I)

    - Install SLEDS by 28 Feb 11

  - Washington Shore Ladder (1 Dec 10 – 28 Feb 11)

    - NORTH MONOLITH (1 Dec 10- 28 Feb 11)

      - Remove avian wires 26-27 October, reinstall early March (USDA)

      - Install stab plates in FOGs 15 Nov 10 (Riggers)

      - NDE SLED removal  Oct 10

      - Fish unit 2 out of service at 0001 15 Nov 10

      - Go to orifice flow on 1 Dec 10

      - Install FV6-9 bulkhead.  1 Dec 10

      - AWS dewatering  1 Dec 10

      - Dewater north monolith to tailwater on 3 Dec 10.

      - Install FERL bulkhead afternoon of 3 Dec 10

      - Dewater/fish salvage entrance section below tail water  6 Dec 10

      - Move existing lamprey plating in junction pool adjacent to wall (Riggers)

      - Inspect and repair north monolith expansion joints (Tech staff/Riggers)

      - Replace/repair research equipment (U of I)

      - Install SLEDS by 28 Feb 11

    - SOUTH MONOLITH (not dewatering)

      - Install new mechanical meter at south end. (Riggers)

      - Install SLEDS by 28 Feb 11

    - Inspect Washington shore exit trashrack. (Riggers)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect, repair, and clean picket leads. (Riggers/Painters)

    - Inspect/repair crowder (Riggers/Painters)

    - Replace current crowder brush with a smaller one and make necessary mechanical changes.  (Mechanics).

    - Fabricate and install picket lead sill ramp. (Riggers)

    - Install ¾ inch crowder picket lead (NOAA)

    - Install engineered anchor point by crowder (Riggers)

    - Pressure wash algae off LPS as soon as dewatered (Painters)

    - Clean count window. (Painters)

    - Pressure wash algae and moss in and around fishway and remove larger debris (Painters)

    - Replace/repair research equipment (U of I)

    - Start bringing WA shore ladder back in service  17 Feb 11

    - Install SLEDS by 28 Feb 11

    - Paint No Parking area at North Monolith for new LPS (Painters)

  - Bradford Island Ladder (A&B-Branches)- NOT GOING OOS

    - Construct new Bradford Island fish exit trashrack.

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Calibrate CC, TW, and entrance gate transducers.

    - Move LPS pumps inside the ladder behind screen (Mechanics).

    - Pressure wash algae off LPS (Painters)

    - Remove weeds near PIT tag room and transceiver enclosures. (Garage)

    - Inspect/repair B-branch conduit sensor, TR 09-244039 (Electricians).

    - Inspect B-Branch entrance and PH1 PCC 05 Jan 11 (ROV inspection)

    - Install SLEDS by 28 Feb 10

- JUVENILE FISHWAYS

  - B2 Corner Collector  (31 Aug 10 – 01 Mar 11)

    - Remove mice from the pull box between the PIT tag building and the Electrical building and possibly set traps for future occupants.

    - Inspect seals around antennae and skid plates.

    - Inspect channel (Tech staff/Fisheries)

    - Install bulkhead hoist.  (contractor)

  - ITS (Not going OOS)

    - Weld elevation markers on chain gates 3C, 6C, and 10B. (Riggers)

  - Juvenile Monitoring Facility (31 Oct 10 – 21 Feb 11)

    - Blow out hydro cannon lines on 15 Sep 10 (Operators)

    - Switch to bypass, drain and inspect sample flume on 31 Oct 10. (Project Fisheries)

    - Winterize truck release site when releases have concluded (Operators)

    - Replace overhead ball valve on truck release site pipe (Mechanics)

    - Inspect and PM equipment- air pressure gauges and oil/water traps.

    - Inspect flume joints.  Re-caulk as needed.

    - Inspect and winterize 2 and 3 way rotating gates.

    - Replace charcoal filters.

    - Inspect/Repair lifting cables for the fish lifts.  (Riggers)

    - Inspect seals on upper and lower switch gates.

    - Clean sediment and solids out of 1000 gal anesthetic water holding tank in basement.

  - DSM 2 (15 Dec 10 – 21 Feb 11)

    - Inspect/replace orifice lenses prior to dewatering.

    - Turn off orifice lights on 13 Dec 10

    - Pull STSs 15-16 Dec 10

    - Dewater DSM on 20 Dec 10

    - Inspect two mile pipe on 21 Dec 10

    - Inspect and repair VBS seals.  (Riggers)

    - PM equipment.

    - Inspect/Repair screen cleaners.  Airburst and mechanical.

    - Inspect orifice stem/gate connection.

    - Rebuild orifice valve cylinders (Mechanics)

    - Escape hatch sign installation (Painters)

    - Tie end of 17B release pipe to bottom of DSM walkway. (Riggers/Fisheries)

    - Water up on 15 Feb 11

    - Install STSs starting 15 Feb 11

- SPILLWAY

  - Test all gates.

  - Repair gate 15 hoist.

KEY TO COLORS-

Black- normal/routine dewatering work

Orange- work to be done by contractors or researchers.                  Blue- work to be done by Fisheries

Pink- highlights special requests or non-routine work items.             Gray- completed items.