Adult Fish Passage Facilities – 2010-11 Winter Maintenance Schedule

U. S.  Army Corps of Engineers

Walla Walla District

MCNARY DAM - Washington Shore Fishway

- Dewater the WA fish ladder from February 1 to February 28 for maintenance.  Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect diffuser gratings with video camera.  If voids are found, divers will be summoned to repair.

- Perform annual maintenance on the WASCO small hydro project, bypass and auxiliary water supply system.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Maintain half-duplex PIT (lamprey) antennas.  Coordinate with University of Idaho.

- Resume normal operation of the ladder and small hydro/auxiliary water system by February 28.

MCNARY DAM - Oregon Shore Fishway

- Shut down AWS pumps 1, 2, and 3 at sundown on January 1 and place ladder on orifice flow.

- Dewater the fish ladder from January 3 to January 31 for extensive maintenance on fish pumps, installation of new auxiliary intake traveling screens at ladder exit.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by a combination of underwater diving. 1

- Perform routine winter maintenance on all three AWS fish pumps, and dewater fish pump number 2 for inspection and maintenance.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Resume normal ladder flow and pump operation on January 31.

ICE HARBOR DAM - North Shore Fishway

- Shut down the AWS pumps on January 1

- Dewater the fish ladder from January 3 – January 14 for maintenance.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by underwater video. 1

- Perform maintenance on the AWS pumps.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Resume normal operation of the AWS pumps on January 14

ICE HARBOR DAM - South Shore Fishway

- Shut down the AWS pumps on the morning of January 15.

- Dewater the fish ladder from January 18 – February 25 for maintenance.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by underwater video. 1

- Perform maintenance on the AWS pumps.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Maintain half-duplex PIT (lamprey) antennas.  Coordinate with University of Idaho.

- Resume normal operation of the AWS pumps on February 25.

LOWER MONUMENTAL DAM - North Shore Fishway

- Shut down the AWS pumps on the morning of January 2.

- Dewater the fish ladder from January 5 - 28 for maintenance.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.  See footnote on page 1.

- Perform maintenance on the AWS pumps.

- Resume normal operation of the AWS pumps on January 28.

LOWER MONUMENTAL DAM - South Shore Fishway

- Dewater the fish ladder from February 2 – February 28 for maintenance.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.  See footnote on page 1.

LITTLE GOOSE DAM

- Shut down the AWS pumps on the morning of January 1.

- Dewater the fish ladder from January 3 through February 27 for maintenance. (Including contractor work to permanently close NPE3 and NSE3)

- Dewater collection channel from January 4 – February 27 for maintenance (including contractor work to permanently close NPE3 and NSE3).  Collection channel may be dewatered in two sections independently, Powerhouse Section and Spillway Section, depending on contractor work requirements/progress.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.  See footnote on page 1.

- Perform maintenance on the AWS pumps.

- Inspect and repair the adult fish fallout fence, and diffusers gratings.

- Repair/replace light fixtures in adult channel.

- Resume normal operation of the AWS pumps on February 28.

# LOWER GRANITE DAM

- Shut down the AWS pumps on the morning of December 31.

- Dewater the fish ladder from January 3 – February 25.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.

- Perform maintenance on the AWS pumps. Repair / replace picketed leads, lift 1.5 inches.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Inspect the adult fish fallout fence.

- Inspect and repair areas within the adult fish trap.

- Replace the diffuser 13 sluice gate.

- Replace the diffuser 14 grating.

- Resume normal operation of the AWS pumps no later than February 26.

Table 1.  Methods used to inspect adult fishway collection channels during past winter maintenance periods, compared to the upcoming winter period.

|  | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008 -09 | 2009-10 | 2010-11 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MCN WA Shore | Dewatering | Dewatering |  | Dewatering | Dewatering |  |  |
| MCN OR Shore | Underwater video or diver? | Underwater video or diver | Dewatering | Video and dive | Dewatering |  |  |
| IHR North Shore | Underwater video | Dewatering | Underwater video | Underwater video | Diver inspected | Underwater video |  |
| IHR South Shore | Underwater video | Underwater video | Dewatering | Underwater video | Underwater video | Dewatering |  |
| LMO North Shore | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering |  |
| LMO South Shore | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering |  |
| LGO | Underwater video | Dewatering | Underwater video then dewatering | Dewatering | Dewatering | Dewatering |  |
| LGR | Dewatering | Dewatering | Dewatering | Underwater video | Dewatering | Dewatering |  |

.