# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER FISHWAY MAINTENANCE 2010/2011.

- This is a working document detailing Bonneville Dam winter fishway maintenance, 2010/2011.  Reviewers can expect changes as we approach the winter maintenance season.

- ADULT FISHWAYS

  - Fish Unit Outages

    - Fish Unit 1: 15 Nov 10 – 28 Feb 11, annual overhaul.

    - Fish Unit 2: 15 Nov 10 – 28 Feb 11, annual overhaul.

  - Adult Fish Facility (01 Nov 10 – 1 Apr 11)

    - Go to orifice flow on 01 Nov 10

    - Dewater exit section on 02 Nov 10

    - Dewater entrance on 02 Nov 10

    - Install FERL bulkhead 08 Nov 10

    - Routine maintenance.

    - PM bridge crane.  Replace wire rope.

    - Repair broken gate cranks and pulleys.

    - Inspect and repair weir doors.

    - Clean fish viewing window.  (Painters)

    - HSS inspect AFF valve 1, 2, and 3. (Tech staff)

    - Replace sample flume rubber lining (Mechanics)

    - Pressure wash the lab and handrails. (Painters)

    - Inspect/Replace silicone around the anesthetic tank bottom.  (Painters)

    - Secure bottom of temperature probe stillwell.  (Electricians)

    - Replace broken timbers in exit section with bulkhead.  (Riggers)

    - Repair/Replace netting over flumes. (Project Fisheries)

    - Relocate bridle storage rack (Riggers)

  - Washington Shore Ladder (15 Nov 10 – 24 Feb 11)

    - Install FOG stab plates/bulkheads week of 8 Nov 10.

    - Go to orifice flow on 15 Nov 10

    - Dewater to tailwater on 17 Nov 10.

    - Install entrance bulkhead 17 Nov 10

    - Dewater entrance section 18 Nov 10

    - Remove avian wires late October, reinstall early March (USDA)

    - NDE lamprey modifications

    - Paint No Parking area at North Monolith for new LPS (Painters)

    - Inspect Washington shore exit trashrack. (Riggers)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect, repair, and clean picket leads. (Riggers/Painters)

    - Inspect/repair crowder (Riggers/Painters)

    - Fabricate and install picket lead lip ramp. (Riggers)

    - Move existing lamprey plating in junction pool adjacent to wall (Riggers/Garage)

    - Install new crowder picket leads (NOAA)

    - Install engineered anchor point by crowder (Riggers)

    - Pressure wash algae off LPS as soon as dewatered (Painters)

    - Clean count window. (Painters)

    - Pressure wash algae and moss in and around fishway and remove larger debris (Painters)

    - Install new mechanical meter at south end. (Riggers)

    - Inspect and repair north monolith expansion joints (Tech staff/Riggers)

    - Replace missing diffuser strap at SUE (Riggers)

    - Replace/repair research equipment (U of I)

    - Install SLEDS or acoustic deterrents by 28 Feb 11

  - Cascades Island Ladder and UMT  (04 Dec 10 – 24 Feb 11)

    - Open barrier at count station on 01 Nov 10

    - Orifice flow 15 Nov 10 until UMT is cleared and south end bulkhead lowered

    - Drop south end UMT bulkhead 15 Nov 10 chase fish from UMT to CI ladder, drop bulkhead behind

    - Pull UMT picket leads on 15 Nov 10

    - Open fish exit on 15 Nov 10

    - Go to orifice flow on 03 Dec 10

    - Drain ladder to tailwater on 06 Dec 10

    - Install bulkheads and drain below tailwater  07 Dec 10

    - Remove large vegetation around fishways (blackberry bushes). (Garage)

    - Pressure wash algae and moss in and around fishway (Painters)

    - Inspect/repair fishway exit trashrack (Riggers/Painters)

    - Remove side entrance weir between fishway and Spillbay 1, add bumpers to bulkhead or replace with concrete bulkhead (Riggers) 2012

    - Clean crowder. (Painters)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect FV5-3 conduit (Riggers/Tech staff)

    - Replace/repair research equipment (U of I)

    - Install SLEDS or acoustic deterrents by 28 Feb 11

  - Bradford Island Ladder (A&B-Branches)

    - Inspect Bradford Island exit trashrack.

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Remove avian wires late October, reinstall early March (USDA)

    - Move LPS pumps inside the ladder behind screen (Mechanics).

    - Pressure wash algae off LPS (Painters)

    - Remove weeds near PIT tag room and transceiver enclosures. (Garage)

    - Inspect/repair B-branch conduit sensor, TR 09-244039 (Electricians).

    - Repair gravel road adjacent to B-branch for 2011/12 dewatering

    - Dredge BI fish exit.  2010/2011 (contractor)

    - Inspect PH1 PCC 05 Jan 11 (ROV inspection)

    - Install SLEDS or acoustic deterrents by 01 Feb 10

A-Branch specific items (Not going OOS)

    - Calibrate CC, TW, and entrance gate transducers.

    - Repair/clean/replace all staff gages (Riggers/Painters)

B-Branch specific items (Not going OOS)

    - Calibrate CC, TW, and entrance gate transducers.

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect entrance pool 05 Jan 11.  (ROV inspection)

    - Remove side entrance weir between fishway and Spillbay 18, add bumpers to bulkhead or replace with concrete bulkhead (Riggers)

- JUVENILE FISHWAYS

  - B2 Corner Collector  (31 Aug 10 – 01 Mar 11)

    - Remove mice from the pull box between the PIT tag building and the Electrical building and possibly set traps for future occupants.

    - Inspect seals around antennae and skid plates.

    - Inspect channel (Tech staff/Fisheries)

    - Remove avian wires late October, reinstall early March (USDA)

    - Remove avian wire anchor line 15 Nov 10 (Riggers/Konnowack)

    - Reinstall avian wire anchor line 01 March 11 (Riggers/Konnowack)

    - PM avian wire anchor line drum/winch (Riggers/Mechanics)

    - Install bulkhead hoist.  (contractor)

  - ITS (Not going OOS)

    - Weld elevation markers on chain gates 3C, 6C, and 10B. (Riggers)

  - Juvenile Monitoring Facility (31 Oct 10 – 21 Feb 11)

    - Blow out hydro cannon lines on 01 Sep 10 (Operators)

    - Switch to bypass, drain and inspect sample flume on 31 Oct 10. (Project Fisheries)

    - Winterize truck release site when releases have concluded (Operators)

    - Inspect and PM equipment- air pressure gauges and oil/water traps.

    - Inspect flume joints.  Re-caulk as needed.

    - Inspect and winterize 2 and 3 way rotating gates.

    - Replace charcoal filters.

    - Inspect/Repair lifting cables for the fish lifts.  (Riggers)

    - Inspect seals on upper switchgate.

    - Clean sediment and solids out of 1000 gal anesthetic water holding tank in basement.

  - DSM 2 (15 Dec 10 – 19 Feb 11)

    - Turn off orifice lights on 13 Dec 10

    - Pull STSs 15-16 Dec 10

    - Dewater DSM on 20 Dec 10

    - Inspect two mile pipe on 21 Dec 10

    - Inspect and repair VBS seals.  (Riggers)

    - PM equipment.

    - Inspect/Repair screen cleaners.  Airburst and mechanical.

    - Inspect/replace orifice lenses.

    - Inspect orifice stem/gate connection.

    - Attach the channel end of the 17 B release pipe. (Riggers/Fisheries)

    - Install STSs starting 21 Feb 11

    - Water up when STSs are installed (not later than 28 Feb 11)

- SPILLWAY

  - Test all gates.

  - Repair gate 15 hoist.

KEY TO COLORS-

Black- normal/routine dewatering work

Orange- work to be done by contractors or researchers.

Blue- work to be done by Fisheries

Pink- highlights special requests or non-routine work items.

Gray- completed items.

Green- items to keep on the radar but postponed for a future in-water work season.