Draft1

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2010/2011

## East Fish Ladder				-Dewater	Dec. 1, ’10 – Jan. 14, ‘11

- PM count station  and exit weirs (TDM, TDE)

- Seal 2 leaking expansion joints and joint over fish office (Eng)

- Replace diffuser grating lower ladder (Eng, TDS)

- Lift count station pickets 1” (TDS)

- Renumber exit staff gages (TDS)

- Clean Stillwell ports (?)

- Redo 158-9 weir flaps (TDS)

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Dec. 2, ‘10

- Replace JP, E Entrance diffuser grating (TDS)

- PM entrance weirs (TDM, TDE, TDS)

- Install new S1 weir (TDS)

- Complete FSQ6 replace (Eng)

- Clear stillwell ports ?

## Juvenile Bypass System			-Inspect	Dec-Feb

- Inspect flume spalling d/s endgate (TDF) Endgate HSS?

## North Fish Ladder                             	- Dewater     	Feb 7, ‘11

- PM count station  and exit weirs (TDM, TDE)

- Seal leaking count station expansion joint (Eng)

- Lift count station pickets 1” (TDS)

- Continue brush removal (TDF)

- Remove lamprey trap count station diffuser (TDF)

## Fishlock Flow Test				-Operate	Feb 8, “11

- Pull exit bulkheads, close culdesac bulkheads, install pickets JP (TDS)

- Open valves (TDO)

- Analyze hydraulic conditions (TDF)

North Entrance				-Dewater 	Feb 9, ‘11

- Inspect diffuser grating (Eng)

- Clear Stillwell ports  ?