# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER FISHWAY MAINTENANCE 2011/2012.

- This is a working document detailing Bonneville Dam winter fishway maintenance, 2011/2012.  Reviewers can expect changes as we approach the winter maintenance season.

- ADULT FISHWAYS

  - Fish Unit Outages

    - Fish Unit 1: At 0001 on 14 Oct 11 – 05 Dec 11, annual overhaul.

    - Fish Unit 2: At 0001 on 14 Oct 11 – 05 Dec 11, annual overhaul.

    - Fish Unit bulkhead installation

  - Adult Fish Facility (13 Oct 11 – 1 Apr 12)

    - AFF to orifice flow on 12 Oct 11

    - Dewater exit section and lab to AFF ladder entrance on 13 Oct 11

    - Dewater entrance on 17 Oct 11

    - Routine maintenance.

    - PM bridge crane.

    - Repair broken gate cranks and pulleys.

    - Inspect and repair weir doors.

    - Clean fish viewing window.  (Painters)

    - Inspect AFF valves 1, 2, and 3. (Mechanics)

    - Pressure wash the lab and handrails. (Painters)

    - Inspect/Replace silicone around the anesthetic tank bottom.  (WDFW)

    - Repair/Replace netting over flumes. (Project Fisheries)

  - Cascades Island Ladder and UMT  (Not going OOS)

    - Remove large vegetation around fishways (blackberry bushes). (Garage)

    - Inspect/repair fishway exit trashrack (Riggers/Painters)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Slot filler hanger installation (Riggers)

    - Install SLEDS by 28 Feb 12.

  - Washington Shore Ladder (14 Oct 11 – 05 Dec 11)

    - SOUTH MONOLITH

      - Fish Unit 1 and 2 out of service at 0001 14 Oct 11.

      - Support divers, install SDE, SUE, and Transverse bulkhead south of Unit 11 on week of 17 Oct 11.

      - Dewater/fish salvage south monolith and south AWS on week of 17 Oct 11.

      - Maintenance and repair of B diffusers on week of 24 Oct 11. (Riggers)

      - Water back up on 5-6 Dec 11.

      - Install new mechanical velocity meter at south end. (Riggers)

      - Install SLEDS by 28 Feb 12.

    - NORTH MONOLITH

      - Fish Unit 1 and 2 out of service at 0001 14 Oct 11.

      - Go to orifice flow on 14 Oct 11.  Dewater WA shore ladder bulkhead (at Y junction) to weir 50.

      - Dewater north monolith - weir 50 to tailwater on 17 Oct 11.

      - NDE, SDE, and Transverse bulkhead install north of Unit 18 on 31 Oct - 03 Nov 11.

      - Dewater/fish salvage entrance section below tail water 02-07 Nov 11.

      - AWS dewatering on week of 07 Nov 11.

      - Debris removal and repairs 08-30 Nov 11.

      - Pull bulkheads 01-05 Dec 11.

      - Water back up on 5-6 Dec 11.

      - Inspect north monolith expansion joints (Tech staff/Riggers)

      - Install SLEDS by 28 Feb 12.

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect, repair, and clean picket leads. (Riggers/Painters)

    - Pressure wash algae off LPS as soon as dewatered (Painters)

    - Replace/repair research equipment (U of I, NOAA, PTAGIS)

    - Start bringing WA shore ladder back in service week of 05 Dec.

    - Install SLEDS by 28 Feb 12.

  - Bradford Island Ladder (A&B-Branches)-

    - B-Branch orifice flow on 16 Sept.  Dewatered from Junction pool to tailwater on 17 Sept.

    - B-branch valve/grating/etc. maintenance and repair 07-31 Dec. 11.

    - A-Branch orifice flow on 03 Jan 12.

    - A-Branch dewater to tailwater 05 Jan 12.

    - Install transverse bulkheads at Unit 8/pump down collection channel. FV1-1 bulkhead install. 06-12 Jan 12.

    - Dewater below tailwater 13 Jan 12.

    - Inspect/repair/clean diffuser grating and diffuser pits of debris in collection channel 14-28 Jan 12.  (Riggers)

    - Repair broken diffuser gates and shafts in collection channel 14-28 Jan 12.  (Riggers)

    - Inspect/repair/clean diffuser grating and diffuser pits of debris in A-branch 30 Jan-11 Feb 12.  (Riggers)

    - Repair broken diffuser gates and shafts in A-branch 14-28 Jan 12.  (Riggers)

    - Repair/clean/replace all staff gages (Riggers/Painters)

    - Inspect picket leads.  (Fisheries/Riggers).

    - Mark picket leads/framework to ensure proper seating visually from walkway.

    - Make 1 inch space under leads uniform.

    - Inspect Bradford Island fish exit trashrack.  (Fisheries/Riggers)

    - Replace AWS pressure transducer (under 55 deck roadway) (Electricians)

    - Adjust count window crowder brush/ new brush. (Mechanics)

    - Install auto cleaning cycle for BIVC viewing window cleaning brushes. (Electricians)

    - Install shad/salmon mode control for FV 3-9. (Electricians)

    - Clean/paint border of crowder.  (Painters)

    - Calibrate CC, TW, and entrance gate transducers. (Electricians)

    - Move LPS pumps inside the ladder behind screen (Mechanics).

    - Pressure wash algae off LPS (Painters)

    - Remove weeds near PIT tag room and transceiver enclosures. (Garage)

    - Inspect/repair B-branch conduit sensor, TR 09-244039 (Electricians).

    - Install SLEDS by 28 Feb 12.

- JUVENILE FISHWAYS

  - B2 Corner Collector  (31 Aug 11 – 01 Mar 12)

    - Inspect seals around antennae and skid plates.

    - Inspect channel (Tech staff/Fisheries)

    - Investigate raising B2CC avian wire array anchor point on Cascades Island.

    - Install bulkhead hoist.  (contractor)

  - PH1 ITS (Not going OOS)

    - No maintenance

  - Juvenile Monitoring Facility (31 Oct 11 – 27 Feb 12)

    - Switch to bypass, drain and inspect sample flume on 31 Oct 10. (Project Fisheries)

    - Blow out hydro cannon lines on 03 Nov 11 (Operators)

    - Winterize truck release site when releases have concluded (Operators)

    - Inspect and PM equipment- air pressure gauges and oil/water traps.

    - Inspect flume joints. (Fisheries)  Re-caulk as needed. (Painters)

    - Inspect and winterize 2 and 3 way rotating gates.

    - Replace charcoal filters.  (Mechanics)

    - Inspect/Repair lifting cables for the fish lifts.  (Riggers)

    - Inspect seals on upper and lower switch gates. (Fisheries)

    - Clean sediment and solids out of 1000 gal anesthetic water holding tank in basement.

  - DSM 2 (31 Oct 11 – 27 Feb 12)

    - Turn off orifice lights on 28 Oct 11.

    - Pull STSs 31 Oct-03 Nov 11.

    - Dewater DSM on 03 Nov 11.

    - Inspect two mile pipe on 10 Jan 12.

    - Inspect and repair VBS seals.  (Riggers)

    - PM equipment.

    - Inspect/Repair screen cleaners.  Airburst and mechanical.

    - Inspect orifice stem/gate connection.

    - Rebuild orifice valve cylinders (Mechanics)

    - Water up in bypass on 20 Feb 12

    - Install STSs starting 20 Feb 12

    - Inspect/replace orifice lenses after water-up.

- SPILLWAY

  - Test all gates.

  - Repair gate 15 hoist.

KEY TO COLORS-

Black- normal/routine dewatering work

Orange- work to be done by contractors or researchers.                  Blue- work to be done by Fisheries

Red- highlights special requests or non-routine work items.             Gray- completed items.