Adult Fish Passage Facilities – 2011-12 Winter Maintenance Schedule

U. S.  Army Corps of Engineers

Walla Walla District

MCNARY DAM1 - Washington Shore Fishway

- Dewater the WA fish ladder down to the tailwater level from February 1 to February 28 for maintenance.  Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect diffuser gratings with video camera.

- Perform annual maintenance on the WASCO small hydro project, bypass and auxiliary water supply system.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Maintain half-duplex PIT (lamprey) antennas.  Coordinate with University of Idaho.

- Resume normal operation of the ladder and small hydro/auxiliary water system by February 28.

MCNARY DAM1 - Oregon Shore Fishway

- Shut down AWS Fish Pumps 1 and 3 at sundown on January 1 and place ladder on orifice flow.

- Perform routine winter maintenance on AWS Fish Pumps 1 and 3.  Complete the ongoing extensive overhaul of Fish Pump #2 and remove the fish pump stop logs.

- Place exit stop logs, perform physical inspection of upper ladder and rov camera inspection of the watered sections of the lower ladder.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Resume normal ladder flow and pump operation on January 31.

ICE HARBOR DAM1 - North Shore Fishway

- Shut down the AWS pumps on January 27

- Dewater the fish ladder from January 30 – February 24 for maintenance and lamprey improvement contractor work.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by visual inspection. 1

- Perform maintenance on the AWS pumps.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Maintain half-duplex PIT (lamprey) antennas.  Coordinate with University of Idaho.

- Resume normal operation of the AWS pumps on February 25

ICE HARBOR DAM1 - South Shore Fishway

- Shut down the AWS pumps on the morning of December 31.

- Dewater the fish ladder from January 3 – January 27 for maintenance and lamprey improvement contractor work.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by underwater video. 1

- Perform maintenance on the AWS pumps.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Maintain half-duplex PIT (lamprey) antennas.  Coordinate with University of Idaho.

- Resume normal operation of the AWS pumps on January 28.

LOWER MONUMENTAL DAM1 - North Shore Fishway

- Shut down the AWS pumps on the morning of January 1.

- Dewater the fish ladder from January 2 - 31 for maintenance and contractor installation of adult lamprey passage improvements.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.

- Perform maintenance on the AWS pumps.

- Resume normal operation of the AWS pumps on January 27.

LOWER MONUMENTAL DAM1 - South Shore Fishway

- Dewater the fish ladder from February 1 – February 28 for maintenance and contractor installation of adult lamprey passage improvements.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.

LITTLE GOOSE DAM1

- Shut down the AWS pumps on the morning of January 3, 2012.

- Dewater the fish ladder from January 3 through February 16, 2012 for maintenance.

- Close fish entrance weirs after fish ladder dewatered, January 3, 2012.

- Dewater collection channel from January 9 – February 15, 2012 for inspection and maintenance.

- Inspect / repair the adult fish fallout fence

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Resume normal operation of the AWS pumps on February 16, 2012.

# LOWER GRANITE DAM1

- Shut down the AWS pumps on the morning of December 31.

- Dewater the fish ladder from January 3 – February 27.

- Complete winter maintenance according to the Fish Passage Plan, Section 2.3.2.1.

- Inspect the collection channel by dewatering.

- Replace diffuser gratings throughout the fishway as needed (extensive work).

- Perform maintenance on the AWS pumps.  Repair/replace picketed leads.

- Maintain adult PIT tag system as required.  Coordinate with PSMFC.

- Inspect the adult fallout fence and repair as needed.

- Inspect and repair areas within the adult fish trap.

- Repair the cleaning brush system on the public fish viewing window.

- Resume normal operation of the AWS pumps no later than February 29.

Table 1.  Methods used to inspect adult fishway collection channels during past winter maintenance periods, compared to the upcoming winter period.

.

|  | 2006-07 | 2007-08 | 2008 -09 | 2009-10 | 2010-11 | 2011-12 |
| --- | --- | --- | --- | --- | --- | --- |
| MCN WA Shore |  | Dewatering | Dewatering |  | Diver / Inspected |  |
| MCN OR Shore | Dewatering | Video and dive | Dewatering | Diver / Inspected |  |  |
| IHR North Shore | Underwater video | Underwater video | Diver inspected | Underwater video | Dewatering |  |
| IHR South Shore | Dewatering | Underwater video | Underwater video | Dewatering | Dewatering |  |
| LMO North Shore | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering |  |
| LMO South Shore | Dewatering | Dewatering | Dewatering | Dewatering | Dewatering |  |
| LGO | Underwater video then dewatering | Dewatering | Dewatering | Dewatering | Dewatering |  |
| LGR | Dewatering | Underwater video | Dewatering | Dewatering | Dewatering |  |

.