Draft

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2011/2012

## Fishlock Flow Test				-Operate	Nov, ‘11

- Install channel bulkheads and dewater (TDS)

- Clean pipes (Eng) - contract

- Run fish lock and test (Eng, TDO) 			Jan. 2, ‘12

## East Fish Ladder				-Dewater	Dec. 5, ’11

- PM count station  and exit weirs (TDM, TDE)

- Inspect/repair joint over fish office (Eng) Contract

- Resume grating installation (Eng, TDS)

- Renumber exit staff gages (TDF)

- Clean Stillwell ports (TDM)

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Dec. 6, ‘11

- PM entrance weirs (TDM, TDE, TDS)

- Install new S1 weir (TDS)

- Complete FSQ6 replace (Eng)

- Clear stillwell ports (TDM)

## Juvenile Bypass System			-Inspect	Dec-Feb

- Inspect flume spalling d/s endgate (TDF)

## North Fish Ladder                             	- Dewater     	Jan. 16, ‘12

- PM count station  and exit weirs (TDM, TDE)

- Re paint count station floor (TDM)

- Continue brush removal (TDF)

- Check count station grating clips (TDS)

North Entrance				-Dewater 	Jan 17, ‘12

- Inspect diffuser grating (Eng)

- Clear Stillwell ports  (TDM)