Bonneville Corner Collector PIT Tag Monitoring Test – Entrance Hydrofoils

Professional Services Contract Proposed Schedule

| Action | Approximate Dates |
| --- | --- |
| Award | July 1 2013 |
| Pre-work coordination meeting | July 8-12, 2013 |
| ###### TASK 1 |  |
| ###### Determine compatibility and/or interference issues between an unshielded system similar to the hydrofoil concept system and existing B2CC PIT-tag detection system. | July 2013 |
| ###### TASK 2 |  |
| ###### Evaluate the physical performance of the prototype forebay PIT-tag detection concept in the lab. | July 2013 |
| ###### Complete and submit a feasibility report of results for Task 1 and 2. | August 31 2013 |
| ###### TASK 3 |  |
| ##### Design, fabricate, and evaluate in the lab a prototype forebay PIT-tag detection system that uses the multiple hydrofoil antennas. | September 2013-January 2014 |
| TASK 4 |  |
| Install monitoring equipment (i.e. hydroacoustic equipment or DIDSON camera) to evaluate the horizontal and vertical passage distribution of fish entering the B2CC. | February 2014 |
| TASK 5 |  |
| Install the prototype forebay PIT-tag detection system infrastructure (i.e. transceivers and power supplies) that was designed in Task 3 to detect PIT-tagged fish entering the B2CC. | February 2014 |
| TASK 6 |  |
| Evaluate the horizontal and vertical distribution of smolts passing into the B2CC using an appropriate technology with the corner collector operating and the prototype forebay PIT-tag detection system installed. | March 1-April 7, 2014 |
| TASK 7 |  |
| Evaluate the physical performance of the prototype forebay PIT-tag detection system in the field with the B2CC operational. | March 1-April 7, 2014 |
| TASK 8 |  |
| Evaluate the horizontal and vertical distribution of smolts passing into the B2CC using an appropriate technology with the corner collector operating and the prototype forebay PIT-tag detection system not installed. | April 9-May 10, 2014 |
| Remove monitoring equipment and prototype forebay PIT-tag detection system. | September 2014 |
| TASK 9 |  |
| Analyze, and compare the horizontal and vertical distribution of smolts passing into the B2CC collected under Task 6 and 8 to determine if the prototype forebay PIT-tag system affects passage into the B2CC. | May 11-July 1, 2014 |
| TASK 10 |  |
| Prepare reports and present study findings. (Task 1 and 2) | August-December 2013 |
| Prepare reports and present study findings. (Task 3 through 8) | August-December 2014 |
| Preliminary Report Due | October 1, 2014 |
| Final Report Due | December 15, 2014 |