OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- Lower Granite Juvenile Fish Collection Channel Upgrades

COORDINATION DATE-  September 10, 2013

PROJECT- Lower Granite

RESPONSE DATE- September 12, 2013 FPOM meeting

Description of the problem

Construction activities associated with the Lower Granite fish bypass system upgrade will require extensive onsite efforts over an approximate 36 to 86 month construction schedule.  While many of the construction activities can occur during normal project operations, some activities may require alteration of normal project operations.  The time necessary for completion of construction activities will be directly correlated with the construction methods employed.  The existing collection channel within the powerhouse will require extensive concrete mining to expand the channel from 6 ft. to 9.5 ft. and the potential replacement of 10” orifices with 14”orifices.  The construction method for concrete mining has yet to be determined but the USACE is approximating 6-10 months to complete the task which likely translates into three un-watered work windows (15 December to 24 March).  On the other end of the spectrum for construction schedules, a single un-watered work window of 1 August to 24 March is anticipated to allow for construction activities without interruption and benefit the collection mining process.  All potentially anticipated construction scenarios have various pros and cons on project operations, fish passage, and overall project costs.

The USACE’s Fish Passage Plan (2013) calls for the collection channel to be operated from 25 March to 31 October for juvenile passage and collection and 1 November to 15 December for adult fallback passage.  Spill operations typically begin 2 April and end 31 August.   The proposed extended un-watered work window would alter the normal operations of the collection channel and as a result limit the available passage routes to the spillway and turbines during the month of August.  Available passage route for September to December would be via the turbines.   The Corps proposes that the RSW operate from 1 September to 15 December to allow alternate passage routes for juvenile and adult salmonids.  The RSW would operate under the following scenario:

- Operate the RSW 12 hours per day (6am to 6pm) from 1 September to 15 December.

Operating the RSW during the extended un-watered work window would require discharge through the RSW of 6.83 kcfs.  During low to average river flow years, minimum generation requirements through the turbines may result in a lack of water to operate the RSW and maintain minimum operating pool.  In that case, the RSW would need to be closed and spill distributed among the other bays.

Table 1. – Average inflows and turbine discharge at Lower Granite Dam, 2006 to 2012.  Inflow and powerhouse discharge are reported as kcfs.

| Month | Inflow (kcfs) | Powerhouse (kcfs) |
| --- | --- | --- |
| August | 31.05 | 13.20 |
| September | 24.77 | 23.95 |
| October | 21.07 | 20.60 |
| November | 21.73 | 20.70 |
| December | 24.03 | 23.65 |

Type of outage required

The removal of ESBS’s and the closure of the collection channel from 1 August 2015 to 24 March 2016.  Unit outages to dip fish out of the corresponding gatewell slots will be needed at least every 48 hours when fish are going into the slots.  Open the RSW for fish passage from 1 September to 15 December.

Impact on facility operation

The impact to facility is the early closure of the collection channel and the de-watering of the Juvenile Fish Facility in August 2015 instead of December as typical.  Fish may enter the gatewells even with ESBSs removed, which would require dipping of fish from the gatewell slots during the August 1 to December 15 period.  Maximum fish holding time in the gatewell slots is 48 hours.  This would require unit outages to dip the corresponding gatewells.

Dates of impacts/repairs

1 August 2015 to 24 March 2016

Length of time for repairs

The construction of the Juvenile Bypass System is anticipated to begin in the fall of 2014 with completion in the spring of 2016.  The extended un-watered work window is expected to occur from 1 August 2015 to 24 March 2016.

Expected impacts on fish passage

The closure of the collection channel may impact juvenile salmonids (Table 2) and adult fallbacks (Table 3) and require the passage through the spillway or turbines.  Fish that are entrained in the gatewells will need to be dipped out and transported to the boat ramp for release downstream of the dam.

Table 2. – Juvenile salmonid collection at Lower Granite Dam Juvenile Fish Facility, 2006 to 2012.  Data collected by USACE.

| Year | August | September | October |
| --- | --- | --- | --- |
| 2006 | 1,841 | 2,107 | 4,219 |
| 2007 | 2,056 | 1,124 | 10,407 |
| 2008 | 21,047 | 9,220 | 8,731 |
| 2009 | 3,044 | 2,002 | 2,115 |
| 2010 | 8,907 | 8,436 | 11,436 |
| 2011 | 6,498 | 14,307 | 5,721 |
| 2012 | 8,121 | 6,443 | 12,255 |

Adult fish passage will tailrace flow conditions will need to be monitored.  If necessary, unit operation or spill distribution and timing may need to be adaptively managed as appropriate, within the constraints of water availability, to improve adult fish passage conditions.

Table 3. – Adult salmonid fallback at Lower Granite Dam, 2006 to 2012.  Data collected by USACE personnel as adult salmonids cross the JFF separator.

| Year | August | September | October |
| --- | --- | --- | --- |
| 2006 | 51 | 335 | 630 |
| 2007 | 67 | 270 | 846 |
| 2008 | 275 | 798 | 2,253 |
| 2009 | 247 | 3,462 | 2,940 |
| 2010 | 477 | 1,202 | 1,919 |
| 2011 | 179 | 1,547 | 2,787 |
| 2012 | 81 | 752 | 2,090 |

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Scott Fielding

Fishery Biologist

US Army Corps of Engineers

201 North 3rd Avenue

Walla Walla, WA 99362

509-527-7236

John C. Bailey

Fishery Biologist

US Army Corps of Engineers

Walla Walla District

Operations Division

201 N. 3rd St

Walla Walla. WA 99362-1876

Phone: (509) 527-7123

Fax:   (509) 527-7823

Email: john.c.bailey@usace.army.mil