Draft 2

JOHN DAY DAM FISHWAYS’ ANNUAL DEWATER SCHEDULE

WINTER 2013/2014

## North Fish Ladder, upper 			-Dewater        Dec. 2, ’13 – Dec. 16, ’13

- Orifice flow starts  at 2100 hrs on Nov.30,  keep control weirs closed until 12/2

- PM count station  and exit weirs (JDM,JDE)

- Level window cleaner and adjust it for proper operation (JDM)

- Re-attach  CS upstream staff gauges correctly

- AWS pumps inspection & annual maintenance

- Repair loose brackets at the “third” orifices; may want to use larger plates bolted to concrete instead (same as JD South) – JD Structural

## North Entrance				- ROV only this year    Dec. 4 or 5, ’13

- Inspect all gratings and fix deficiencies if found

- AWS pumps inspection & annual maintenance

North AWS Channel                                   - None this year

- Engineering inspection

SMF 						-Dewater 	Nov. 26, ’13

- PMs and cleanup

- Seal water leak in the transport flume, upstream of switch gate- JDM

## Juvenile Bypass System			-Dewater	Mid Jan, ’14?

- Repair flume spalling

- Search for all metal strips/brackets to assure their structural integrity.

- Inspect conduit (Engineering)

- PM all SMF equipment and tainter gate (JDM, JDE)

South Turbine Bulkhead Install		-ROV inspect	  Jan.6, ‘14

- Inspect sill before and proper seal after bulkhead installation

- Inspect inside penstock - JDM

## South Fish Ladder, upper                            - Dewater        Jan 7, ’14 – Feb. 28, ‘14

- Orifice flow on January 5 at 1800 hrs, keep control weirs closed until 1/7 AM.

- PM count station equipment and exit sills (JDM,JDE)

## South Entrance, Collection channel	- Dewater        Jan.  9, ‘14

- Replace SE1 weir with  new to assure it fits  (old weir becomes spare) – JD Structural

- PM SE1, NE1/2 entrance weirs (JDM, JDE)

- Inspect all gratings and fix deficiencies if found

- SE1 wall diffuser – seal off this year? (JDM, Engineering)

- Inspect diffuser valves (JDM, Engineering)

- Three lowest overflow weirs need to be removed (this year?)

- Lamprey walkways/plates over diffusers between overflow weirs :  Contract -  POC Mackintosh

- Demob and remove butterfly gates hardware from collection channel – Engineering and JD Structural planning for this year or future?

South AWS conduit                                    - Dewater         Jan. 13, ‘14

- Inspect and remove accumulated mussel shells if necessary – JD Structural

Engineering to determine if accumulated shells are impacting AWS performance?

- PH leak repair contract will require access to work inside – JD Engineering

## South fish turbine intake trashrack install	-ROV 		End of Feb, ‘14

- Inspect sill & clean debris before trashrack installation

- Inspect forebay north and south diffuser intakes

## Guidelines:

- Adult winter maintenance (outage) season is Dec 1 through Feb 28.

- Juvenile winter maintenance (outage) season is Dec 1 through March 31.

- One adult ladder in regular service at all times when the second one is OOS for winter maintenance. Any overlapping outages (two ladders OOS at the same time)

are required to be coordinated in advance with FPOM.