Draft 9/02/15

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2015/2016

## North/South entrance sill and North grating inspect	-Dive		Nov 18, ‘15

## Coordinate logistics – TDF

- Inspect diffuser grating -TDF

## North Fish Ladder                             	- Dewater     	Nov 16, ’15 – Nov 30, ‘15

- PM count station  and diffuser valve (TDM, TDE)

- Re-secure count station floor (TDF)

- PM entrance weirs (TDM, TDE, TDS)

- PM diffuser valves (TDM)

## East Fish Ladder 				-Dewater	Dec. 1, ’15 – Feb 28, ‘16

- Inspect exit weirs (TDS, TDM)

- PM count station  and replace brush(TDM, TDE, TDS)

- Renumber exit staff gages (TDF)?

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Dec. 2, ’15 – Feb 28, ‘16

- PM entrance weirs (TDM, TDE, TDS)

- Remove gearboxes JP1,3,5 weirs (TDM, TDS)

- PM diffuser valves, excluding collection channel (TDM)

- Replace remaining entrance weir wheels (TDS, Eng)

- Replace E2 guides (TDS)

- Inspect all grating (TDS)

- Collection channel pumps?

- Evaluate south dewater pump? (TDS)

- Remove vegetation south channel (TDF)

Ice Trash Sluiceway				-Inspect	~Dec 16-Feb28

- Inspect flume spalling downstream endgate (TDF)

- PM endgate and sluicegates (TDS, TDM)

- Adjust new sluicegate settings (TDE, TDS)