OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 17TDA20 AWS October Start Revised

COORDINATION DATE- 8/9/2017

PROJECT- The Dalles Dam

RESPONSE DATE- 8/10/2017 August FPOM meeting

UPDATE:  FPOM concurred during the 14 July 2017 FPOM with working nights in November and the last 10 days of November starting at 1200. FPOM did not support work in October during day or night. Additional coordination is requested for 12-hour night shifts from 1800-0600 during Oct. 15-31 and day shifts during Nov. 12-20 starting at 1200.

The PDT and construction office discussed the schedule and identified remaining uncertainty surrounding the excavation of the 10 ft. valve room.  In addition, USACE desires to reduce risk to worker safety and increase efficiency by minimizing 24hrs/7 day per week, i.e., double shifts for extended periods.

The following MOC has been modified to address fish manager concerns by rearranging schedule to minimize fish impacts, expand on description of potential construction impacts, and continue FPOM coordination in an effort to complete contract work during the second IWW period.

Description of the problem

The AWS project is behind schedule after season 1 due to weather and differing site conditions. In attempts to complete the project in season 2, an early start is requested for some of the work items. November night work was approved for season 1. Without additional weather or differing site conditions, an additional 40 shifts need to be scheduled in order for the project to be completed.  In addition to the contractually awarded nights in November, nights are requested from October 15-October 31 and day shifts from November 12-20 are requested to perform in-water work for season 2. This totals 29 additional allowable shifts excluding Sundays.  Without this extension, the work could potentially continue to a third season.

Work Description:

All heavy construction and diving will be scheduled for night work. Work items for area 1 include installing forebay erection frame by barge and installing forebay steel anchor beams to dam face by barge and diver. Area 1 is ~30’ downstream from the east fish ladder exit.

UPDATE: All work identified in Area 1 will not be pursued during nights of Oct. 15-31 and days of Nov. 12-20.

Work items for area 3 include common earth excavation, dozer with ripper attachment, hydraulic hammering of concrete, and rock excavation for the 10’ pipe. Some of this work area is ~45’ from fish ladder.

UPDATE: Due to differing site conditions identified during Season 1, concrete beams are in the exact location of the common earth excavation.  The contractor must utilize additional time and effort to remove the concrete beams to stay on schedule.  Common earth excavation, using backhoe(s), bulldozers, dump trucks, etc. would occur from ground elevation (EL 111.5) until the locations of the concrete beams (EL 104).  At Elevation 104’, the distance to the fish ladder is approximately 48’.  Removal of the concrete beams would include hydraulic hammering of concrete and rock excavation.  Initial excavation of the common fill is requested to occur during nights of Oct. 15-31.  Hydraulic hammering of concrete is requested to occur during days of Nov. 12-20.

Work items for area 4 include common earth excavation for the 10’ penstock. This work varies from ~30’from the fish ladder at the 7’ valve room to ~40’ from the fish ladder at the 10’ valve room.

UPDATE: Excavation of common fill from the area will utilize heavy equipment, including dump trucks, backhoe, bull dozer, and track hoe.  These efforts are identical in nature to those performed in March 2017 in Work Area 5.  Little noise/vibration impact was observed during that time.  Common excavation efforts in this work area are requested to occur during nights of Oct. 15-31.

Work items for area 5 include crane to install valves and lids and electrical installation. This work is ~30 directly under the fish ladder.

UPDATE: All work identified in Area 5 will not be pursued during nights of Oct. 15-31 and days of Nov. 12-20.

Figure 1 - TDA AWS features and work areas

Type of outage required - No outage required.

Impact on facility operation (FPP deviations) - No operations changes.   	Working within 50 ft. of a fishway and within 100 ft. of an exit.

Impact on unit priority- None expected

Impact on forebay/tailwater operation - None expected

Impact on spill - None expected

Dates of impacts/repairs – Oct 15 – Nov 30, 2017

UPDATE:  Additional coordination for 12-hour night shifts from 1800-0600 during Oct. 15-31 and day shifts during Nov. 12-20 starting at 1200.

Length of time for repairs – 6 weeks overall

Analysis of potential impacts as a result of a 3rd construction season in FY19, TDA project impacts, and other contract work:

- Additional schedule - Due to impacts from Season 1, the Contractor will have to accelerate operations in work area 6, installation of the diffuser and 7’ penstock expansion joints. The Contractor will need to make up approximately 40 shifts during the fish ladder outage. Double shifted (24/7) work creates both a quality concern and a safety impact.  The level of effort in Quality Management is lost between change-out of crews from shift to shift.  Fatigue Management and employee cognizance is at risk and can result in both quality and safety issues.  This also takes a toll on employees’ moral. In addition, by directing acceleration and moving to a 24/7 or double shifted work schedule, the Contractor will experience a significant inefficiency factor, causing additional shifts to be incurred.

In addition to the work noted above, the Government must direct the Contractor to accelerate 40 shifts of work within work areas 3 & 4. In an attempt to mitigate the potential safety and quality impacts of working double shifts, the additionally requested shifts will allow acceleration of work to one type of activity at a time. This will allow staggering of night work between subcontractors and greater oversight by Contractor and Government quality and safety personnel.

- Work area 3 includes excavation of material not yet disturbed during this contract which includes a risk of additional differing conditions. Furthermore, the increased quality and safety risk associated with the anticipated double shifts in the fish ladder increase the likelihood of delays to contract work and decrease the amount of time left to react. Without extending the IWWP in addition to acceleration efforts, this contract has potential to extend into a third season during FY19.

- Currently there are numerous contracts scheduled and being planned for active construction at The Dalles Dam in the location of AWS Backup work during the IWWP of FY19:  Fish Unit Breaker, SR Panel Replacement, GSU Transformer, and Rail Road Removal.  If the East Fish Ladder is taken out of service for three consecutive years, the North Fish Ladder will have missed several opportunities for maintenance and rehabilitation.  Each of these projects has the potential for cost and schedule impacts by extending TDA AWS into a third season.

Analysis of potential impacts to fish

- Table 1 shows the 10 year average passage for all chinook, all steelhead, coho, and lamprey during October, with average counts during Oct. 15-31 bolded (DART data).  Average daily passage through the north ladder is less numerous than the east ladder.  Approximately 5-20% pass the north fish ladder and are not exposed to the work area.  Chinook, steelhead, and coho passage numbers decline through Oct. with very few lamprey passing after Oct. 15.

Table 1 – TDA October average daily passage, 2005-2016

| Date | All Chinook | All steelhead | Coho | Lamprey |
| --- | --- | --- | --- | --- |
| 1-Oct | 3648 | 3345 | 749 | 6 |
| 2-Oct | 3562 | 2968 | 757 | 2 |
| 3-Oct | 3472 | 2744 | 771 | 1 |
| 4-Oct | 2882 | 2073 | 597 |  |
| 5-Oct | 3022 | 2181 | 692 |  |
| 6-Oct | 2937 | 2200 | 808 | 4 |
| 7-Oct | 2369 | 1905 | 855 |  |
| 8-Oct | 1937 | 1667 | 604 | 2 |
| 9-Oct | 1950 | 1494 | 376 | 1 |
| 10-Oct | 2264 | 1243 | 272 | 1 |
| 11-Oct | 2186 | 1445 | 481 | 1 |
| 12-Oct | 1885 | 1397 | 834 |  |
| 13-Oct | 1582 | 1321 | 632 | 1 |
| 14-Oct | 1234 | 973 | 322 | 1 |
| 15-Oct | 1173 | 1083 | 555 |  |
| 16-Oct | 1318 | 1336 | 810 |  |
| 17-Oct | 1031 | 1120 | 774 |  |
| 18-Oct | 910 | 826 | 401 |  |
| 19-Oct | 755 | 810 | 530 | -1 |
| 20-Oct | 805 | 902 | 482 |  |
| 21-Oct | 606 | 668 | 198 |  |
| 22-Oct | 665 | 661 | 149 |  |
| 23-Oct | 579 | 524 | 183 |  |
| 24-Oct | 533 | 605 | 344 |  |
| 25-Oct | 514 | 501 | 233 |  |
| 26-Oct | 446 | 467 | 170 |  |
| 27-Oct | 382 | 509 | 159 |  |
| 28-Oct | 335 | 506 | 189 |  |
| 29-Oct | 295 | 332 | 108 |  |
| 30-Oct | 250 | 316 | 116 | 1 |
| 31-Oct | 230 | 292 | 67 |  |

- November night work was previously analyzed for season 1 (USACE count data). For day work in November, the average counts are listed with Nov. 12-20 bolded in Table 2.   Average daily passage through the north ladder is less numerous than the east ladder.  Approximately 5-20% pass the north fish ladder and are not exposed to the work area.  Chinook, steelhead, and coho passage numbers continue to decline through Nov.

Table 2 - TDA-E and TDA-N November average daily passage, 2003-2007 and 2012

| Date | All Chinook TDA-E TDA-N |  | All Steelhead TDA-E TDA-N |  | All Coho TDA-E TDA-N |  | Total Fish TDA-E TDA-N |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1-Nov | 190 | 18 | 248 | 30 | 159 | 28 | 1193 | 152 |
| 2-Nov | 148 | 15 | 221 | 21 | 66 | 17 | 871 | 105 |
| 3-Nov | 130 | 14 | 220 | 19 | 49 | 6 | 799 | 77 |
| 4-Nov | 124 | 16 | 254 | 28 | 113 | 27 | 980 | 141 |
| 5-Nov | 111 | 17 | 223 | 24 | 119 | 15 | 905 | 113 |
| 6-Nov | 125 | 17 | 208 | 18 | 70 | 9 | 804 | 86 |
| 7-Nov | 110 | 13 | 180 | 10 | 33 | 8 | 647 | 60 |
| 8-Nov | 71 | 11 | 125 | 9 | 25 | 5 | 444 | 50 |
| 9-Nov | 71 | 10 | 153 | 13 | 17 | 2 | 482 | 51 |
| 10-Nov | 60 | 11 | 138 | 12 | 8 | 3 | 414 | 51 |
| 11-Nov | 54 | 6 | 163 | 15 | 9 | 3 | 452 | 47 |
| 12-Nov | 52 | 7 | 160 | 11 | 18 | 6 | 459 | 47 |
| 13-Nov | 51 | 6 | 198 | 11 | 12 | 7 | 524 | 47 |
| 14-Nov | 46 | 5 | 200 | 10 | 8 | 1 | 510 | 30 |
| 15-Nov | 42 | 5 | 240 | 10 | 8 | 1 | 579 | 32 |
| 16-Nov | 39 | 7 | 207 | 13 | 5 | 1 | 252 | 21 |
| 17-Nov | 34 | 13 | 163 | 39 | 9 | 4 | 206 | 56 |
| 18-Nov | 30 | 4 | 149 | 8 | 16 | 3 | 195 | 15 |
| 19-Nov | 27 | 5 | 140 | 11 | 9 | 4 | 176 | 20 |
| 20-Nov | 23 | 4 | 139 | 7 | 7 | 2 | 170 | 13 |
| 21-Nov | 23 | 6 | 108 | 5 | 4 | 0 | 135 | 11 |
| 22-Nov | 16 | 7 | 106 | 7 | 4 | 1 | 126 | 15 |
| 23-Nov | 19 | 2 | 101 | 4 | 2 | 0 | 121 | 6 |
| 24-Nov | 16 | 3 | 68 | 7 | 3 | 1 | 86 | 11 |
| 25-Nov | 14 | 4 | 77 | 6 | 5 | 1 | 96 | 11 |
| 26-Nov | 15 | 2 | 64 | 8 | 3 | 1 | 82 | 11 |
| 27-Nov | 10 | 1 | 50 | 5 | 4 | -1 | 64 | 6 |
| 28-Nov | 9 | 2 | 42 | 3 | 1 | 0 | 52 | 4 |
| 29-Nov | 6 | 2 | 28 | 4 | 0 | 0 | 35 | 6 |
| 30-Nov | 8 | 3 | 26 | 5 | 1 | 0 | 35 | 8 |

- The NOAA forecast is lower than 10 year average.

- There is no night passage data for October and November available.

Summary statement - expected impacts on:

Upstream migrants (including Bull Trout)

Given the trends in passage over recent years, it is possible that chinook, steelhead and coho could experience some delay if elevated levels of vibration or noise were detectable by fish.  The levels of noise or vibration from the activity in October and November in work areas 3 and 4 are not well understood regarding the ability of fish to detect with negative responses when passing the TDA-E.

Any fish that are in the area during nights Oct. 15-31 may experience some delay in passage if present in TDA-E.  It is possible that fish may back down the ladder or exit to the forebay.  If they back down overnight, it is expected that passage will resume during the day under typical project operating conditions.

Any fish that are present during the day after 1200 during Nov. 12-20 may experience some delay at the TDA-E.  It is possible that fish may back down the ladder or exit to the forebay if they react to work in the area.  Delaying the start times until 1200 allows significant time for fish to pass during daytime hours without the potential impacts from construction.  Those that back down may also utilize the north ladder as an alternate route.

Given the type of work based on last year’s observations, work areas and distance from the ladder, as well as scheduling work to not be continuous, the noise and/or vibration impacts on adult salmonids in the worst case are expected to be short term (<24 hrs) and non-lethal.

Downstream migrants - There are no downstream migrants near this location.

Lamprey - There is no expected lamprey impact, there is generally no lamprey 	passage after October 15.

Comments from agencies

Final coordination results – Minutes from 14 July 2017 FPOM

6.18  17TDA20 MOC AWS October Start – Due delays caused by the weather problems last year, the project is proposing starting in October for night work, November nights and daytime work the last two weeks of November. There are three areas for working. Area 1 is on the forebay side and with eddy recirculation, the water comes right down to the east fish ladder exit. Area 3 and 4 are near the east entrance. Fredricks is very concerned about working in October right under the ladder. FPOM concurred with working nights in November and the last 10 days of November starting at noon but not in October.

After Action update (After action statement stating what the effect of the action was on listed species. This statement could simply state that the MOC analysis was correct and the action went as expected, or it could explain how the actual action changed the expected effect (e.g., you didn’t need to close that AWS valve after all, so there was no impact of the action).  List any actual mortality noted as a result of the action)

Please email or call with questions or concerns.

Thank you,

Erin

Erin Kovalchuk

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

Erin.H.Kovalchuk@usace.army.mil

Bob Cordie

Chief of Fisheries

The Dalles Dam

Robert.P.Cordie@usace.army.mil

Jon Rerecich

Fish Passage Section

Environmental Resources Branch

503-808-4779

Jonathan.g.rerecich@usace.army.mil