Lower Columbia River Forebay Temperature Monitoring – Phase 1 and Phase 2 Scope of Work

# Purpose

There is regional interest in more rigorous monitoring of water temperatures in the forebays and within the fish ladders of the three Lower Columbia River (LCR) Dams - John Day, The Dalles and Bonneville. This stems from concerns regarding fish ladder water temperature differentials and subsequent delayed migration of adult salmonids. A water temperature data collection effort is currently being carried out by the Walla Walla District to monitor conditions at the lower four Snake River Dams and McNary Dam; efforts should be standardized across both Districts to the extent possible.

# Current Water Temperature Monitoring

Water temperatures are currently monitored at the LCR dams mid-fish ladder as well as upstream and downstream of each dam at the Total Dissolved Gas (TDG) Fixed Monitoring Stations (FMS) (Table 1).

Table . Current Water Temperature Monitoring Locations, LCR Dams

|  |  |  |
| --- | --- | --- |
| **ID** | **Monitor Type** | **Location** |
| JDAAN1 | Hobo Temperature Monitor | North Exit Pool |
| JDAAN2 | Hobo Temperature Monitor | North Entrance Pool |
| JDAAS1 | Hobo Temperature Monitor | South Exit Pool |
| JDAAS2 | Hobo Temperature Monitor | South Entrance Pool |
| JDY | TDG Temperature Monitor | Forebay Temperature |
| JHAW | TDG Temperature Monitor | Tailwater Temperature |
| TDAAN1 | Hobo Temperature Monitor | North Ladder Count Station |
| TDAAE1 (TDA) | TDG Temperature Monitor | Forebay Temperature |
| TDDO | TDG Temperature Monitor | Tailwater Temperature |
| TDAAE2 | Hobo Temperature Monitor | East Ladder Count Station |
| BONAB1 | Temperature Monitor | Bradford Island Count Station |
| BONAN1 | Temperature Monitor | Washington Shore Count Station |
| BONAN2 | Temperature Monitor | Washington Shore Adult Fish Facility downstream return pool |
| BONAL1 | Temperature Monitor | Bradford Island Lamprey Passage Structure, near exit |
| BONAL2 | Temperature Monitor | Cascade Island Lamprey Passage Structure |
| BONAL3 | Temperature Monitor | Washington Shore Auxiliary Water Supply Lamprey Passage Structure |
| BONAL4 | Temperature Monitor | Washington Shore North Downstream Entrance Lamprey Flume/Passage System |
| BON | TDG Temperature Monitor | Forebay Temperature |
| CCIW | TDG Temperature Monitor | Tailwater Temperature |
| WRNO | TDG Temperature Monitor | Tailwater Temperature |

Thermal profile data is not currently monitored in the LCR dam forebays. Past data indicates that there is a lack of reservoir thermal stratification, so instead, hourly point measurements collected by each FMS has been used to track forebay water temperature conditions at the dams.

# Proposed Water Temperature Monitoring

There has been a resurgence in tracking forebay water temperatures, especially as they relate to potential water temperature problems within the fish ladders at the LCR dams. For that reason, additional water temperature probes will be added to the entrances and exits of each fish ladder located at Bonneville, The Dalles and John Day dams. These instruments will be deployed, maintained and downloaded by project staff. Data will be submitted to the Fish Passage Center (FPC) for upload onto their publically accessible website (<http://www.fpc.org/river/Q_ladderwatertempgraph.php>).

The forebay water temperature monitoring is expected to be more involved and will therefore be contracted out. Option 2 was chosen from three options of data collection methods for the Bonneville, The Dalles and John Day Dams. This is the most practical choice with more flexibility for determining the location of the temperature profile strings. However, the Regional participants of the Fish Passage Operations and Maintenance (FPOM) coordination team concluded that a brief study should be conducted first to determine the most suitable locations for the temperature profile monitoring (Phase 1). The Phase 1 portion of the water temperature monitoring shall be conducted in late summer of 2017; Phase 2, the installation of the temperature strings and platforms, shall occur the following year in 2018. The study should be conducted for at least one week during the hotter portion of the summer, possibly in August. The Corps may perform the work in-house, rather than contract out, and utilize the Walla Walla District Water Quality staff, in which case, the IGE may need to be updated. The IGE does not include annual maintenance for following years.

**Option 2 – Phase 1: Temperature Depth Profile Monitoring Study (manually collected data)**

To help determine the most suitable location of the water temperature monitoring equipment platforms for 2018, the contractor shall first install up to four temporary temperature depth profile sites at the John Day and The Dalles forebays, and up to eight sites at the Bonneville forebay (four at two different fish ladder exists). One set of thermistors (Onset Hobos ® or similar) will be used at each site. Water temperature data shall be monitored at 1 ft, 5 ft, 10, ft, 20 ft, 40 ft, 60 ft, and 80 ft from surface, on an hourly time interval. The data will be manually downloaded at the end of the study. These sites will be installed during the hotter portion of the summer, possibly in mid - August, and will collect data for a minimum of one week. A longer study may be warranted if the temperatures or wind conditions are more variable the following weeks, so that a variation in conditions can be monitored. This will not affect the cost of the study.

Ideally, the monitoring sites should be located where the coolest water resides and preferably closer to the following main fish ladder exists and within ten feet or so from the dam or on the actual dam (Tammy Mackey may provide a maximum distance from the fish ladders that the projects are willing to pump water from):

* John Day - South fish ladder
* The Dalles – East fish ladder
* Bonneville - Washington shore and Bradford Island (include both for study).

In addition, a monitor site will be close to each main fish ladder exist during the study so that the data from the other temperature sample sites can be compared to it. If the contractor determines that temperatures do not vary laterally, the platform will be placed closer to the main fish ladder or on the dam structure. Originally the sample locations were going to be located upstream of boat restriction zone (BRZ) for Bonneville and The Dalles Dams; however, it is preferred that they are closer to the fish ladders at all dams so that the distance to pump the water is not as great. There can be significant fluctuations in temperatures near the powerhouse and inlets, so these areas will be avoided. As a result of this study, in 2018 a real – time data collection temperature string (TempLine) platform will be installed at each forebay. These costs could be significantly lower if the temperature strings could be mounted to the dam structure or upstream of the BRZ; however, it is important to have the string near potentially cooler water and the fish ladder exist. The following is a web link to the BRZ access requirements and restrictions: <http://www.nwd-wc.usace.army.mil/tmt/documents/FPOM/2010/NWP%20Research/Research.html>

All necessary equipment required for the temporary deployment of water temperature equipment - including boats, trailers and deployment materials (stainless steel cables, buoys, cable clamps, buoys, etc.) - shall be supplied by the contractor or the Corps if work is performed in-house.

All visits to reservoirs and thermistor deployment locations shall be coordinated with the respective project staff. All safety training and requirements shall be completed prior to deployment of equipment.

**Phase 1 Study - Option 2 - Estimated Cost within BRZ: $90,000 (outside of BRZ ~ $55,000).**

**Option 2 – Phase 2: Floating Platform with (Real-time) Data Collection**

Contractor shall install permanent water temperature monitoring equipment in the forebays of The Dalles and Bonneville dams using real-time water temperature equipment (NexSens® or similar), along with one set of back-up thermistors (Onset Hobos ® or similar) in case of templine failure. Water temperature instrumentation will be deployed on platform buoys built by the Contractor and location of deployment will depend on the Phase I study results. Originally they were going to be installed immediately upstream of BRZ of the reservoir; however, closer to the fish ladders is preferred (Figure 1).

 

Figure 1. Photographs of the water quality platforms located in the Willamette Basin.

Water temperature data shall be monitored at 1 ft, 5 ft, 10, ft, 20 ft, 40 ft, 60 ft, and 80 ft from surface, on an hourly time interval. Data will be collected real-time and broadcasted via GOES satellite to the Portland District’s Corps Water Management System (CWMS) database that is maintained by the Portland District Reservoir Regulation & Water Quality Section.

Data transmission equipment, including the DCP, GOES link, and antennae will be provided by Portland District, however, deployment, programming and ensured functionality will be the responsibility of the Contractor. Water temperature equipment shall be checked and calibrated at least twice during the year, preferably in the fall and again in the spring before the spill season begins. All services to the templines should be completed on site, as feasible, as these are permanent temperature monitoring locations. Thermistor strings will be downloaded manually by the Contractor at the same time the templines are being serviced.

Temperature data that is transmitted to the Portland District via GOES will be shared with the FPC for upload onto their publically accessible website; this is the District’s responsibility. Any data manually downloaded by the Contractor should be emailed to both the FPC and the Portland District water quality staff for upload onto respective websites. All field notes and meta data such as site location, site name and latitude/longitude shall also be emailed as well.

All necessary equipment required for the deployment of water temperature equipment - including boats, trailers and deployment materials (stainless steel cables, cable clamps, buoys, etc.) - shall be supplied by the contractor.

All visits to reservoirs and thermistor deployment locations shall be coordinated with the respective project staff. All safety training and requirements shall be completed prior to deployment of equipment.

**Phase 2 - Option 2 - Estimated Cost: $165,000. Actual costs will be higher if within BRZ.**