Draft 10/2/17

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2017/2018

## East Fish Ladder 				-Dewater	Dec 1, ’17 – Feb 28, ‘18

- Inspect exit weirs

- Rehab weir 155 and 156 gearbox

- PM count station

- FCQ7 install continuation

- Continue expansion joint seal as needed

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Dec 2, ’17 – Feb 28, ‘18

- PM entrance weirs

- PM diffuser valves, excluding collection channel

- Install weir caps on W1, W2, W3, S1, S2 (Moorings fab)

- Rehab sticking west weir W1 (cable drum issue)

- Inspect all grating

- Collection channel pump remove repair

- Assess diffuser valves and remove P1-1 stem

## North Fish Ladder                             	- Dewater     	Jan 16, ’18 – Jan 30, ‘18

- PM count station  and diffuser valve

- PM entrance weirs

- PM diffuser valves

- Trim trees (Crane access/rescue team drill)

- Replace window brush

- Replace leaking window brush motor (refer to oil WO)

- Install weir car on N1 and spare (Moorings fab)

- Repair oil leaking diffuser valve at count station

- Install cable trays in count station

North Entrance				-Dewater	Jan 17, ’18 – Jan 30, ‘18

- PM entrance weir

- Inspect grating

- Install weir caps on N1

Ice Trash Sluiceway				-Inspect	~Dec 16, ’17 - Feb28, ‘18

- Inspect flume spalling downstream endgate

- PM endgate and sluicegates

- Adjust new sluicegate settings

- Spray blocker updgrade