**Spillway PIT-Construction Schedule as of 12/12/19**

|  |  |
| --- | --- |
| **Date** | **Activity** |
| 30-Oct | Concrete pour - South Bottom below Antenna zone |
| 31-Oct | Set Lower Conex |
| 1-Nov | Concrete pour - North Bottom below Antenna zone |
| 3-Nov | Set Upper Conex |
| 11/5-11/19 | Install side shields |
| 13-Nov | Deliver antennas |
| 14-Nov | Transceiver room commissioning |
| 15-Nov | Transceiver room complete |
| 11/15-11/22 | Antenna Installation |
| 11/18-12/4 | PSMFC Testing and Tuning |
| 12/5 | Site Visit Prior to Antennas Encased in Concrete |
| 12/9-12/10 | **Full System Test-No issues found can move forward with antenna zone concrete** |
| 13-Dec | Concrete pour - South Antenna Zone **weather dependent** decision made Thursday 2/12 (12/16 alternate date) |
| 16-Dec | Concrete pour - North Antenna Zone **weather dependent** |
| 12/12-12/18 | Concrete cure |
| 12/20-1/6 | Concrete wetting and PSMFC monitoring |
| 1/6-1/10 | PSMFC wet & dry test buried antennas |
| 13-Jan | Remove bulkhead |
| 1/26 | Spill test 8 hours |
| 1/28-1/30 | PSMFC inspect & tuning |
| 1/31 | Spill test 6 hours |
| 2/2-2/4 | PSMFC inspect & tuning |
| 2/6 | Spill test 4 hours |
| 2/8-2/10 | PSMFC inspect & tuning |
| 15-Mar | Project Complete (if all goes well could be as early as mid-February) |