## Sheet1
FPOM Transmission Outages That Have Potential to Limit Generation March-May 2019
ONGOING Continuous Outages 2019- 2020
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
N/A
MARCH - 2019 (45 day outage planning process completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (6:30)-3/7/19 (17:00) | Continuous | TDA Units 5-8 OOS | BPA- Connect T3 CT circuit
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (8:00)-3/7/19 (17:00) | Continuous | TDA Units 5-8 OOS | USACE work- Arc flash mitigation
The Dalles PH-Big Eddy 4 230kV Line OOS | 3/11/2019 (8:00)-3/21/19 (18:00) | Continuous | TDA Units 9-12 OOS | USACE work- Pre-work for T5 replacement
The Dalles PH-Big Eddy 6 230kV Line OOS | 3/25/2019 (8:00)-4/02/19 (17:00) | Continuous | TDA Units 17-22 OOS | USACE work- Arc flash mitigation
APRIL - 2019 (Tentative: 45 day outage planning process completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH-Big Eddy 6 230kV Line OOS | 3/25/2019 (8:00)-4/02/19 (17:00) | Continuous | TDA Units 17-22 OOS | USACE work- Arc flash mitigation
Big Eddy: 230kV Main Bus Section 1 OOS | 2019-04-11 | 6:00-21:00 | TD Units 5-8 OOS | USACE work- 230kV main bus service
The Dalles PH-Big Eddy 2 115kV Line OOS | 4/15/19 (9:00)- 4/25/19 (17:00) | Continuous | TDA Units 3-4 OOS | USACE work- Arc flash mitigation
Hatwai-Dworshak 1 500kV Line OOS | 4/22/19 (9:30)- 5/09/19 (17:00) | Continuous | Hatwai PH 1 OOS | USACE work- Replacement of Ground Switch
McNary PH-McNary 6 115kV Line OOS | 4/17/19 (8:00)- 4/19/19 (16:00) | Continuous | MCN Units 13, 14 & Fishway OOS | To pull conductor from 115/69kV bank #10
MCNARY: 115KV MAIN BUS SECTION 2 | 2019-04-25 | 8:30-16:00 | MCN Units 13 & 14 OOS | To restore bus sections to service
MAY - 2019 (45 day outage planning process NOT completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
Hatwai-Dworshak 1 500kV Line OOS | 4/22/19 (9:30)- 5/09/19 (17:00) | Continuous | Hatwai PH 1 OOS | USACE work- Replacement of Ground Switch