**Spillway PIT-Construction Schedule as of 11/6/19**

|  |  |
| --- | --- |
| **Date** | **Activity** |
| 30-Oct | Concrete pour - South Bottom below Antenna zone |
| 31-Oct | Set Lower Conex |
| 1-Nov | Concrete pour - North Bottom below Antenna zone |
| 1-Nov | Deliver antennas |
| 3-Nov | Set Upper Conex |
| 11-Nov | Transceiver room complete |
| 11/5-11/13 | Install side shields |
| 11/16-11/21 | Antenna Installation |
| 11/18-12/4 | PSMFC Testing and Tuning **Best Time to Visit Prior to Antennas Encased in Concrete** |
| 10-Dec | Concrete pour - North Antenna Zone |
| 12-Dec | Concrete pour - South Antenna Zone |
| 12/12-12/18 | Concrete cure |
| 12/19-1/6 | Concrete wetting and PSMFC monitoring |
| 1/6-1/10 | PSMFC wet and dry test buried antennas |
| 13-Jan | Remove bulkhead |
| 1/20-1/21 | Spill test |
| 1/20-1/22 | PSMFC inspect and final tuning |
| 15-Mar | Project Complete |