# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2017/2018.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.

KEY TO COLORS:

Red - Painters

Blue – Mechanics

Pink – Riggers

Green – Garage

Orange – Electricians

Aqua- Fisheries

Yellow- Contractors or Researchers

- OREGON SIDE

  - Bradford Island Ladder – (30 Nov 19 – 27 Feb 20)

Orifice flow on Saturday, Nov 30th

Dewater A-branch and B-branch to tailwater on Monday, Dec 2nd & Tuesday, Dec 3rd

Dewater PH1CC past tailwater on Wednesday, Dec 4th and Thursday, Dec 5th

    - FG3-3 through FG3-9 (A-branch):

      - FG3-5 OOS since 28-Mar-19.

    - FG3-18 through FG3-33 (B-branch):

      - FG3-27 Caution Card.

    - FV1-1 / FV1-2:

    - FV3-7:

    - FV3-9:

    - FV4-3:

    - FV4-4:

    - FG2-4 through FG2-22B (PH1CC):

    - WG1/2:

    - WG64/65:

    - PH1 ITS:

    - SG4-N / SG4-S (B-branch):

    - Pressure wash fishways, remove vegetation on top of weirs, A-Branch!!! (GAR or PNT)

    - Remove BI Wetted Wall? (MPH1)

    - Pressure wash BI LPS and exit chute (GAR or PNT)

    - Repair or replace FV 1-1 AWS level sensor

- WASHINGTON SIDE - Not dewatering 2019/20.

  - Cascades Island – (Dewater on 10 Dec 19)

PSMFC inspection 11 Dec

ROV inspection during winter 15-16 Jan?

  - Washington Shore Ladder – Not dewatering

ROV inspection during winter 15-16 Jan?

  - PH2CC, North and South entrances – Not dewatering

ROV inspection during winter 15-16 Jan?

  - B2 Corner Collector  (01 Sept 2019 – Mar 2020)

    - Check/repair PIT antenna joints (FISH/PNT) 09 Sept

  - DSM 2 (15 Dec – 28 Feb 2020)

    - Turn off orifice lights on Saturday, Dec 14th?

    - Dewater DSM on Sunday, Dec 15th?

    - Pull STSs week of Dec 16th – 19th?

    - STS repairs / maintenance.

    - 2-mile pipe inspection Wednesday, Jan 22nd?

    - Install STSs starting week of Feb 17th 2020?

- RESEARCH FACILITIES

  - Adult Fish Facility (Nov – late Mar / early Apr)

Go to orifice flow on Monday, Nov 18th?

Dewater on Tuesday, Nov 19th?

    - Replace seals in fill station.

  - Smolt Monitoring Facility (31 Oct – 28 Feb)

Switch to bypass, drain and inspect sample flume on 31 Oct (PSMFC)

    - Will update once Dean sends up his annual list for maintenance.

  - Lamprey Passage Systems (01 Nov – 01 Apr)

    - Turn off systems, check rest boxes, and dewater 31 Oct

    - Pull pumps week of 04 Nov

    - Power wash accessible surfaces

    - WA Shore LPS cabinet repairs?

    - LFS hatch repairs