## Living Table
FPOM Transmission Outages Feb 2020 - April 2020
ONGOING Continuous Outages 2019- 2020
| Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
FEBRUARY - 2020 (45 day outage planning process completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
| BIG EDDY: A-824 TERMINAL OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 2/18/2020 (6:30) - 3/5/20 (00:00) | Continuous | The Dalles - Units 9-12 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 4 FOR T6 GSU INSTALLATION
| THE DALLES PH-BIG EDDY NO 4 230KV LINE | 2/10/20 (6:30) -2/20/20 (17:00) | Continuous | The Dalles - Units 9-12 | USACE Work - Terminal Clearance for XFMR GSU install
MARCH - 2020 (45 day outage planning process completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
| BIG EDDY: A-824 TERMINAL OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 2/18/2020 (6:30) - 3/5/20 (00:00) | Continuous | The Dalles - Units 9-12 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 4 FOR T6 GSU INSTALLATION
| BIG EDDY: PCB A-812 TERMINAL OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 3/2/2020 (6:30) - 3/5/20 (17:00) | Continuous | The Dalles - Units 5-8 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 3 FOR RESISTOR REPLACEMENT, BREATHER MAINTENANCE, & T4 BUSHING INSPECTION.
| BIG EDDY: PCB B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 3/9/20 (6:30) - 6/4/20 (17:00) | Continuous | The Dalles - Units 1, 2 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 1 FOR GSU 1 REPLACEMENT
| JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING MOD 4156 & PCB 4155 | 2020-03-26 | 8:00-16:00 | John Day - Units 5 - 8 | USACE Work - RECONNECT REMOVED BUS ON LINE SIDE AND PCB SIDE OF MOD 4156
APRIL - 2020 (45 day outage planning process NOT completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
| BIG EDDY: PCB B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 3/9/20 (6:30) - 6/4/20 (17:00) | Continuous | The Dalles - Units 1, 2 and Fish Units 1, 2 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 1 FOR GSU 1 REPLACEMENT
| THE DALLES PH-BIG EDDY NO 2 115KV LINE | 2020-04-01 | 8:00 - 11:30 | The Dalles - Units 3,4 | USACE Work - BLACK START TESTING MU4 AND L2
| JOHN DAY PH-JOHN DAY NO 3 500KV LINE INCLUDING PCB 4164 | 2020-04-14 | 8:00-16:00 | John Day - Units 9-12 | REMOVE BUS BETWEEN MOD 4165 AND THE JDPH 3 LINE IN PREPARATION FOR REPLACING MOD 4165