Very, very  Draft

10/1/20

THE DALLES DAM FISHWAY DEWATER SCHEDULE

AND NON-ROUTINE MAINTENANCE

WINTER 2020/2021

## East Fishway Fish Units			-Out service	Dec 1, ’20 -  Jan 9, ‘21

East Fish Ladder 				-Dewater	Dec 2, ’20 – Jan 14, ‘21

- Fill old bulkhead slot gap upstream 155 weir

- Seal count station leaks ?

- Continue 2 expansion joint seals (180 bend and 1 other)

- Close 158 seal gaps

## East Entrances, Coll and Trans Chan.	-ROV		Dec 3, ’20 – Jan 13, ‘21

- Install SCADA all entrances

- E1 calibration adjust for access

- Grating and weir inspect

## North Fish Ladder                             	- Dewater     	Jan 18, ‘21 – Feb 25, ‘21

- Trim trees 2 day crane

- Inspect PUD intake rack ROV

Pull north exit trashrack inspect?

- Repair/install exit boom and fix forebay staff gage

- Install new north count station diffuser valve

- Repair count station expansion joint

North Entrance				-Dewater	Jan 19, ’21 – Jan 21, ‘21

- Inspect grating

Ice Trash Sluiceway				-Dewater	~Dec 16, ’19 - Feb28, ‘20

- Contractor install spray roof

- Inspect flume downstream endgate