Update for Natalie Richards- 8/17/2011

Lamprey Program- 118738

| Meet with MOA Treaty Tribes-10-year Lamprey Plan | Sept 28, 2008 |
| --- | --- |
| Discussed Research needs Lamprey and Salmon | Feb and March 2009 |
| USACE Lamprey team meeting- PMP, 10-year Plan, 2010 estimated funds and FY09 | March 19 |
| Starting BONN Washington Shore- Kickoff Entrance Modification work | April 21 |
| Meet with MOA Treaty Tribes- 10 year Plan comments addressed and Prioritization | April 22 |
| 1-year Accord Celebration | May 8 |
| Lamprey Passage Efficiency- Cascade Island Ladder | June –July |
| USACE Lamprey team meeting | Aug 17 |
| USACE meet with CRITFC/ Tribes | Aug 18 |
| USACE Lamprey team meeting- NWW | Oct 28 |
| USACE meet with CRITFC/Tribes- 3 meetings-NWP, NWP, NWW | Oct 1 (COL), Oct 21 (COL), Oct 29 (Team) |
| NWP Meeting with CRITFC Tribes | 2/11/2010 at McNary Dam |
| NWP Lamprey Ranking Meeting-NWW | 3/24/2010 |
| Bi- Monthly Meeting- NWW | 9/2/2010 |
| Bi- Monthly Meeting- NWW | 10/29/2010 |
| Bi- Monthly Meeting | 1/14/2011 |
| Bi- Monthly Meeting | 3/11/2011 |
| Bi- Monthly Meeting-Portland | 5/20/2011 |
| Next- Bi- Monthly Meeting-NWW | 7/7-8/2011 |
| Juvenile Lamprey Workshop 8/18-19/2011-3A & B Bi- Monthly Meeting-NWW 9/8-9/2011 |  |

Issues-

- BONN WA Shores-Gravity Flow-100% DDR out for review, confirming team can meet schedule for a Notice To Proceed- July 2012

- FY11 Closeout $ coming- please move through quickly- awaiting NMFS

Adult Salmon and Steelhead Studies-118618- no change

John Day North Fish Ladder – 138171

Issues-

ARRA Fish Exit- processing As-Builts

Entrance

- Entrance-Out to bid for Full and Open competition, 10 Contractors interested, Site Visit-8/23/2011,

Working on Obligation/Notice To Proceed for end of FY11

- ARRA 13.8 KV Power-August 24 expected completion

- 6 Pumps, Power Controls and Housing-Model Testing/Design and Construction

  - Excavation, pouring concrete for electrical building and concrete coring into existing chamber

  - Testing Variable Frequency Drives which will be placed in the Electrical Building. Whole building will be brought up on a Barge

  - Out of Service Pump 4 will be opened up to assess corrosion issues 9/12/2011