Update for Natalie Richards- 12/5/2011

Lamprey Program- 118738

| Meet with MOA Treaty Tribes-10-year Lamprey Plan | Sept 28, 2008 |
| --- | --- |
| Discussed Research needs Lamprey and Salmon | Feb and March 2009 |
| USACE Lamprey team meeting- PMP, 10-year Plan, 2010 estimated funds and FY09 | March 19 |
| Starting BONN Washington Shore- Kickoff Entrance Modification work | April 21 |
| Meet with MOA Treaty Tribes- 10 year Plan comments addressed and Prioritization | April 22 |
| 1-year Accord Celebration | May 8 |
| Lamprey Passage Efficiency- Cascade Island Ladder | June –July |
| USACE Lamprey team meeting | Aug 17 |
| USACE meet with CRITFC/ Tribes | Aug 18 |
| USACE Lamprey team meeting- NWW | Oct 28 |
| USACE meet with CRITFC/Tribes- 3 meetings-NWP, NWP, NWW | Oct 1 (COL), Oct 21 (COL), Oct 29 (Team) |
| NWP Meeting with CRITFC Tribes | 2/11/2010 at McNary Dam |
| NWP Lamprey Ranking Meeting-NWW | 3/24/2010 |
| Bi- Monthly Meeting- NWW | 9/2/2010 |
| Bi- Monthly Meeting- NWW | 10/29/2010 |
| Bi- Monthly Meeting | 1/14/2011 |
| Bi- Monthly Meeting | 3/11/2011 |
| Bi- Monthly Meeting-Portland | 5/20/2011 |
| Next- Bi- Monthly Meeting-NWW | 7/7-8/2011 |
| Juvenile Lamprey Workshop –Room 3A | 8/18-19/2011 |
| Bi-Monthly FY12- please mark Fishery calendar | 1/12-13, 3/1-2, 5/31- 6/1, 9/6-7, 2012 |

Issues-

- Upper level Meeting with Gen McMahon and CRITFC in Dec 14 at CRITFC

- BONN WA Shores-Gravity Flow-Completed 60% Plans and Specifications-Going through Comments. AWS leakage contract is in conflict- working through issues

Adult Salmon and Steelhead Studies-118618- awaiting estimates for Kelt work

John Day North Fish Ladder – 138171

Issues- Fish Exit- ARRA-Completed training, finalizing the project

Entrance

- ARRA 13.8 KV Power - processing As-Builts

- Slayden- Mobilizing and planning to start in ladder early Dec

- 6 Pumps, Power Controls and Housing-Model Testing/Design and Construction

  - Electrical Building. Building is in place

  - Out of Service Pump 4 opened up- sand blast paint Contract Mod being negotiated

  - Out of Service Pump 3 next- fabricating head cover

  - Contractor know that  the ladder must be up and running in the 1st season even if that means using Pump #5 and #6 with a blockage

JDA (353193) &TDA PIT (353174) alternatives Study- 30% Report out for review through Dec 9 for team, to FFDRWG early January

Bradford Emergency Repair- Completed Oct 31- awaiting hydrosurvey results- discussing adding rock