Fish Facility Design Review Work Group

2 August 2012

John Day Lamprey Trap ( Count Station)

- Accelerated design and acquisition

- DDR 30% ready for review; 3 Aug DDR 90% 28 Sep

- P&S to construction 26 Nov

- Installation: 22 Jan – 1 Feb 13

B2 Corner Collector Channel Repair

- Concrete spalling repair is being scheduled for Sep/Oct 2012

- Comprehensive analysis and evaluation report under review.  The problem:

  - Thermal expansion contraction

  - Joints susceptible to hydraulic wear

  - Concrete Roughness attributed to hydraulic velocities

- Comprehensive repairs are being scheduled for next fall.  Solution:

  - using concrete and epoxy compounds to repair large spalled areas

  - Fill joints and/or bevel corners

Turbine Survival Program (Medina/Amman/Schwartz)

BIT document schedule slippage: Should be available for regional review in early September

B1 Bonneville ERDC model draft report should be available for review in September

B2 modeling for best operating point will start in September

Ice Harbor Runner Design is moving forward with 3rd iteration for fixed blade unit

External tag: preliminary results suggest tags work effectively

Sensor fish study for B2 et all: depleted supply of sensor fish.  Need to replace

JDA Configuration TSW Permanence (Medina/Hanson/Askelson/Tackley)

- TSW BCOE process complete, looking to award a contract in mid September

- Construction planned for next in-water work period

- Preparing O&M manuals for avail lines

The Dalles North and East Adult Fish Ladder Study - (Medina/Lee/Tackley)

- 90%  EDR ATR review to commence 15 August

- DDR scheduled to start early FY13;  P&S scheduled for FY13/FY14

- Construction contract award at the end of FY14 with construction in FY15

B2 FGE/Orifice Study (Medina/Lee/Schwartz)

- 90% report currently being drafted

- Recommendation

  - Field test turbulence reduction devise

  - Further investigate flow control devise

- Turbulence reduction device (TRD) completed BCOE and identified contractor

- Study plan being developed

- Will field test orifice lights with TRD