Update for Natalie Richards- 7/25/2012

CRFM

118738 Lamprey Program- Turned over Research to Mike Langeslay.

373409-BONN WA Shores-Gravity Flow-Awarded to Fowler- Preconstruction Conference was July 25

118618-Adult Salmon and Steelhead Studies-No change

138171-John Day North Fish Ladder

Entrance

Slayden- possible entrance undermining work

- Per the request of HD, ROV August 2 to see what damage has occurred.  Fix with CM?

- I think under the ladder is easily fixed but an eroded slope issue into the stilling basin is not.

Olsson-6 Pumps, Power Controls and Housing- Pumps #2-#4 are up and running ladder in criteria.

-Dive conducted 7/18/2012 to clear bulkhead sill to seal bulkhead for Pump #6

-Ktr working on #1, #5 lower bearing issue. #6 awaiting results from #1 and #5

-We still have not heard back from PMSL (pump subcontractor) about a plan forward.

353174-TDA PIT Alternatives Study Report- Team working on 90% Alternative Report.

-Schedule and Cost Change Request (SACCR) being processed - Expect Final by Sept- BiOp Due Dec 2012

-Continuing with all possible alternatives to meet Regions needs including vertical slot and Orifice/ Overflow which requires research by Pacific States

-7/24/2012- Fish Forum discussions about discontinuing TDA counting in O&M which may impact Count Stations.

-The DDR schedule may be affected by this decision.

393762-Fall Creek Fish Facility-

-July 11, 2012 all agency site visit was conducted.

-Jeff Brown working with Chad Helms to see Fish Trap and Haul operation.

-Brainstorming  meeting August 16, 2012 in Portland- hopefully on the 3rd floor of RDP

- Drawdown is a couple day process between Thanksgiving and Christmas- See one day? Stay Tuned

O&M

354296-Bradford Island Reliability – 90% Risk Matrix report provided for comments

2406 Program

373284- JDA PH Monolith Drainage issues – Team working on 30% DDR

-I’m working on the Agency Technical Review- Review Plan approval