| ◄ February | ~ March 2013 ~ |  |  |  |  |  |  |  |  |  |  | April ► |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon |  | Tue |  | Wed |  |  | Thu |  | Fri |  | Sat |
|  |  |  |  |  |  |  |  |  | 1 |  | 2 |  |
| 3 |  | 4 Bulkhead 14A Trash Rack Installation NMFS & COE |  | 5 Unit 14 Dry Trash Rack Installation NMFS & COE |  | 6 Unit 14 Dry TRD Guide Installation | 7 Unit 14 Dry TRD Guide Installation |  | 8 Unit 14 Dry TRD Guide Installation |  | 9 Unit 14 Dry TRD Guide Installation |  |
| 10 Unit 14 Dry TRD Guide Installation |  | 11 Unit 14 Dry TRD Guide Installation |  | 12 Unit 14 Dry TRD Guide Installation |  | 13 Unit 14 Dry TRD Guide Installation | 14 Unit 14 Dry TRD Guide Installation |  | 15 Unit 14 Dry TRD Guide Installation |  | 16 Unit 14 Dry TRD Guide Installation |  |
| 17 Unit 14 Dry TRD Guide Installation |  | 18 Unit 14 Dry TRD Guide Installation |  | 19 Unit 14 Dry TRD Guide Installation |  | 20 Unit 14 Dry TRD test pic | 21 Scaffolding removal Unit 11 ADV dry run |  | 22 Unit 14 Dry run ADV |  | 23 Unit 14 Dry run ADV |  |
| 24 |  | 25 Water Up Unit 14. Bulkhead 14A removal. STS install. Trashracks |  | 26 Water Up Unit 14. Bulkhead 14A removal. STS install. Trashracks |  | 27 Units 14 & 15 Velocity Testing begins | 28 Units 14 & 15 Velocity Testing |  | 29 Units 14 & 15 Velocity Testing |  | 30 Units 14 & 15 Velocity Testing |  |
| 31 Units 14 & 15 Velocity Testing |  |  |  |  |  |  |  |  |  |  |  |  |
| Notes: TRDs = Turbulence Reduction Devices (aka Slot Fillers). |  |  |  |  |  |  |  |  |  |  |  |  |

| ◄ March |  |  | ~ April 2013 ~ |  |  | May ► |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue |  | Wed | Thu |  | Fri | Sat |
|  | 1 Units 14 & 15 Velocity Testing | 2 Units 14 & 15 Velocity Testing |  | 3 Units 14 & 15 Velocity Testing | 4 Units 14 & 15 Velocity Testing |  | 5 Units 14 & 15 Velocity Testing | 6 Units 14 & 15 Velocity Testing ? |
| 7 Units 14 & 15 Velocity Testing ? | 8 SpCr R1 TRDs Out Start A (0830h) Up 1% (0800h) | 9 SpCr R1 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 10 SpCr R1 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 11 SpCr Rel. TRDs Out End C (0930h) Clean VBSs |  | 12 Spring Creek Passage No Testing | 13 Spring Creek Passage No Testing |
| 14 Spring Creek Passage No Testing | 15 Spring Creek Passage No Testing | 16 SpCr R2 TRDs Out Start A (0830h) Low 1% (0800h) |  | 17 SpCr R2 Place TRDs End A (0830h) Start B (0930h) Up 1% (0900h) | 18 SpCr R2 Remove TRDs Clean VBSs End B (0900h) Start C (1000h) Up 1% |  | 19 TRDs Out End C (1000h) | 20 |
| 21 | 22 SpCr R3 TRDs Out Start A (0830h) Up 1% (0800h) | 23 SpCr R3 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 24 SpCr R3 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 25 TRDs Out End C (0930h) Clean VBSs |  | 26 | 27 |
| 28 | 29 SpCr R4 TRDs Out Start A (0830h) Up 1% (0800h) | 30 SpCr R4 Place TRDs End A (0830h) Start B (0900h) Up 1% |  |  |  |  |  |  |
| Notes: Treatments: A = TRDs out, upper 1% unit flow (17.5-18K); B = TRDs installed, upper 1% unit flow (17.5-18K); and C = TRDs out and lower 1% unit flow (12-12.5K). SpCr = Spring Creek Hatchery. R1, 2, 3, 4 denote replicates. Test duration is 24 hours. Test fish are released 0800-1000h. |  |  |  |  |  |  |  |  |

| ◄ April |  |  | ~ May 2013 ~ |  |  | June ► |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue |  | Wed | Thu |  | Fri | Sat |
|  |  |  |  | 1 SpCr R4 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 2 SpCr Rel. TRDs Out End C (0930h) Clean VBSs |  | 3 Spring Creek Passage No Testing | 4 Spring Creek Passage No Testing |
| 5 Spring Creek Passage No Testing | 6 TRDs Out | 7 TRDs Out |  | 8 TRDs Out | 9 TRDs Out Clean VBSs |  | 10 | 11 |
| 12 | 13 ROR YC R1 TRDs Out Start A (0830h) Up 1% (0800h) | 14 ROR YC R1 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 15 ROR YC R1 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 16 TRDs Out End C (0930h) Clean VBSs |  | 17 | 18 |
| 19 | 20 ROR YC R2 TRDs Out Start A (0830h) Up 1% (0800h) | 21 ROR YC R2 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 22 ROR YC R2 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 23 TRDs Out End C (0930h) Clean VBSs |  | 24 | 25 |
| 26 | 27 ROR YC R3 TRDs Out Start A (0830h) Up 1% (0800h) | 28 ROR YC R3 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 29 ROR YC R3 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 30 TRDs Out End C (0930h) Clean VBSs |  | 31 |  |
| Notes: Treatments: A = TRDs out, upper 1% unit flow (17.5-18K); B = TRDs installed, upper 1% unit flow (17.5-18K); and C = TRDs out and lower 1% unit flow (12-12.5K). ROR YC = run-of-river yearling Chinook salmon. Test duration is 24 hours. Test fish are released 0800-1000h. |  |  |  |  |  |  |  |  |

| ◄ May |  |  | ~ June 2013 ~ |  |  | July ► |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue |  | Wed | Thu |  | Fri | Sat |
|  |  |  |  |  |  |  |  | 1 |
| 2 | 3 ROR YC R4 TRDs Out Start A (0830h) Up 1% (0800h) | 4 ROR YC R4 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 5 ROR YC R4 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 6 TRDs Out End C (0930h) Clean VBSs |  | 7 | 8 |
| 9 | 10 | 11 |  | 12 | 13 |  | 14 | 15 |
| 16 | 17 | 18 |  | 19 | 20 |  | 21 | 22 |
| 23 | 24 ROR SYC R1 TRDs Out Start A (0830h) Up 1% (0800h) | 25 ROR SYC R1 Place TRDs End A (0830h) Start B (0900h) Up 1% |  | 26 ROR SYC R1 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 27 TRDs Out End C (0930h) Clean VBSs |  | 28 | 29 |
| 30 |  |  |  |  |  |  |  |  |
| Notes: Treatments: A = TRDs out, upper 1% unit flow (17.5-18K); B = TRDs installed, upper 1% unit flow (17.5-18K); and C = TRDs out and lower 1% unit flow (12-12.5K). ROR SYC = run-of-river subyearling Chinook salmon. Test duration is 24 hours. Test fish are released 0800-1000h. ROR SYC tests could be scheduled one week earlier or later depending on river flow. |  |  |  |  |  |  |  |  |

| ◄ June | ~ July 2013 ~ |  |  |  |  | August ► |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  | 1 ROR SYC R2 TRDs Out Start A (0830h) Up 1% (0800h) | 2 ROR SYC R2 Place TRDs End A (0830h) Start B (0900h) Up 1% | 3 ROR SYC R2 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 4 TRDs Out End C (0930h) Clean VBSs | 5 | 6 |
| 7 | 8 ROR SYC R3 TRDs Out Start A (0830h) Up 1% (0800h) | 9 ROR SYC R3 Place TRDs End A (0830h) Start B (0900h) Up 1% | 10 ROR SYC R3 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 11 TRDs Out End C (0930h) Clean VBSs | 12 | 13 |
| 14 | 15 ROR SYC R4 TRDs Out Start A (0830h) Up 1% (0800h) | 16 ROR SYC R4 Place TRDs End A (0830h) Start B (0900h) Up 1% | 17 ROR SYC R4 Remove TRDs End B (0900h) Start C (0930h) Low 1% (0900h) | 18 TRDs Out End C (0930h) Clean VBSs | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 | 31 |  |  |  |
| Notes: Treatments: A = TRDs out, upper 1% unit flow (17.5-18K); B = TRDs installed, upper 1% unit flow (17.5-18K); and C = TRDs out and lower 1% unit flow (12-12.5K). Test duration is 24 hours. Test fish are released 0800-1000h. |  |  |  |  |  |  |