OFFICIAL COORDINATION REQUEST

FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION DATE- 3/26/2009

PROJECT- Bonneville Lock and Dam

RESPONSE DATE- 4/9/2009

Description of the problem

BON is requesting a bank outage for 7/8 from 0000 on 13 April until 1159 on 16 April 2009 for bank repairs.

Type of outage required

This bank outage will take unit 8 out of service from 0000 on 13 April until 1159 on 16 April.   Unit 7 will remain out of service due to turbine rehab.

Impact on facility operation

The outage will begin after spill has started, to minimize the impacts.  Unit 8 is seventh on the list for PH1 priority units.

The T11 & T 12 outages are also scheduled for that week.  During the 2 hour T11/12 outages Project capacity to pass water will include 100K spill plus approximately 64K at PH1 and with three units available at PH2 at 45K.  With miscellaneous flow, the Project can safely pass 215K without needing additional spill.

Per the STP runs from March 23rd flows are expected to be between 147-156K for that week in April.  The Project will have no problems passing that amount even during this T 7/8 outage and the T 11/12 one as well.

Length of time for repairs

One week.

Expected impacts on fish passage

There is no expected impact on fish passage.  While Unit 8 is out of service, the next available priority unit will be operated.

Comments from agencies

NOAA- No concerns with this.  You might recheck that forecast since flows might be a bit higher.  Even so, I doubt there will be involuntary spill.  Thanks, Gary

Final results- Approved by FPOM at the April FPOM meeting.  The Project will move forward with the work as coordinated.

Please email or call with questions or concerns.

Thank you,

Tammy

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

541-374-4552 Bonneville Office

503-961-5733 Blackberry

Tammy.m.mackey@usace.army.mil