OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION DATE- 29 Jan 2010

PROJECT- Bonneville First Powerhouse JSATS Trolley Pipe Installation

RESPONSE DATE- 12 Feb, 2010

Description of the problem- Steel 4”Trolley pipes that support the housing of the JSATS detection system are to be installed on each of the main unit pier noses in the first powerhouse forebay.  To safely have divers in the water to complete the installation the main of where the pipe is being install will be shut down as well as units on either side for protection.  In addition to the main units having to be OOS for diver safety the project is also requiring that the Ice and Trash Sluiceway (ITS) end gate be closed. The proposed dates for the dives are 15-19 March 2010. Dives are scheduled for daylight hours Monday through Friday.  The ITS end gate will be reopened at the end of each day. ITS operating hours during days of dive operations will be 1700-0600 each day.

Type of outage required- Divers require the units on either side as well as the main unit that they are diving over to be shut down.  It is the project’s safety policy to close the ITS for activities over the sluiceway area or dives that may have the potential for a person falling in the water.

Impact on facility operation- The powerhouse will operated, to facilitate dives, with as many as 3 main units OOS.  Currently units 7 & 9 are OOS for Rehab.  PH2 will remain the priority PH during this time.  The ITS end gate will be closed while divers are working then re-opened when they leave for the day.

Length of time for repairs- Five days of main unit outages and sluiceway gate closures are expected.  There is a potential for the dive time to be reduced depending on work progression and ease of placement.

Expected impacts on fish passage- There should be minimal impacts to fish passage from the trolley pipe dives.  PH2, the priority powerhouse this time of year will still be operating and the fish units will still provide attraction flow to the fishway. Depending on rivers flows mid March we anticipate that PH1 units will not be running at this time due to low river conditions. Impacts resulting from these dives would include pushing migrating juveniles that would normally exit the PH1 forebay via the sluiceway through the PH1 minimum gap runner turbines.

The Project has very specific mandatory safety regulations and protocols to ensure diver and worker safety while working and diving on the PH1 forebay deck and over water.  The impacts on fish passage will be from shutting down various the sluiceway entrances. The placement of these pipes are part of a much larger 7 million dollar LCR Survival Study (BON, TD, JD) approved within the AFEP Process for 2010 by the regional fish managers.  Acoustic nodes will be deployed on these trolley pipes to measure and determine passage routes through PH1 and ultimate survival below Bonneville Dam.

Comments from agencies

USFWS- Sooner would be better, but no objections.  At least don't let the work time extend.  We'll be into the expected time for adult steelhead fall back.  David Wills

CRITFC- No concern as long as we can use B2 sluiceway if we trip the Kelt trigger, if not then we would prefer this work to be done sooner if possible. tom

Final results- trolley pipe installation will go forward as coordinated above.

Thank you,

Dennis Schwartz

NWP Planning biologist

503-808-4779

Dennis.E.Schwartz@usace.army.mil