OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION DATE- 7 March 2011

PROJECT- Bonneville Lock and Dam, PH1 Sluiceway

RESPONSE DATE- 14 March 2011

Description of the problem- Starting on 28 March and continuing through 29 March, dive contractors will remove and reattached 3 transducer trolley pipes at PH1.  2 of the trolley pipes are located on the PH1 wing wall in front of sluiceway gates 6C & 7A and the other pipe is located on the north concrete wall just above sluice gate 10C.   Recent raking operations at PH1 at the beginning of the 2011 FPP have confirmed that the newly placed pipes from 2010 are impacting the main units rake and is impeding it’s travel to the bottom of the racks.

Type of outage required- BON project has requested a rolling outage of 2 units in front of each of the trolley pipes to facilitate dive operations.  No more than 2 units will be off-line at PH1 for this operation.  The Corps is also asking that the B1 sluiceway be closed to ensure safe dive operations from 0700-1630 each day.  The sluiceway will then be reopened each night to pass any fish and debris

Impact on facility operation- The Second Powerhouse is currently still the priority powerhouse.  River flows can be accommodated during these two days with little to no impacts to PH operations. No spill is anticipated with this operation.

Length of time for repairs/removal- Rolling outage for 2 main units that dives are taking place at (units 5&6, 7&8, 9&10) at PH1 from 0500-1700 on 28 and 29 March, 2011. The Corps anticipates that the work will take 2 days or less to complete.  If completed early, PH1 units will be brought back online and the sluiceway will be reopened when appropriate.

Expected impacts on fish passage- Fish impacts are expected to be minimal due to the low numbers of fish passing in late March.  Adult fishway entrances are still in operation and PH2 will be fully operational except unit 11.

Comments from agencies-

IDFG- -----Original Message-----
From: Kiefer,Russell [mailto:russ.kiefer@idfg.idaho.gov] 
Sent: Monday, March 07, 2011 3:49 PM
To: Mackey, Tammy M NWP
Subject: RE: FPOM: Official coordination BON PH1 trolley pipe dives

Tammy,

No objections!

Russ

BON Project Fisheries- If PH1 is priority, Project Fisheries would prefer to switch powerhouse priority to PH2 and open the B2CC to provide the best passage route for downstream migrating adults.

10 March FPOM- Fredricks asked if the work could be broken up more.  The ITS may not be open while divers are in the water.  Schwartz said passage would be delayed but the B2CC will be open.  Sweet asked what opening the B2Cc would buy you in terms of kelt passage.  The fish impacted are already at PH1.  The chain gates would be left in their current position, the endgate would be closed.  Fredricks asked if the ITS could be opened mid-day to flush out any fish in the channel then close it again for the rest of the dives.  Schwartz said the endgate could be opened for an hour.  FPOM agreed to the trolley pipe dives as long as the ITS is open for an hour during lunch to flush fish in the channel.  Meyer asked about the flushing flow once the endgate is closed.  Hausmann and Schwartz said there is plenty of leakage.

Final Action- FPOM agreed to the trolley pipe dives as long as the ITS is open for an hour during lunch to flush fish in the channel

Please email or call with questions or concerns.

Thank you,

Dennis Schwartz

Dennis Schwartz, Fisheries Biologist

NWP Fish Passage Team, Environmental Resources

503-808-4779

Dennis.e.schwartz@usace.army.mil