OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 12BON07 BON flushing spill in March.

COORDINATION DATE- 22 March 2012

PROJECT- Bonneville Lock and Dam

RESPONSE DATE-26 March 2012 or as soon as possible.  This MOC does not allow for the two week coordination as the operation was developed and needs to be implemented in a very short time.

Description of the problem- NWP would like to conduct a bathymetry survey of the BON spillway tailrace for five days, 26 – 29 March and 2 April.

There will also be a flushing spill operation in an attempt to move rock piles downstream of spillway apron.  Flushing spill will consist of 50-54kcfs through two bays (27kcfs each).

Flushing spill was evaluated in the 1:55 General Model with agency participation from NOAA and ODFW during the 11-16 March ERDC trip.

Type of outage required-

For the bathymetry survey- BON spill gates 2-17 during daylight hours for each of the five days of the survey.  Spill gate 1 and 18 would remain open at 0.5 ft for adult ladder attraction.

Impact on facility operation- Spill gates 2-17 would not be in service during the bathymetry survey.  Surveys will occur during the day starting 26 March, continuing on 27-29 March and then on 2 April.

Spill for approximately 4 hours on evening of 26 March or morning of 27 March out of bays 15 and 16 for a total of 50-54 Kcfs.

If survey results on 27 March prove successful, resume same spill operation at bays 12 and 13 on night of 27 March.

Continue at bays 13 and 14 on night of 28 March.

Continue at bays 14 and 15 on night of 29 March.

Continue at bays 15 and 16 on 30 March.

Dates of impacts/repairs- Depending on flows and capacity flushing is expected to occur on 26-29 March and 2 April.

Length of time for repairs- 6 days.

Bathymetry surveys will be done during daylight hours on 26-29 March and 2 April.

Flushing spill will occur during nighttime hours on 26 – 30 March.

HOWEVER- There is a 230Kv line outage on 27 March.  This outage may result in spill during the daytime hours.  If that occurs, that spill will be shaped as per the spill pattern developed by L. Ebner (attached below).

Expected impacts on fish passage-

For the bathymetry survey- No impacts to juvenile, adult or kelt passage.  There will be no change to fish passage operations during this activity.

For flushing spill-

Juvenile salmonids - the flushing operation at night will provide 50-54kcfs through two spillbays.  Juveniles may pass through the spillway during this spill operation.  Current juvenile fish numbers for the past six days of March are in Table 1.

Adult downstream migrating salmonids - kelts may pass through the spillway during this operation.  PH2 will remain the priority powerhouse with the B2CC open.  PH1 ITS will remain open.  Unit operation should draw more kelts to the surface passage routes at each powerhouse.  Total kelt numbers are not known at this time, however, Table 1 shows kelts numbers seen at the JMF from 17 – 22 March.

Table 1. Juvenile fish numbers for 17 - 22 March 2012.

| Chinook |  | Steelhead |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Yearling | Sub-yearling (fry) | Juveniles | kelts | Coho | lamprey |
| 9722 | 5871 | 18 | 16 | 52 | 707 |

Adult upstream migrating salmonids- this action should have limited impacts on upstream migrating adults since flushing spill will occur at night and attraction flow will not be altered.  Adults tend not to travel at night this time of year.  Adult fish counts for the 18-31 March are in Table 2.

Table 2.  Adult fish passage numbers for Bonneville Dam from 18-31 March 2007 – 2011.

| Year | Chinook |  |  | Steelhead |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Adults | Jacks | Total | Clipped | Un-clipped | Total |
| 2011 | 110 | 0 | 110 | 446 | 320 | 766 |
| 2010 | 410 | 12 | 422 | 963 | 400 | 1363 |
| 2009 | 134 | 0 | 134 | 354 | 167 | 521 |
| 2008 | 116 | 0 | 116 | 221 | 163 | 384 |
| 2007 | 52 | 0 | 52 | 512 | 232 | 744 |

Chum and TDG – According to NOAA Fisheries, the chum emergence model predicts the 50% chum emergence dates to be 21 - 28 March.  This operation would occur towards the end of the predicted 50% emergence dates.  Additionally, regarding depth compensation this operation does not appear that it would have any significant impacts based on the current BON TW elevation.  As of 22 March the BON TW was 19.8’ msl.   WDFW had the highest chum redd at 13.0 ft.  We have 6.8 ft of dept compensation.  With an approximate 3% TDG reduction per foot of depth over the redds there is sufficient depth compensation to minimize any potential TDG impacts on chum.

Comments from agencies

NWP  EC-HD

- -----Original Message-----
From: Ebner, Laurie L NWP 
Sent: Friday, March 23, 2012 8:51 AM
Subject: RE: BON 230 KV line limitation on 3/27 (UNCLASSIFIED)

I have put together a recommended spill pattern for flushing operation.

It looks strange and is a bit strange.

In order to override the deflector and push the rocks off the apron we need really high discharge and the flow not trying to flow under deflector flow.  Thus to augment spill above the flushing operation I am bringing on spill in the northern part of the spillway.  If you need to augment a lot it would make sense to go to a flushing spill in bay 14 as well as 15 and 16.  But we don't want less than a 14 foot gate opening on the southern bays (exception being gate 18).  We don't want flow in bay 17 since it would most likely put too large of velocities on the recently repaired Bradford Island.

CRITFC- -----Original Message-----
From: Tom Lorz [mailto:lort@critfc.org] 
Sent: Friday, March 23, 2012 9:40 PM
Subject: Re: FPOM: MOC#12BON07 BON flushing spill 26-2 April

It would be nice to have a little more time to review and think about these sort of operations, however there does not appear to be any significant fish impact with the operation so we will not object, however we need to do a better job of getting these issues out to review and comment on in a timely manner.  tom lorz  CRITFC

NOAA - -----Original Message-----
From: Gary Fredricks [mailto:gary.fredricks@noaa.gov] 
Sent: Monday, March 26, 2012 11:06 AM
Subject: Re: FPOM: MOC#12BON07 BON flushing spill 26-2 April

Did the Corps actually do this this morning?  I see that ~65 k spill occurred for several hours starting at 1 am.  I'm not sure what pattern was used, but if it was the two bay pattern, it looks like the TDG at Chum redd level was probably ok.  Warrendale isn't the best spot for this measurement.  However, as long as the tailwater is in the 20'+ range, redd level TDG's should be well compensated for river TDG levels up to about 120%.  Chum are the only species I am particularly concerned with for the proposed operations.  I didn't note a predicted TDG level at Warrendale for this test in the MOC, but one should be included.  Thanks,  Gary

Final results- Due to flows, involuntary spill occurred at 2356 on 25 March.  This spill was shaped as flushing spill.  A survey occurred on 26 March with spill that evening and into 27 March.  A survey on 27 March found the rocks to be flushed out.  Flushing operations concluded at 1200 on 27 March.

The FPP spill patterns are now in effect for any involuntary spill prior to the start of fish spill season.

Please email or call with questions or concerns.

Thank you,

Jon Rerecich

Jon Rerecich

NWP PM-E biologist

503-808-4779

Jonathan.g.rerecich@usace.army.mil