OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 12BON26 BON summer and fall operations

COORDINATION DATE- 29 June 2012

PROJECT-  Bonneville Lock and Dam

RESPONSE DATE- 12 July 2012 (FPOM meeting) extended to 31 July 2012

Description of the problem- Several transmission, generation and fisheries projects have been scheduled for late July through November.  Most of this work has been previously coordinated in the following MOCs :

110425 UPDATED 110413 BON Gantry 7 rehab.doc

12BON08 BON Gantry 7 rehab.doc

12BON15 Updated Unit 11 return to service testing.doc

100713 BON WS lamprey outage.doc

110505 UPDATED 110412 BON WS lamprey flume construction.doc

12BON11 2012 NOV Chum ops

12BON12 BON stilling basin erosion hole repair.doc

At the May and June FPOM meetings, BPA and BON Operations requested coordination for T-11 and T-12 outages in August and September.  The need to incorporate these outages has initiated the new MOC, which summarizes the series of events scheduled for July through November and provide a recommendation, incorporating most of the feedback we have received from FPOM, regarding powerhouse operations to best protect migrating salmonids.

Type of outage, or change to FPP operations, required-

Table 1.  Available turbine units, B2CC and spillway from 24 July 2012 through 31 March 2013.

| Date | PH1 Units | PH2 Units |  | Fish Units | B2CC | Spillway | Gantry 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Screened | Unscreened |  |  |  |  |
| 7/24/12 | 1,2,9,10 | 11-18 |  | F1, F2 | Yes | Yes | Yes |
| 7/25-31 | 1-10 | Will vary as screens are pulled from U13-17 |  | F1, F2 | Yes | Yes | Yes |
| 7/30, 31 | 1-10 | No PH2 units available 1000-2000 |  |  | Yes | Yes | Yes |
| 8/1-5 | 1-10 | 11,12, 18 | 13-16 | F1, F2 | Yes | Yes | No |
| 8/6-23 | 1-10 | 18 | 15, 16 | F1, F2 | Yes | Yes | No |
| 8/24-26 | 1-10 | 11,12, 18 | 13-16 | F1, F2 | Yes | Yes | No |
| 8/27-31 | 1-10 | 11,12 | 13-14 | F1, F2 | Yes | Yes | No |
| 9/1-17 | 1-10 | 11,12 | 13-14 | F1, F2 | Maybe | Yes | No |
| 9/18-10/31 | 1-10 | 11,12, 18 | 13-17 | F1, F2 | No | Yes | No |
| 11/1-10 | 1-10 | 11,12, 18 | 13-17 | F1, F2 | NO | NO | NO |
| 11/11-14 | 1-10 | 11,12,18 | 13-17 | None | Yes | No | No |
| 11/15-2/14 | 1-10 | None | 13-17 | None | Yes | No | No |
| 2/15-28 | 1-10 | Varies as screens are installed in U13-17 and WS returns. VBS are installed in U11-12, and WS returns. |  |  | Yes | No | Yes |
| 3/1-31 | 1-10 | 11-18 |  | F1, F2 | Yes | No | Yes |

PH2 STSs will be removed from five PH2 units prior to 15 December 2012 leaving some units unscreened but available on a limited basis during the fish passage season.  Powerhouse priority will switch on 16 September.  PH1 units may operate at open geometry prior to 1 November.  The B2CC will be out of service for repairs.  The spillway will be out of service for repairs.  The Washington Shore fishway will be out of service prior to winter maintenance season to install lamprey passage structures.  DSM2 will be OOS prior to winter maintenance season.

Impact on facility operation-.  With Gantry 7 OOS, the Project will not have a way to pull STSs.  For this reason, only three units will remain screened after 31July.  For most of August, only one screened unit will be available due to the T-11 and T-12 outages.  To reduce flows through PH1 during spill, unscreened PH2 units may operate.

The B2CC will not be available from 16 September until 11 November to complete deferred maintenance.  A one day outage will occur on 4 September to allow the contractor access to the channel in preparation of repairs.  There is the possibility the contractor will request the B2CC remain OOS due to the time needed for repairs, however, the expectation is that the B2CC will re-open through 15 September to provide adult fallback protection while PH2 remains the priority powerhouse.

The spillway will not be available from 1 November 2012 through 31 March 2013 to complete erosion repairs.

The Project requests concurrence in deviating from the 2012 Fish Passage Plan (FPP) by operating unscreened units at PH2 beginning on 25 July through 15 December and operating PH1 units at open geometry beginning 16 September (this is about two months earlier than 2012 FPP guidance).

Dates of impacts/repairs- Please also see the attached outlook calendar.

24 July 2012 from 1000 – 2200.  PH1 units 3-8 OOS.

25, 26, 30, 31 July 2012.  PH2 STS removal from units 13-17.  Units 11, 12 and 18 will remain screened.

30 and 31 July 2012 from 1000 – 2200 each day.  PH2 units (including fish units) OOS.

1 August 2012 – 15 February 2013.  PH2 90’+ intake crane, Gantry 7, OOS.

6 – 23 August 2012.  PH2 T-11 OOS.  Takes out units 11-14.  Unit 17 will also be out of service for air gap monitoring.  Fish Units will be in service.  Unit 18 will be the only available screened unit.  Units 15 and 16 will be the available unscreened units.  Units at PH1 will be available.

27 August – 17 September 2012.  PH2 T-12 OOS.  Takes out units 15-18.  Fish Units will be in service.  Units 11 and 12 will be the only available screened units.  Units 13 and 14 will be the available unscreened units.  Units at PH1 will be available.

16 September 2012 – 28 February 2013.  PH1 will be the priority powerhouse.  PH1 units will operate at open geometry.

16 September – 11 November 2012.  B2CC OOS.  Repairs were scheduled to begin on 4 September 2012 and be completed by 11 November 2012.  A one day outage will occur on 4 September to allow the contractor access to the channel in preparation of repairs.  There is the possibility the contractor will request the B2CC remain OOS due to the time needed for repairs, however, the expectation is that the B2CC will re-open through 15 September to provide adult fallback protection while PH2 remains the priority powerhouse.

1 November 2012 – 31 March 2013.  BON spillway OOS.  Repairs are scheduled to being on 1 November 2012 and be completed by 31 March 2013.  PH1 units and unscreened PH2 units will be available to pass additional flows to reduce the likelihood of spill and/or to provide chum salmon spawning flows.

8 November 2012.  Cascades Island exit opens.  Video monitoring in the count station to begin.  BON AFF dewatered in preparation of Washington Shore fishway going to orifice flow.

10 November 2012.  Washington Shore fishway goes to orifice flow.  Fish units are OOS.

13 November 2012.  Washington Shore fishway dewatering.  DSM2 orifice lights turned off in preparation for DSM2 dewatering.  The fishway dewatering is to accommodate the lamprey passage system installation at the north monolith.

15 November 2012.  DSM2 dewatering.  Screened unit 18 is no longer available at PH2.  VBSs pulled from Units 11 and 12; these units will be available for operation as long as the VBSs are removed.  This dewatering is to accommodate the lamprey passage system installation at the north monolith.  South units (11-14) will likely be the only units available during diving operations.

1 December 2012.  Start of winter maintenance season.  Cascades Island fishway goes to orifice flow.  Routine winter maintenance activities at PH2, Washington Shore and Cascades Island will continue through late February 2013.

Length of time for repairs- these outages/ changes to FPP criteria will occur from 25 July 2012 through 28 February 2013.  Normal winter maintenance season begins on 1 December 2012 however, so deviations from the FPP are from 25 July through 30 November 2012.

Expected impacts on fish passage-

Downstream migrating juvenile salmonids- The proposed maintenance work will have minimal effect, if any, on downstream migrating juvenile salmonids.  The majority of juvenile migrants are subyearling Chinook salmon.  Run timing data reported by the Fish Passage Center indicates that 95% of subyearling Chinook will pass Bonneville Dam (21 July) before the start of this work (Table 2).

Table 2.  Run timing of subyearling Chinook salmon at Bonneville Dam 2002-2011.

| Year | First | 5% | 10% | 50% | 90% | 95% | Last |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2002 | 12-Mar | 14-Mar | 16-Mar | 29-Jun | 18-Jul | 23-Jul | 31-Oct |
| 2003 | 11-Mar | 16-Apr | 16-Apr | 28-Jun | 16-Jul | 24-Jul | 31-Oct |
| 2004 | 3-Mar | 12-Mar | 13-Mar | 18-Jun | 8-Jul | 15-Jul | 29-Oct |
| 2005 | 2-Mar | 5-Mar | 5-Mar | 9-Jun | 10-Jul | 17-Jul | 31-Oct |
| 2006 | 2-Mar | 5-Mar | 5-Mar | 15-Jun | 10-Jul | 15-Jul | 30-Oct |
| 2007 | 3-Mar | 8-Mar | 8-Mar | 6-May | 15-Jul | 20-Jul | 31-Oct |
| 2008 | 4-Mar | 8-Mar | 9-Mar | 6-May | 15-Jul | 22-Jul | 31-Oct |
| 2009 | 3-Mar | 15-Apr | 15-Apr | 17-Jun | 12-Jul | 20-Jul | 30-Oct |
| 2010 | 9-Mar | 15-Apr | 15-Apr | 25-Jun | 17-Jul | 22-Jul | 29-Oct |
| 2011 | 2-Mar | 13-Apr | 13-Apr | 11-May | 25-Jul | 1-Aug | 31-Oct |
| Median | 3-Mar | 13-Mar | 14-Mar | 16-Jun | 15-Jul | 21-Jul | 31-Oct |

An analysis of PIT-tagged wild subyearling fall Chinook salmon detected at Bonneville Dam in 2007 through 2011 indicates that, except for 2011, 95% pass Bonneville by approximately 25 July (Figure 1).

Adult salmon and steelhead passage- The proposed maintenance work (late July – November) coincides with peaks in adult steelhead, fall Chinook, and coho salmon passage at BON (Table 3).  With the exception of a 2-day disruption in attraction flow at the Washington Shore Fish Ladder on July 30-31, a minimum of two fish ladders will be in full service during the period in question.  Steelhead passage typically peaks between early and mid-August, and fall Chinook and coho salmon runs generally (5-year average) peak between late August and mid-September (Table 3).

The primary concern with respect to upstream migrants during this period is fallback past the dam, which can cause direct injury, delay issues, and reduced escapement.  Fish may fallback via the spillway, turbines, the navigation lock, the PH2 juvenile bypass system, the B2CC, or the PH1 ice and trash sluiceway (ITS).  Fallback via the spillway during the juvenile salmon spill operations (through August 31) is particularly problematic for steelhead passing via the Bradford Island Fish Ladder (Bjornn et al. 2000, Boggs et al. 2005).  Steelhead fallback rates observed during radio-telemetry studies in 1996-1997 and 2000-2001 averaged 11.3% for Bradford Island-passed fish, reaching as high as 15% in 1997, a year characterized by high flows (Table 5).  Fallback concerns informed the decision to operate PH2 as the priority powerhouse after 2002, with the intention of attracting fewer salmon and steelhead to the Bradford Island Fish Ladder (PH1).  Spill volume is a factor in fallback of Bradford Island-passed fish, so the 2012 FOP specifically limits BON daytime spill from June 16 through August spill to 100 kcfs or less.  The FOP also indicates that the daytime spill amount shall be 75 kcfs from August 1-31 to accommodate juvenile salmon passage.  This is the greatest period of risk to adult migrants, as the juvenile salmon passage season ends August 31.  From September 1 – February 28, except in forced-spill conditions, spill will only occur at Spillbays 1 and 18 in the form of attraction flow for Cascades Island and Bradford Island (B-Branch) fish ladders.

To minimize potential fallback impacts on steelhead, the Corps proposes to operate PH2 as priority powerhouse through the end of the spill season (through August 31).  This does not include July 30-31, when PH2 units, including fish units, will be unavailable.  High flows, spill, and a higher % of fish using Bradford Island Fish Ladder will likely result in higher fallback for steelhead (5-year average count for July 25-31 is 38,655), later-run sockeye salmon (5-year average count for July 25-31 is 326) and later-run summer Chinook (5-year average count for July 25-31 is 3,831) on July 30-31 (Table 3).

Bypass screens (STS) are typically left in place through 15 December to prevent adult fish from falling back via turbines.  Of concern during this period will be potential impacts of operating an unscreened units (if necessary) at PH2, especially during the PH2 priority operation (through August 31).  The unavailability of Gantry 7 after August 1 limits the Corps’ ability to clean screens at PH2.  The Corps proposes to keep units 12 and 18 (the ends of the powerhouse) screened during the period in question to minimize adult turbine fallback and downstream migrant risks.  The B2CC will also provide a surface route for adult and juvenile fish through the spill season (August 31).  All units will be available at PH1, and operation of the ice and trash sluiceway (ITS) will provide a surface route for steelhead and other fallbacks.

Pacific lamprey passage- The lamprey run at Bonneville Dam typically peaks in mid-July, tapering off through September.  Overall dam passage efficiency of Pacific lamprey is higher during PH1 priority operations, so the temporary loss of attraction flow on July 30-31 and PH1 priority operation after September 1 may result in a net benefit to lamprey passage in 2013.  The mean fallback rate for lamprey during PH2 priority operation years (since 2002) was 12.8%, which is higher than the mean of 8.9% observed prior to 2002, when PH1 was priority powerhouse (Table 6).  It is important to note that NOAA and University of Idaho are less confident about pre-2002 fallback data (M. Keefer, personal communication) and that the migration behavior and fate of fallback lamprey is poorly understood.

Table 3.  Salmon & Steelhead Passage at Bradford Island and Washington Shore Fish Ladders of Bonneville Dam (July 25-November 15).  Peak passage periods are highlighted in yellow.

| Date | Chinook | Steelhead | Coho | Sockeye | Chum | Pink |
| --- | --- | --- | --- | --- | --- | --- |
| July 25-31 |  |  |  |  |  |  |
| 2007 | 2759 | 19950 | 4 | 114 | 2 | 0 |
| 2008 | 2721 | 37171 | 1 | 89 | 1 | 4 |
| 2009 | 2877 | 48808 | 6 | 228 | 0 | 0 |
| 2010 | 3504 | 39776 | 1 | 412 | 0 | 0 |
| 2011 | 7293 | 47620 | 5 | 791 | 2 | 0 |
| Average | 3831 | 38665 | 3 | 327 | 1 | 1 |
| August 1-6 |  |  |  |  |  |  |
| 2007 | 4276 | 55031 | 31 | 155 | 2 | 1 |
| 2008 | 3788 | 45970 | 2 | 96 | 0 | 22 |
| 2009 | 3019 | 59101 | 21 | 239 | 0 | 0 |
| 2010 | 5069 | 62551 | 22 | 406 | 0 | 0 |
| 2011 | 7797 | 66913 | 21 | 619 | 2 | 0 |
| Average | 4790 | 57913 | 19 | 303 | 1 | 5 |
| August 7-23 |  |  |  |  |  |  |
| 2007 | 16302 | 110835 | 777 | 31 | 0 | 4 |
| 2008 | 27072 | 50421 | 734 | 21 | 0 | 2 |
| 2009 | 48038 | 270030 | 9356 | 57 | 2 | 4 |
| 2010 | 23367 | 74693 | 679 | 49 | 0 | 1 |
| 2011 | 27660 | 105221 | 5784 | 54 | 0 | 106 |
| Average | 28488 | 122240 | 3466 | 42 | 0 | 23 |
| August 24-26 |  |  |  |  |  |  |
| 2007 | 3754 | 10364 | 603 | 0 | 0 | 2 |
| 2008 | 13160 | 7897 | 1238 | 1 | 0 | 4 |
| 2009 | 33732 | 24375 | 11962 | 1 | 0 | 1 |
| 2010 | 17992 | 10260 | 1552 | 4 | 0 | 1 |
| 2011 | 9234 | 11304 | 1482 | 5 | 0 | 67 |
| Average | 15574 | 12840 | 3367 | 2 | 0 | 15 |
| August 27- September 17 |  |  |  |  |  |  |
| 2007 | 116197 | 52396 | 46684 | 8 | 0 | 16 |
| 2008 | 239224 | 105091 | 67177 | 17 | 0 | 0 |
| 2009 | 246388 | 109648 | 92691 | 4 | 0 | 63 |
| 2010 | 331896 | 73724 | 38685 | 8 | 0 | 1 |
| 2011 | 297472 | 71619 | 82195 | 3 | 1 | 2052 |
| Average | 246235 | 82496 | 65486 | 8 | 0 | 426 |
| September 18-30 |  |  |  |  |  |  |
| 2007 | 48672 | 19476 | 16437 | 0 | 0 | 0 |
| 2008 | 35203 | 17129 | 22963 | 1 | 0 | 0 |
| 2009 | 50931 | 24684 | 27706 | 0 | 0 | 16 |
| 2010 | 122178 | 20579 | 20375 | 0 | 0 | 2 |
| 2011 | 102424 | 20958 | 31547 | 0 | 0 | 1396 |
| Average | 71882 | 20565 | 23806 | 0 | 0 | 283 |
| October 1 - 7 |  |  |  |  |  |  |
| 2007 | 8108 | 4754 | 4587 | 0 | 0 | 0 |
| 2008 | 7537 | 2871 | 19195 | 0 | 0 | 0 |
| 2009 | 8716 | 7437 | 29435 | 0 | 0 | 9 |
| 2010 | 19275 | 4219 | 18003 | 0 | 0 | 0 |
| 2011 | 21525 | 3667 | 11161 | 0 | 0 | 112 |
| Average | 13032 | 4590 | 16476 | 0 | 0 | 24 |
| October 8-14 |  |  |  |  |  |  |
| 2007 | 7844 | 3854 | 7137 | 0 | 2 | 0 |
| 2008 | 4399 | 1391 | 19977 | 0 | 1 | 0 |
| 2009 | 4359 | 4489 | 21959 | 0 | 0 | 0 |
| 2010 | 8065 | 2550 | 25526 | 1 | 2 | 1 |
| 2011 | 12483 | 2154 | 11221 | 0 | 0 | 81 |
| Average | 7430 | 2888 | 17164 | 0 | 1 | 16 |
| October 15-21 |  |  |  |  |  |  |
| 2007 | 3526 | 1674 | 9729 | 0 | 10 | 0 |
| 2008 | 2058 | 973 | 8699 | 0 | 1 | 0 |
| 2009 | 3079 | 3611 | 24551 | 0 | 0 | 1 |
| 2010 | 3262 | 1280 | 10916 | 0 | 4 | 0 |
| 2011 | 5893 | 998 | 4402 | 0 | 0 | 12 |
| Average | 3564 | 1707 | 11659 | 0 | 3 | 3 |
| October 22-28 |  |  |  |  |  |  |
| 2007 | 1557 | 1049 | 5815 | 0 | 8 | 0 |
| 2008 | 1223 | 671 | 3554 | 0 | 5 | 0 |
| 2009 | 1183 | 1482 | 10746 | 0 | 10 | 1 |
| 2010 | 1805 | 614 | 6306 | 0 | 22 | 0 |
| 2011 | 2726 | 645 | 1127 | 0 | 1 | 1 |
| Average | 1699 | 892 | 5510 | 0 | 9 | 0 |
| October 29-30 |  |  |  |  |  |  |
| 2007 | 480 | 228 | 1363 | 0 | 4 | 0 |
| 2008 | 262 | 147 | 346 | 0 | 6 | 0 |
| 2009 | 486 | 516 | 3288 | 0 | 15 | 0 |
| 2010 | 438 | 235 | 2421 | 0 | 11 | 0 |
| 2011 | 542 | 187 | 291 | 0 | 4 | 0 |
| Average | 442 | 263 | 1542 | 0 | 8 | 0 |
| November 1-10 |  |  |  |  |  |  |
| 2007 | 537 | 471 | 1956 | 0 | 30 | 0 |
| 2008 | 546 | 493 | 881 | 0 | 40 | 0 |
| 2009 | 505 | 875 | 2378 | 0 | 46 | 0 |
| 2010 | 739 | 468 | 2416 | 0 | 46 | 0 |
| 2011 | 932 | 569 | 392 | 0 | 10 | 0 |
| Average | 652 | 575 | 1605 | 0 | 34 | 0 |
| November 11-15 |  |  |  |  |  |  |
| 2007 | 182 | 240 | 528 | 0 | 37 | 0 |
| 2008 | 75 | 158 | 285 | 0 | 8 | 0 |
| 2009 | 97 | 204 | 251 | 0 | 10 | 0 |
| 2010 | 208 | 176 | 452 | 0 | 20 | 0 |
| 2011 | 300 | 197 | 84 | 0 | 7 | 0 |
| Average | 172 | 195 | 320 | 0 | 16 | 0 |

Table 4.  Fallback rates (total fallback events / unique fish that passed a fishway) and re-ascension percentage (unique fish that reascended / unique fish that fell back after passing a fishway) of BON Bradford Island Fish Ladder-passed fish during Powerhouse 1 priority operations (1996-2001 study years) and Powerhouse 2 priority operations (2002-2010).  References: Bjornn et al. (2000), Boggs et al. (2005), Jepson et al. (2010).

| Study Year | Spring-Summer Chinook |  | Fall Chinook |  | Steelhead |  | Sockeye |  |  | Pacific Lamprey |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension |  | Fallback | Re-ascension |  |
| Powerhouse 1 Priority (1996-2001) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1996* | 25.4 | 89.4 | - | - | 8.7 | 93.1 | - |  | - | - |  | - |
| 1997 | 27.8 | 92.7 | - | - | 15.0 | 86.8 | 22.7 |  | 96.8 | 0.0 |  | 0.0 |
| 1998 | 19.7 | 89.9 | 4.4 | 55.6 | - | - | - |  | - | 2.4 |  | 0.0 |
| 1999 | - | - | - | - | - | - | - |  | - | 29.3 |  | 0.0 |
| 2000 | 22.9 | 94.6 | 5.7 | 63.2 | 13.6 | 96.1 | - |  | - | 4.2 |  | 0.0 |
| 2001* | 5.0 | 81.3 | 6.3 | 75.0 | 7.8 | 83.3 | - |  | - | 11.3 |  | 0.0 |
| Mean | 20.2 | 89.6 | 5.5 | 64.6 | 11.3 | 89.8 | 22.7 |  | 96.8 | 9.4 |  | 0.0 |
| Powerhouse 2 Priority (2002-2010) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2002 | 9.3 | 93.8 | 4.6 | 37.5 | 4.2 | 94.4 | - |  | - | 0.0 |  | 0.0 |
| 2003 | 9.8 | 79.4 | 7.6 | 14.3 | 7.7 | 73.7 | - |  | - | - |  | - |
| 2004 | 3.4 | 50.0 | 5.4 | 37.5 | 5.5 | 100.0 | - |  | - | - |  | - |
| 2005 | 5.7 | 100.0 | - | - | - | - | - |  | - | - |  | - |
| 2006 | 23.0 | 74.3 | - | - | - | - | - |  | - | - |  | - |
| 2007 | 8.2 | 70.0 | - | - | - | - | - |  | - | 28.9 |  | 0.0 |
| 2008 | - | - | - | - | - | - | - |  | - | 21.5 |  | 0.0 |
| 2009 | 11.7 | 82.8 | - | - | - | - | - |  | - | 10.8 |  | 12.5 |
| 2010 | 11.4 | 87.0 | - | - | - | - | - |  | - | 3.4 |  | 0.0 |
| Mean | 10.3 | 79.7 | 5.9 | 29.8 | 5.8 | 89.4 | - |  | - | 12.9 |  | 2.5 |

*Notes:  1996 and 1997 were very high flow and spill years.  Data from 2001 study, when river flows were only 55% of ten-year average.  There was no spill in 2001.

Table 5.  Fallback rates (total fallback events / unique fish that passed a fishway) and re-ascension percentage of BON Washington Shore Fish Ladder-passed fish during Powerhouse 1 priority operations (1996-2001 study years) and Powerhouse 2 priority operations (2002-2010).  References: Bjornn et al. (2000), Boggs et al. (2005), Jepson et al. (2010).

| Study Year | Spring-Summer Chinook |  | Fall Chinook |  | Steelhead |  | Sockeye |  |  | Pacific Lamprey |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension |  | Fallback | Re-ascension |  |
| Powerhouse 1 Priority (1996-2001) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1996* | 5.5 | 61.9 | - | - | 1.8 | 66.7 | - |  | - | - |  | - |
| 1997 | 10.2 | 100.0 | - | - | 3.4 | 38.5 | 0.5 |  | 0.0 | 15.4 |  | 0.0 |
| 1998 | 9.1 | 72.7 | 2.7 | 16.7 | - | - | - |  | - | 0.0 |  | 0.0 |
| 1999 | - | - | - | - | - | - | - |  | - | 7.3 |  | 0.0 |
| 2000 | 7.7 | 85.7 | 1.6 | 75.0 | 1.5 | 66.7 | - |  | - | 0.0 |  | 0.0 |
| 2001* | 7.7 | 87.5 | 4.6 | 66.7 | 2.4 | 70.0 | - |  | - | 16.9 |  | 0.0 |
| Mean | 8.0 | 81.6 | 3.0 | 52.8 | 2.3 | 60.5 | 0.5 |  | 0.0 | 7.9 |  | 0.0 |
| Powerhouse 2 Priority (2002-2010) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2002 | 5.0 | 77.3 | 2.6 | 55.6 | 4.1 | 53.3 | - |  | - | 1.8 |  | 0.0 |
| 2003 | 4.1 | 80.0 | 2.7 | 50.0 | 8.5 | 47.1 | - |  | - | - |  | - |
| 2004 | 3.7 | 55.6 | 4.4 | 30.0 | 2.5 | 50.0 | - |  | - | - |  | - |
| 2005* | 4.4 | 33.3 | - | - | - | - | - |  | - | - |  | - |
| 2006 | 3.9 | 28.6 | - | - | - | - | - |  | - | - |  | - |
| 2007 | 5.4 | 62.5 | - | - | - | - | - |  | - | 25.0 |  | 0.0 |
| 2008 | - | - | - | - | - | - | - |  | - | 11.3 |  | 0.0 |
| 2009 | 1.1 | 33.3 | - | - | - | - | - |  | - | 18.6 |  | 0.0 |
| 2010 | 1.7 | 66.7 | - | - | - | - | - |  | - | 3.0 |  | 50.0 |
| Mean | 3.7 | 54.7 | 3.2 | 45.2 | 5.0 | 50.1 | - |  | - | 11.9 |  | 10.0 |

*Notes:  1997 was a very high flow and spill year.  Data from 2001 study, when river flows were only 55% of ten-year average.  Spill was limited in 2001.  In 2005, an additional sample of fall Chinook salmon was released directly from the BON trap; the Washington shore fallback rate for this group was 5.3%.  In 2007, an additional sample of spring–summer Chinook was released directly from the BON trap; the Washington shore fallback rate for this group was 5.8%.

Table 6.  Fallback rates (total fallback events / unique fish that passed a fishway) and re-ascension percentage of Bonneville Dam-passed fish during Powerhouse 1 priority operations (1996-2001 study years) and Powerhouse 2 priority operations (2002-2010).  References: Bjornn et al. (2000), Boggs et al. (2004), Jepson et al. (2010).

| Study Year | Spring-Summer Chinook |  | Fall Chinook |  | Steelhead |  | Sockeye |  |  | Pacific Lamprey |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension | Fallback | Re-ascension |  | Fallback | Re-ascension |  |
| Powerhouse 1 Priority (1996-2001) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1996* | 16.4 | 89.3 | - | - | 5.3 | 85.7 | - |  | - | - |  | - |
| 1997 | 19.9 | 92.1 | - | - | 9.9 | 77.7 | 13.7 |  | 95.0 | 8.2 |  | 0.0 |
| 1998 | 15.8 | 82.7 | 4.2 | 37.5 | - | - | - |  | - | 1.4 |  | 0.0 |
| 1999 | - | - | - | - | - | - | - |  | - | 18.3 |  | 0.0 |
| 2000 | 16.8 | 92.7 | 5.2 | 50.0 | 7.4 | 91.1 | - |  | - | 2.4 |  | 0.0 |
| 2001* | 7.0 | 75.8 | 6.9 | 60.0 | 4.5 | 78.8 | - |  | - | 14.0 |  | 0.0 |
| Mean | 15.2 | 86.5 | 5.4 | 49.2 | 6.8 | 83.3 | 13.7 |  | 95.0 | 8.9 |  | 0.0 |
| Powerhouse 2 Priority (2002-2010) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2002 | 6.9 | 83.3 | 4.6 | 43.2 | 4.4 | 72.7 | - |  | - | 1.1 |  | 0.0 |
| 2003 | 6.2 | 80.4 | 4.8 | 21.7 | 8.3 | 54.5 | - |  | - | - |  | - |
| 2004 | 3.5 | 52.9 | 4.7 | 11.1 | 3.8 | 81.8 | - |  | - | - |  | - |
| 2005 | 4.9 | 66.7 | - | - | - | - | - |  | - | - |  | - |
| 2006 | 13.7 | 68.3 | - | - | - | - | - |  | - | - |  | - |
| 2007 | 6.7 | 66.7 | - | - | - | - | - |  | - | 27.7 |  | 0.0 |
| 2008 | - | - | - | - | - | - | - |  | - | 16.9 |  | 0.0 |
| 2009 | 6.4 | 78.1 | - | - | - | - | - |  | - | 15.3 |  | 3.7 |
| 2010 | 5.2 | 77.8 | - | - | - | - | - |  | - | 3.2 |  | 25.0 |
| Mean | 6.7 | 71.8 | 4.7 | 25.3 | 5.5 | 69.7 | - |  | - | 12.8 |  | 5.7 |

*Notes:  1996 and 1997 were very high flow and spill years.  Data from 2001 study, when river flows were only 55% of ten-year average.  Spill was limited in 2001 due to low flows.

Comments from agencies

July 12 FPOM.  12BON26 BON summer and fall operations.  The Project requests concurrence in deviating from the 2012 Fish Passage Plan (FPP), operating unscreened units at PH2 through August, and allowing PH1 units to operate at open geometry beginning 1 September (this is two months earlier than the FPP allows).  Lorz suggested screens in 12, 18 and 11 (since it may or may not return to service).  Hausmann confirmed VBSs could be removed and the units operated with STSs in place.

Fredricks suggested for August PH2 priority with two or three screened units, run unscreened units, B2CC, and spill.  For 1-15 September operate the same as in August with spill going to PH1.  15 September PH1 priority, B2CC OOS, no spill and push the T-11 and T-12 outages to start in September.  He is concerned about adult fallback through unscreened turbines at PH2.  The B2CC would provide protection for adult fallback when operating PH2 as the priority powerhouse with both screened and unscreened units.

ACTION: Rerecich will check on the ability to move the B2CC outage starting in mid-September.

ACTION: Hausmann and Mackey will find out if the T-11 and T-12 outage can move to September.

Unit 11 update.  Hausmann said there was an oil leak that may require an intensive un-stack the Project has even done.

NWP- Rerecich- The B2CC may be delayed until 15 September, however, a one day outage is needed on 4 September to allow the contractor to see the spalling and prepare for repairs.  In the event that the scoping on Sept. 4 results in a determination that the entire (Sept. 4-Nov. 11) timeframe is needed for repair, we would allow the contractor in the B2CC to begin work at that point.  If there is some flexibility on the front end, then water up for approximately another 10 days or whatever duration is deemed appropriate.  We want to try to avoid a situation where the contractor is done and out of the B2CC with a significant amount of time left on the tail end of the schedule.  Unless, there is a construction factor that necessitates this.

CRITFC- -----Original Message-----
From: Tom Lorz [mailto:lort@critfc.org] 
Sent: Saturday, July 21, 2012 9:08 PM
To: Mackey, Tammy M NWP
Subject: Re: FPOM: Official Coordination 12BON26 updated (UNCLASSIFIED)

If I read this correctly this looks like only 2 operating units will be screened, unless there has been a miracle with unit 11 and it will come back in service in the near future.  I am not happy about his operation but it seems like it might be the best operation we can come up with given the constraints we are facing with the BON project.  Need clarification, unit 11 is still out for an undermined length of time, and the CC can be used through Sept 15?  Also will need to get some information from BPA on potential impacts of the project operations on trbial fisheries pool requests.  tom lorz  CRITFC

BON Chief of Maintenance- -----Original Message-----
From: Kirk, Tony R NWP 
Sent: Friday, July 20, 2012 9:51 PM
Subject: Re: FPOM: Official Coordination 12BON26 updated (UNCLASSIFIED)

As discussed; from a maintenance and environmental stand-point, I do not agree with leaving screens in 3 units.  Bonneville and furthermore the FCRPS cannot afford extended forced outage periods should a screen fail.  I'm interested in discussing further at your convenience.

Tony Kirk

Maintenance Manager

Bonneville Lock and Dam

Office: 541-374-8307

BB: 541-399-3921

Sent from my blackberry

BPA (Bettin) via phone call- Need further guidance on B2CC operation in September.  Will it be opened based on a trigger?

BON Ops (D. Smith)- -----Original Message-----
From: Smith, David B NWP 
Sent: Friday, July 27, 2012 7:24 AM
To: Mackey, Tammy M NWP
Subject: CBT

While you are working on the TTY for STS removal could we put in there that we will limit the screen units loading to 15kcfs max to prevent damage... Dave

NOAA Fisheries (T. Conder via voicemail received on 30 July)- The proposed B2CC operation in September sounds reasonable.    If only screened units are operating, then the B2CC may be closed but if an unscreened unit is operated, then open the B2CC.

CRITFC (T. Lorz via phone call on 30 July)- Ok with the proposed September B2CC operation.

Final results- This MOC is being implemented as described below.

The T-11 and T-12 outages may not be moved due to budget constraints and work activities already scheduled.

FPOM requests the Project leave STSs in three units (11, 12, 18).  They will pull VBSs from units 11 and 12 in November, when the DSM goes out of service.  This will allow the Project to use those two units if needed.  Unit 11 status may not be known until 31 July, at which point we will know if STSs will remain in only two units (12 and 18) or if they will remain in three (U11, 12 and 18).

The B2CC closure may be delayed until 15 September, however, a one day outage is needed on 4 September to allow the contractor to see the spalling and prepare for repairs.  There is the possibility the contractor will request the B2CC remain OOS due to the time needed for repairs, however, the expectation is that the B2CC will re-open through 15 September to provide adult fallback protection while PH2 remains the priority powerhouse.

The B2CC would be opened from 1 – 15 September (except for 4 September as noted above) as long as unscreened units are operating at PH2.  PH2 will be the priority powerhouse with screened units priority over unscreened units.

The new timeline is as follows:

From 1-31 August- PH2 will be the priority powerhouse (running screened units first, then unscreened units), the B2CC will be operating and spill will be FOP/FPP spill.

From 1-15 September- PH2 will remain the priority powerhouse, the B2CC will be operating (when unscreened units are operating at PH2) and additional flow will go through PH1.  Please note, the B2CC will need to be OOS on 4 September to allow the contractor access.  .  A one day outage will occur on 4 September to allow the contractor access to the channel in preparation of repairs.  There is the possibility the contractor will request the B2CC remain OOS due to the time needed for repairs, however, the expectation is that the B2CC will re-open through 15 September to provide adult fallback protection while PH2 remains the priority powerhouse.

16 September through mid November- PH1 will be the priority powerhouse and will operate at open geometry, the B2CC will be closed, PH2 screened units will be operated before unscreened units.

Table1 (with edits accepted).  Available turbine units, B2CC and spillway from 24 July 2012 through 31 March 2013.  (assumes Unit 11 is available)

| Date | PH1 Units | PH2 Units |  | Fish Units | B2CC | Spillway | Gantry 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Screened | Unscreened |  |  |  |  |
| 7/24/12 | 1,2,9,10 | 11-18 |  | F1, F2 | Yes | Yes | Yes |
| 7/25-31 | 1-10 | Will vary as screens are pulled from U13-17 |  | F1, F2 | Yes | Yes | Yes |
| 7/30, 31 | 1-10 | No PH2 units available |  |  | Yes | Yes | Yes |
| 8/1-5 | 1-10 | 11, 12, 18 | 13-16 | F1, F2 | Yes | Yes | No |
| 8/6-23 | 1-10 | 18 | 15, 16 | F1, F2 | Yes | Yes | No |
| 8/24-26 | 1-10 | 11, 12, 18 | 13-16 | F1, F2 | Yes | Yes | No |
| 8/27-31 | 1-10 | 11, 12 | 13-14 | F1, F2 | Yes | Yes | No |
| 9/1-17 | 1-10 | 11, 12 | 13-14 | F1, F2 | Maybe | Yes | No |
| 9/18-10/31 | 1-10 | 11, 12, 18 | 13-17 | F1, F2 | No | Yes | No |
| 11/1-10 | 1-10 | 11, 12, 18 | 13-17 | F1, F2 | NO | NO | NO |
| 11/11-14 | 1-10 | 11, 12,18 | 13-17 | None | Yes | No | No |
| 11/15-2/14 | 1-10 | 11 and 12 w/o VBSs | 13-17 | None | Yes | No | No |
| 2/15-28 | 1-10 | Varies as STSs are installed in U13-17, VBS are installed in U11-12, and WS returns. |  |  | Yes | No | Yes |
| 3/1-31 | 1-10 | 11-18 |  | F1, F2 | Yes | No | Yes |

Please email or call with questions or concerns.

Thank you,

Tammy

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

503-961-5733

Tammy.m.mackey@usace.army.mil