## Sheet1
Lamprey Flume Installation | [5 empty] | Comment
Piece on drawing | Activity | Estimated Schedule Finished Date as of 2/4/2013 | Completed? | PH generation expectation
|  |  |  | 06:00-20:00-14 hour outage | 20:00-6:00 10 hours Generation
0 | Remove Old Lamprey Flume | 2013-02-04 |  | 0 | Full Generation
| Ramp off Point | NOT Functioning Flume
| Remove Caisson, Connection and predrill activities/(Check Lower entrance concrete??) | 2/5-6/2013 |  | 0 | Full Generation
| 2/6/2013 change Outage and Generation |  |  | 06:00-16:00-10 hour outage | 16:00-6:00 14 hours Generation
1 | Remove Old Lamprey Flume/(Check Lower entrance concrete??) | 2013-02-07 |  | 0 | Full Generation
| Connection and predrill activities | 2/8-9/2013 |  | 0 | Full Generation
| Remove existing Didson Beams/install new beams | 2013-02-10 |  | 0 | Full Generation
2 | Install upper entrance elbow | 2/11/2013-2/13/2013 |  | 0 | Full Generation
3 | Flow Splitter (with no antenna if no IWW extension) | 2/14/2013-2/16/2013 |  | 0 | Full Generation
| 2/17-McAmis complete Bay 14 Spillway? Fowler back to 14 hours |  |  | 0:600-16:00- 10 hour outage OR 06:00-20:00-14 hour outage?? | 16:00-6:00 14 hours Generation OR 20:00-6:00 10 hours Generation ?? | McAmis complete Bay 14 Spillway? Fowler back to 14 hours
| Ramp off Point | NOT Functioning Flume
| Connection and predrill activities | 2/17-2/18/2013 |  | 0 | Full Generation
4 | Lower Flume (Bus) | 2013-02-19 |  | 0 | Full Generation | McAmis complete Bay 14 Spillway? Fowler back to 14 hours
5 | Supply Pipe | 2/20/2013-2/21/2013 |  | 0 | Full Generation | McAmis complete Bay 14 Spillway? Fowler back to 14 hours
| All In ladder work must be completed, Bring up ladder | 2013-02-22
6 | Upper Flume | 2/22/2013-2/23/2013 |  | 0 | Full Generation | McAmis complete Bay 14 Spillway? Fowler back to 14 hours
| Assume McAmis Complete on Spillway work | 2013-02-23 |  | 06:00-20:00-14 hour outage | 20:00-6:00 10 hours Generation | McAmis Complete on Spillway work
| Ramp off Point | Partial Functioning Flume
7 | Fill Plate | 2/24/2013-2/27/2013 |  | 0 | Full Generation | IWW Work Extension Provided
8 | Supply Water- Make up piece | 2013-02-28 |  | 0 | Full Generation | IWW Work Extension Provided
9 | Lower Entrance | 2/29/2013-3/4/2013 |  | 0 | Full Generation | IWW Work Extension Provided
10 | Connect Elbow | 3/5/2013-3/8/2013 |  | 0 | Full Generation | IWW Work Extension Provided
| Flume in water Completed | 2013-03-09 |  | 0 | Full Generation | IWW Work Extension Provided
|  | Functioning Flume in water complete |  |  |  | IWW Work Extension Provided
8 continued | Complete University of Idaho LPS to collection area- out of ladder | 3/9/2013-3/15/2013 |  | Full Generation | Full Generation | IWW Work Extension Provided
|  | Total Functioning Flume Complete |  |  |  | IWW Work Extension Provided
| Completion of remaining contract work | 3/16/2013-3/31/2013 |  | Full Generation | Full Generation | IWW Work Extension Provided
Assumptions: | Subject to change at any time
Dependent of Flow conditions/Chum being able to be met with PH1 and Spill
Dependent on PH1 units remaining in service
McAmis complete spillway work 2/23