OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION DATE- 28 September 2009

PROJECT- John Day Dam

RESPONSE DATE- 06 October 2009

Description of the problem- According to FPP, JDA spill bay 2 is required to be on during daylight hours at one stop (1.5 Kcfs) for attraction of adults to north ladder’s entrance through October. JDA maintenance needs half day outage for tri-annual maintenance of tainter gate ASAP.  This work is required to be performed during dry and warm weather so it can’t be postpone till winter outage and it will be the last gate done this year.

Structural crew has graciously agreed to stay after hours to minimize impact on fish passage.  Also, Operations is proposing to substitute for bay2 with 1.5 kcfs spill from bay 1 or 3 during this outage, if necessary.

Type of outage required- spill bay 2 closed for maintenance.

Impact on facility operation- attraction flow would be limited for about five hours from 1400 until 1900 in early October.

Length of time for repairs- About five hours.  The Structural crew has agreed to work late afternoon to early evening to minimize impacts to fish passage.

Expected impacts on fish passage- Attraction flow to the north ladder will be off for about five hours.  Bay 1 or 3 will be used to compensate for flow.

Bay 1 showed long retention times for dye, which could result in poor evacuation for juveniles, however, the spill at this time of year is for adult attraction instead of juvenile passage.

Bay 3 could be used to compensate flow but that bay if further from the fishway entrance and may not provide the same adult attraction as a closer bay would.

Due to short duration, PM timing and substitution spill, an impact on passing adults is expected to be minimal.

Comments from agencies- FPOM says ok to doing the work anytime after 15 September and compensating with flow from Bay 3.

Final results

Please email or call with questions or concerns.

Thank you,

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

541-374-4552 Bonneville Office or 503-961-5733 Blackberry

Tammy.m.mackey@usace.army.mil