OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION DATE- 7 May 2010 modified on 07 July 2010

PROJECT- John Day Lock and Dam- North Fish Ladder

RESPONSE DATE- 08 July FPOM meeting .

Description of the problem- The Corps of Engineers has been tasked with redesigning the John Day North Fish Ladder (JDAN) to improve adult salmon and lamprey passage, with construction scheduled to begin during the 2011-2012 in-water-work (IWW) period.  JDAN entrance modification construction requires work outside the normal 2011-2012 IWW period of 1 December through 29 February.  In order to complete installation of AWS pumps and modifications to the entrance, we are requesting an extension of the IWW period to 1 November through 30 March.

After talking with the Project on 07 July, it appears the south ladder can remain watered up, except for a three day outage, during the 2011-2012 winter maintenance period.

Type of outage required- Ladder outage outside normal IWW period.

Impact on facility operation- Early dewatering.  Limited maintenance on south ladder.

Length of time for repairs- to avoid a dual ladder outage, the following winter maintenance schedule is proposed for both ladders.  UPDATE- FPOM did not like an early outage.  The south ladder will be taken out of service for a brief outage in the Jan-Feb timeframe.

South Ladder: .  Jan-Feb 2012 timeframe.

North Ladder: 7 November 2011 through 30 March 2012

Expected impacts on fish passage- There will likely be little impact to ESA-listed adult and juvenile salmonids during this period.

From 1 November to 1 December 2011:

The ten year average shows fewer than 20 adult Fall Chinook salmon typically pass JDA daily.  Typically, approximately 200 adult steelheads pass daily from 1 to 15 November, with counts descending to roughly 10 fish per day by 1 December.  Fish counts were not conducted during this period in 2009.

From 29 February to 30 March 2012:

The ten year average shows that fewer than 150 adult Spring Chinook and steelhead (of each species) typically pass the dam during this period.  Adult fish counts were not conducted during this period in 2010.

Comments from agencies.

CRITFC- Once we get the full detailed plan for what the work plan for this winter is would help, but we are ok with both of these for now thanks tom lorz

NOAA Fisheries (Fredricks), at the July FPOM, preferred a short dual outage as opposed to an early outage for the south ladder.

USFWS (Wills), personal communication, gave approval for the dual ladder outage.

ODFW (Kruger), personal communication, deferred to Lorz and Fredricks on this request.

Final results- This coordination form was discussed at the July FPOM meeting.  At that time, several FPOM members expressed concern about taking the south ladder out of service early, even for three days.  Their preference was for a short, overlapping outage with the north ladder later in the winter maintenance period.

The Project will move forward with scheduling the north and south ladder out of service for as minimal a time as possible in the Jan-Feb 2012 winter maintenance period.

Please email or call with questions or concerns.

Sean Tackley

503-808-4751

sean.c.tackley@usace.army.mil

7 May 2010

FILE MEMORANDUM

TO:		FPOM

FROM:	Natalie Richards, Project Manager (USACE Portland District)

SUBJECT:	Addendum to 2011-2012 Winter maintenance period extension request to complete JDA North Fish Ladder Entrance modifications

The JDA North Fish Ladder (JDAN) entrance is being modified to provide better adult salmonid and Pacific lamprey passage.  In order to reduce the confusing flows in the transition pool section of the fishway and to provide higher attractive velocities and flow signature into the tailrace, more flow is needed than the existing 6 auxiliary water supply (AWS) pumps can provide.  A minimum of 4 new pumps need to be installed to provide enough flow for the new entrance weir and bollard configuration.

During the Alternatives Selection Process, Alt. 3 was selected which required the modification of gear boxes, motors and impellers within the confines of the current pump casings.  Working within the confines of the existing pump casings produces some risk to the project and schedule, as this work can be complicated and time-consuming.

The Request for Qualification Solicitation for these pump modifications, along with power controls and housings, has been submitted and is open for bidding.  This request assumes an in-water-work period of 1 December 2011- 29 February 2012.  An award of the Pumps Hydraulic Modeling and Testing contract is expected in mid-August 2010, with ARRA funding with the remaining work to be awarded as money becomes available. The August 2010 award date will give the contractor 12 months to complete modeling, testing, and all necessary fabrication.

The Portland District’s Small Projects Team is designing a second Intake Pump Bulkhead to allow the contractor to work on out of service (OOS) Pump #3 (and possibly #4, as time allows) while the ladder is in operation, in the October-November 2011 time period (prior to the in-water-work period of 1 December through 29 February).  In January 2011, a Hollow Structural Section (HSS) inspection of the Outlet Butterfly Valves will be conducted to ensure a safe environment for this work.  If the contractor is only able to complete work on 1 pump prior to the IWW period, this allows only 1 month per pump for the remaining 3 pumps.  This is a very aggressive schedule which carries risk.  Electrical specifications will provide a strict commissioning schedule which could vary from 2 weeks to 1 month.  In order to complete the required 4 new pumps and ensure the commissioning is completed, more construction time is needed and therefore an extension of the IWW period is requested (to 1 November 2011 – 30 March 2012).

If there are any fewer than 4 new pumps ready for service in March 2012, the JDAN entrance construction (new weir and bollards, etc.) should and will not occur during the 2012-2013 IWW period, as there will be insufficient flow for the modified entrance.  Potential sources of delay and incompletion of the necessary 4 pump modifications include: 1) Problems with the HSS inspection; 2) Problems with the delivery of the second bulkhead; 3) Inflexibility of the IWW period, causing entrance construction to be delayed at least a year because there will not be enough flow to meet fish passage criteria.

If all goes well with the modifications to pumps #1 through #4, the remaining 2 pumps (#5, #6) can be sealed off within the Intake Pump Bulkheads and HSS inspected butterfly valves, then completed in the April-June 2012 timeframe with pumps #1- #4 operating the fishway.