OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 12TDA04 120403 TDA T1 outage.

COORDINATION DATE- April 4, 2012

PROJECT- The Dalles Dam

RESPONSE DATE- April 12, 2012 (FPOM)

Description of the problem: Line T1 at TDA is scheduled to be out of service Oct 15 – Nov 8 for doble testing, transformer oil replacement bushing replacement and routine maintenance.  Line T1 is associated with main units 1 and 2. Per Fish Passage Plan, main unit 1 and/or 2 must be in operation through the juvenile fish passage season ending Nov 30.

Type of outage required: Main units 1 and 2.

Impact on facility operation: This is the latest in the year that this transformer work can be completed to avoid inclement weather.

Dates of impacts/repairs: Oct 15– Nov 8, 2012.

Length of time for repairs: Approximately 3 weeks.

Expected impacts on fish passage:

Minimal impacts to fish passage are expected. The Sluiceway will remain in operation during this work with sluice gates open over unit 3 to replace sluice gates over unit 1. Both unit 3 and 4 will operate to assure sufficient sluiceway attraction.

The vast majority of juvenile fish passage is through by the end of August. The sluiceway stays in operation Sept – Nov for the remaining juvenile out migration and some adult steelhead passage.

Data from PNNL passage research shows horizontal distribution across the powerhouse relatively even among units for summer passage, unlike the spring passage preference for U1.  Horizontal distribution per unit flow skews more toward center and east end units for summer.  Consultation with Fenton Kahn from PNNL; “I don’t see any problem as long as unit 3 and the sluicegates above it are operating.

The 2012 summer performance testing is expected to be completed before this time period.

Comments from agencies

PNNL (Fenton) -----Original Message-----

- From: Khan, Fenton [mailto:Fenton.Khan@pnnl.gov]

Sent: Tuesday, April 03, 2012 11:40 AM

Subject: RE: need passage advice (UNCLASSIFIED)

Nope, I don't see any problems with this plan, as long as MU 3, along with the sluice gates above it, is operated during the MU 1 and 2 OOS.  And, you have MU 4 as a priority.  If the project has to shut down MU 3 and operate MU 4, then I suggest operating the sluice gates above MU 4 while it is operated.

__________________________________________________

Fenton Khan

Research Scientist

Earth Systems Science Division/ Ecology Group

12 April 2012 FPOM- Cordie briefed FPOM.  He noted that the materials may not be available in time so the timing may be pushed back.  Fredricks didn’t note any concerns with the outage that late.  FPOM gave concurrence with the caveat that any schedule slippage be discussed at FPOM.

Final results- The Project will continue to move forward with this outage as coordinated.

Please email or call with questions or concerns.

Thank you,

Tammy

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

503-961-5733

Tammy.m.mackey@usace.army.mil