OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 19TDA19 East/North fishway dewater overlap

COORDINATION DATE- 11/18/19

PROJECT- The Dalles

RESPONSE DATE- 12/02/19

Description of the problem

The north fishway is scheduled to be dewatered 2/4/20-2/28/20. Per Fish Passage Plan, the east fishway should be in operation during that time. However the Fish Unit breaker upgrade schedule has slipped from mid Jan to the end of Jan. The commission testing afterwards will require units to be on/off periodically during 2 weeks of tests. The scenario involves operating a unit through T3 while testing the other through T1. Overall it is expected that both unit will be off ~2 hours/day during the transitions.

Type of outage required – Periodic outages of 1 and both fish units

Impact on facility operation (FPP deviations)

Intermittent outages of east fishway attractions while the north fishway is dewatered

Impact on unit priority

None

Impact on forebay/tailwater operation

None

Impact on spill

None

Dates of impacts/repairs – 2/1/20 – 2/7/20

Length of time for repairs - Approximately 2 hours per transition for 1 week

Analysis of potential impacts to fish

- 10-year average passage by run during the period of impact for adults and juvenile listed species, as appropriate for the proposed action and time of year;

https://www.nwfsc.noaa.gov/research/divisions/fe/estuarine/oeip/g-forecast.cfm

10 year average for these dates not available

- Statement about the current year’s run (e.g., higher or lower than 10-year average); Chinook and Steelhead presently at ~50% of 10 yr. average. Coho is at approx. 10 yr. average.

- Estimated exposure to impact by species and age class (i.e., number or percentage of run exposed to an impact by the action); Expected minimal impact to Steelhead, Chinook and Coho. Total month of Feb counts for Steelhead range from 16 (2006) to 485 (2003), for Chinook 0-11 and Coho 0.  The most salmonids expected could be ~16/day, which is ~2/hour during daylight. Fish unit attraction flow will be off approximately 2 hours/day for 7 days, which could result in a maximum impact of 28 Steelhead delayed (1-2 hours) for the entire week.

- Type of impact by species and age class (increased delay, exposure to predation, exposure to a route of higher injury/mortality rate, exposure to higher TDG, etc.);

Adult salmonids

Summary statement - expected impacts on:

Downstream migrants - No impact due to location.

Upstream migrants (including Bull Trout) – Some possible delay

Lamprey –Minimal to no impact, not within typical migration period.

Comments from agencies – No comments were received.

Final coordination results – This action will move forward as coordinated.

After Action update (After action statement stating what the effect of the action was on listed species. This statement could simply state that the MOC analysis was correct and the action went as expected, or it could explain how the actual action changed the expected effect (e.g., you didn’t need to close that AWS valve after all, so there was no impact of the action).  List any actual mortality noted as a result of the action)

Please email or call with questions or concerns.

Thank you,

Erin

Erin Kovalchuk

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

Erin.H.Kovalchuk@usace.army.mil

Bob Cordie

Chief of Fisheries

The Dalles Dam

mailto:Robert.P.Cordie@usace.army.mil