Nez Perce Tribe Department of Fisheries Resources Management

Pacific Lamprey Translocation Project – The Dalles Dam - 2017

PROJECT WORK PLAN

The Nez Perce Tribe Department of Fisheries Resources Management (NPT DFRM) plans to collect approximately 600 adult lamprey, depending on availability, from The Dalles Dam.  Note that the total aggregate of adult Pacific lamprey collected at Bonneville, John Day and The Dalles Dam would not exceed 1,600.  Collection of adult Pacific lamprey would be conducted intermittently from approximately July 1 through September, 2017, contingent on run timing, trapping success, fish availability and funding.

Collections would focus on the deployment of pot traps in fishways behind the picketed leads.  Trap placement will be chosen to avoid contact with any migrating salmonids.  Trapping and scheduling would be determined through coordination with The Columbia River Inter-Tribal Fish Commission, the Confederated Tribes of the Umatilla Indian Reservation and the Yakama Nation.

The collected adult lamprey would be loaded into a portable fish tank and transported to Nez Perce Tribal Hatchery (NPTH), Clearwater County, Idaho.  Loading into the portable fish tank would be no more than 200 adults per load.  The adults would be transported through Oregon and Washington to the Snake River Basin, Idaho, and unloaded into 8' X 8' insulated fiberglass fish tanks plumbed for a constant flow of 4-5 gpm per tote.  Maximum loading density would be about 250 fish per tote.  A prophylactic treatment (OTC) for furunculosis would be administered promptly upon arrival at NPTH.

Work will be coordinated with Columbia River Coordinator Erin Kovalchuck and The Dalles Dam Research Coordinator Jeffrey Randall, Confederated Tribes of the Umatilla Indian Reservation fisheries staff, Yakama Nation fisheries staff, and Columbia River Inter-Tribal Fish Commission staff.  Prior to collection, we will apply for and obtain ID badges, access keys, all required permits and will attend all required safety/coordination meetings.

The objective is to augment juvenile lamprey production in Snake River tributaries in view the continued decline of lamprey in the Snake Basin, as exemplified by the critically low counts of adults passing Lower Granite Dam.  Recent adult  lamprey counted passing Lower Granite Dam during the day have numbered 12, 15, 48, 48, 19, 82, 50 and 106  in 2009, 2010, 2011, 2012, 2013, 2014, 2015 and 2016, respectively.  The downward spiral of adults migrating to the Snake River Basin to spawn translates to severely reduced presence of larval lamprey available to emit attractants that may draw adults into the spawning tributaries.

PROJECT IMPACT STATEMENT

The NPTDFRM has no anticipated impacts to the existing project activities.  Project safety procedures will be applied.

JOB HAZARD SAFETY ANALYSIS

See attached Activity Hazard Analysis sheet.

MATERIAL SAFETY DATA SHEETS (MSDS)

No hazardous materials will be brought on site for this activity.

FUNDING ARRANGEMENTS

No project support will be necessary to perform job activities.

PERMITS

The NPTDFRM’s collection permit from the NPT Fish and Wildlife Commission is effective through December 31, 2017.

PERSONNEL LIST

NAME			AGENCY	ACTIVITY			EXPIRATION

1ST AID		CPR

SWEEN, TOD			NPTDFRM	Fishways		2010			2010

ELLENWOOD, Raymond	NPTDFRM	Fishways

STATLER, DAVID		NPTDFRM	Fishways		2010			2010

OATMAN, JAY		NPTDFRM	Fishways

Batten, George		CRITFC	Fishways

Ellenwood, Gerald		CRITFC	Fishways

Lejins, Spencer		CRITFC	Fishways

VEHICLE LIST

LICENSE	ST		DESCRIPT	COLOR	AGENCY	OWNER	POC/CREW BOSS

G63 1961S	GOVT		FORD F-350	GREEN  	NPTDFRM	US GOVT	SWEEN, TOD

TBD		TBD		TBD		TBD		CRITFC	RENTAL	TBD