# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2014/2015.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.

- ADULT FISHWAYS

  - Bradford Island Ladder – (10 Nov 14 – 21 Nov 14)

Go to orifice flow on 8 Nov 14

Dewater to tailwater on 10 Nov 14

    - While dewatered: Install new lamprey pump stillwells (Riggers)

    - While dewatered: Repair FG3-3 if necessary.

    - Install new drain valves on LPS rest boxes anytime from Nov to Mar. (Mechanics)

    - Replace lamprey exit section with perf material. (Fisheries and FFU)

  - PH1CC and Entrances – Not dewatering

ROV inspection of the ladder (Dec or Jan)

  - Adult Fish Facility (17 Nov 14 – 01 Apr 15) Dates estimated

Go to orifice flow on 17 Nov 14

Dewater exit section on 18 Nov 14

Dewater entrance on 18 Nov 14

    - Inspect rubber in false weir entrances and sample flumes. (Fisheries and Mechanics)

    - Repair brail pool hoist cable pulley system in NW corner of pool. (Mechanics)

    - Cover brail pool wires (Fisheries and Mechanics)

    - Attach UHMW lamprey plating strips on valve 15 trash rack and along bottom of return pool? (Garage)

    - Attach permanent baffle (new wood 4x4s?), remove and paint existing support hardware. (Garage, Painters)

    - Install still well and remove derelict water sensor conduit and wiring. (Electricians)

  - Cascades Island and UMT (1 Dec 2014 – 28 Feb 2015)

Go to orifice flow on 01 Dec 14

Dewater to tailwater on 03 Dec 14

Dewater entrance on 04 Dec 14

    - Modify new downstream lamprey picket leads at UMT junction to close gaps – metal plate on bottom, sides. (Riggers)

    - Remove last piece of side entrance gate (Riggers)

    - Replace staff gauge in entrance. (Riggers)

    - Re-lamp UMT (Electricians)

  - Washington Shore Ladder – (1 Dec 2014 – 28 Feb 2015)

Go to orifice flow on 06 Dec 14

Dewater UMT and exit section to tailwater on ~08 Dec 14

Dewater entrance on ~10 Dec 14

    - Lamprey pump still wells for 6-9 system (Mechanics)  WO# G215-20255

    - Repair counter picket lead rubber seal that detached and was removed in September? (Riggers)

    - Install SLEDS by 28 Feb 15

    - Install lamprey plating in NUE junction pool triangle. (Contractor)

    - Replace lamprey exit section with perf material. (Fisheries and FFU)

    - NORTH and SOUTH MONOLITH (1 Dec 2014 – 28 Feb 2015)

NDE, NUE, SDE, SUE closed on 08? Dec 14

      - Replace/repair/remove research equipment. (U of I)

      - Replace entrance staff gauges (x4) (Riggers)

      - Repair diffusers A2, B4, B7, B8 (Riggers and Mechanics)

      - Replace B3 diffuser gate (Riggers)

      - Lamprey mods to telescoping gates (Riggers)

      - Remove and flush entrance bulkheads below SLEDs for debris the week of 24 Feb 15. ?? (Riggers)

      - Install SLEDS by water-up

- JUVENILE FISHWAYS

  - ITS gate install  (TBD)

  - B2 Corner Collector  (01 Sep 14 – Mar/Apr 15)

  - Smolt Monitoring Facility (31 Oct 14 – 28 Feb 15)

Switch to bypass, drain and inspect sample flume on 31 Oct 13. (Project Fisheries/PSMFC)

    - Inspect seals on upper and lower switch gates. (Fisheries)

    - Repair or replace the fish lift filling/flushing booster pump due to diminished discharge (Mechanics)

    - Examine and (if needed) repair the small fracture in 3-way gate rotating tube section. (Mechanics)

    - Weld a knob on the inspection port just upstream of the River Exit PIT detector. (Mechanics)

    - Replace drain valve to fish lift #3. (Mechanics)

    - Arrange to pump/remove sludge from 1000-gal wastewater tank. (Mechanics)

    - Charcoal filter has clogged; repair if no PM will occur over winter. (Mechanics)

    - Re-plumb fish lift drain lines with sweeping 90s (PVC) for more efficient drainage. (PSMFC could do themselves)

  - DSM 2 (15 Dec 2014 – 28 Feb 2015)

    - Pull STSs week of 15? Dec 14.

    - Turn off orifice lights on 15 Dec 14.

    - Dewater DSM on 22? Dec 14.

    - Inspect and repair VBS seals. (Riggers)

    - Water up on 16? Feb 15.

    - Install STSs starting 16? Feb 15. (Riggers)

KEY TO COLORS-

Black- Multiple crews or Operators

Red - Painters

Blue – Mechanics

Pink – Riggers

Green – Garage

Orange – Electricians

Aqua- Fisheries

Yellow- contractors or researchers