Draft 9/30/14

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2014/2015

## 1400 cfs Flow Test						~Jan 30, ‘15

## North/South entrance sill inspect		-Dive		Nov 25, ‘14

## Coordinate logistics – TJF

## East Fish Ladder 				-Dewater	Dec. 2, ’14 – Jan.29, ‘15

- Install 158 weir (TDS, TDM)

- PM count station  (TDM, TDE, TDS)

- Renumber exit staff gages (TDF)

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Dec. 3, ‘14

- PM entrance weirs (TDM, TDE, TDS)

- Remove oil from fishlock and JP1,3,5 weirs (TDM)

- Remove JP1,3,5 (TDS)

- PM diffuser valves, excluding collection channel (TDM)

- E3  and W weir sticking (TDS, Eng)

- Inspect all grating (TDS)

- Pull remaining 4 collection channel dewater pumps/evaluate (TDM, TDE, TDS)

- Evaluate south dewater pump (TDS)

- Move spare south weir to north for PUD test (TDS)

- Open access to AWS near junction pool (TDS) 	Dec. 9, ‘14

Ice Trash Sluiceway				-Inspect	~Dec 15-Feb28

- Inspect flume spalling d/s endgate (TDF)

- PM endgate and sluicegates (Eng, TDS, TDM)

- Extend lift beam 1-3, build extension for unit 18 in house (Eng, TDS)

## North Fish Ladder                             	- Dewater     	Feb 2, ’15 – Feb 28, ‘15

- PM count station  and diffuser valve (TDM, TDE)

- Brush/tree removal (TDF)

- Modifications to count station (TDF)

North Entrance				- Dewater	Feb 3, ‘15

- Inspect diffuser grating (Eng)

- PM entrance weirs (TDM, TDE, TDS)

- PM diffuser valves (TDM)

- Inspect AWS channel (PUD)