Draft 12/07/15

THE DALLES DAM FISHWAY DEWATER SCHEDULE

WINTER 2015/2016

## North/South entrance sill 			-Dive		Dec 3, ‘15

North Grating and exit trashrack inspection –ROV	Dec 16, ‘15

## North Fish Ladder                             	- Dewater     	Dec 3, ’15

- PM count station  and diffuser valve (TDM, TDE)

- PM entrance weirs (TDM, TDE, TDS)

- PM diffuser valves (TDM)

## East Fish Ladder 				-Dewater	Jan 5, ’16 – Feb 28, ‘16

- Inspect exit weirs (TDS, TDM)

- PM count station  and replace brush(TDM, TDE, TDS)

- Renumber exit staff gages (TDF)?

- Move 158 weir back a slot (TDS)

- Expansion joint leak repair (Eng)

## East Entrances, Coll. Chan., Trans. Chan.	-Dewater	Jan 6, ’16 – Feb 28, ‘16

- PM entrance weirs (TDM, TDE, TDS)

- Remove gearboxes JP1,3,5 weirs (TDM, TDS)

- PM diffuser valves, excluding collection channel (TDM)

- Replace remaining entrance weir wheels (TDS, Eng)

- Replace E2 guides (TDS)

- Inspect all grating (TDS)

- Evaluate south dewater pump? (TDS)

- Remove vegetation south channel (TDF)

Ice Trash Sluiceway				-Inspect	~Dec 16-Feb28

- Inspect flume spalling downstream endgate (TDF)

- PM endgate and sluicegates (TDS, TDM)

- Adjust new sluicegate settings (TDE, TDS)