# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2016/2017.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.

- OREGON SIDE

  - Bradford Island Ladder – Not dewatering

Rov inspection in Dec

    - On hold until 2017: Set lower limit on B-branch entrance gate 4S

B-branch erosion repair in spillway:

FV4-3, FV4-4, and spill bay 18 closed (Dec-Jan)

    - Remove B2CC and spillway avian wires in Nov-early Dec (Riggers)

  - PH1CC and Entrances – Not dewatering

Rov inpsection in Dec

  - Navigation Lock – Extended outage (12 Dec 2016 – 9 Feb 2017)

    - Riggers, mechanics, electrician crews required

- WASHINGTON SIDE

  - Cascades Island – Not dewatering, exit will be open when UMT bulkhead in (~1 Dec)

    - Replace Cascades Island crowder (sandbag/pump out count station area) (Riggers/Mechanics) in Oct-Nov.

    - On hold until 2018: Paint FV5-3 stem with feet open markers to tenths (Painters)

    - On hold until 2018: Repair grating in FG6-20 diffuser pit (Riggers)

  - Washington Shore Ladder  (1 Dec 2016 – 28 Feb 2017)

Orifice flow on 1 Dec (25 Nov requested)

Dewater to tailwater on 6 Dec (28 Nov requested) – includes final exit section

UMT south bulkhead will remain, dewater UMT on 6 Dec

    - Lamprey orifice cutting in serpentine weirs (NWP Contractor)

    - New lamprey pumps and cages near FV6-9 (NWP Contractor)

    - New lamprey flumes from below count station (NWP contractor)

    - FGE hydroacoustic study at PH2 +90 gatewells (PNNL) – barge install and equipment mounting to STS, track racks (Rigger support) and trailer electrical hookup (Electricians)

    - Place screen on square opening between AWS and crowder area (GAR)

    - Reverse lower picket leads to correct position and eliminate any new gaps (Riggers)

    - Rehab FV6-9 (Mechanics) and inspect trash racks

    - Fix UMT bulkhead seals if time allows (Riggers)

    - Inspect and repair weir 37, hitting torque limits (Mechanics)

  - PH2CC, North and South entrances  (1 Dec 2016 – 28 Feb 2017)

Place transverse bulkheads between 12 and 13, place stab plates in FOGs, F2 tail logs in

Dewater past tailwater on ~11 – 12 Dec

    - Refasten RT conduit at NDE – vibrates at certain tailwaters.

    - Lamprey plating in lower ladder (NWP Contractor)

    - LFS hatch repair (NWP dive contractor – 21-24 Nov)

    - Replace diffuser B5 gate, remove a different gate for rehab (Riggers, Mechanics)

    - Replace diffuser gate (B4?) with new gate if time allows (Riggers, Mechanics)

    - Fix diffuser gate A2 (Mechanics, Riggers)

    - Assess and repair PH2CC grating (Riggers)

    - Assess and remove sand in AWS, suck truck if necessary (Riggers)

    - Rehab C-valves, focus on C5-C10 (Mechanics, Riggers)

    - Lamprey weir caps on NDE, NUE entrance gates (Riggers)

    - Remove NDE, NUE entrance gates, repair wheels, blast, paint if time allows (Riggers, Painters)

  - B2 Corner Collector  (01 Sep 16 – Mar 2017)

  - DSM 2 (15 Dec 2016 – 28 Feb 2017)

Turn off orifice lights on 16 Dec 16.

Dewater DSM on 19 Dec.

    - Pull STSs week of 19 Dec 16.

    - STS repairs / maintenance.

    - Overhaul of screen cleaner #3 (Mechanics)

    - Overhaul of ERG hydraulics, remove and reseal, blast/paint (Mechanics, Painters)

    - Install STSs starting Feb 2017. (Riggers)

- RESEARCH FACILITIES

  - Adult Fish Facility (Nov 2016 – April 2017) Dates estimated

Go to orifice flow on ~21 Nov 16

Dewater on ~23 Nov 16

    - New netting over fish flumes (Fisheries)

    - Repair weirs, shims (Mechanics)

  - Smolt Monitoring Facility (31 Oct 15 – 28 Feb 16)

Switch to bypass, drain and inspect sample flume on 30 Oct 13. (PSMFC)

    - TBD

KEY TO COLORS-

Red - Painters

Blue – Mechanics

Pink – Riggers

Green – Garage

Orange – Electricians

Aqua- Fisheries

Yellow- contractors or researchers