**THE DALLES FISHWAY DEWATER SCHEDULE**

**2021-22**

Fish Unit 1 and 2 OOS Dec 1, 2021

East Fishladder Dewater Dec 2, 2021

1. 158 seal
2. Inspect weir brackets
3. Inspect lower ladder grating
4. Scan for PITs (TDF)
5. Pull exit trashrack inspect
6. Install exit oil boom

East Fishway below tailwater Dewater Dec 6, 2021

1. Inspect grating
2. Inspect diffuser valves JP AWS chamber
3. Install SCADA west entrance

North Fishladder Dewater Jan 17, 2022

1. Inspect diffuser valve at count station
2. Pull Exit trashrack inspect
3. Pull PUD intake trashrack inspect

North Fishway below tailwater Dewater Jan 18, 2022

1. Inspect grating
2. Install SCADA north entrance
3. Inspect weir N1 wheel wear

Ice Trash Sluiceway OOS Dec 16, 2021

1. Endgate inspect
2. Lower channel check for spalling