## SR
FISHWAY STATUS REPORT | [5 empty] | JOHN DAY DAM
Date: | 2010-01-18 | [6 empty] | JD/WC Project-Fisheries
Inspection Period: 01/10 - 01/16/2010 | [7 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541-506-3800
Fishway inspections twice daily.
John Day Dam |  | Inspections | Criteria | Total Number of Inspections: |  | 7 | Temperature: |  | 40 | F
|  | Out of Criteria | Limit | Comments |  |  | Secchi: | 6 | Ft.
NORTH FISHWAY |  |  |  | OOS since 16 Nov 09 for new control weirs' construction. RTS 15 March 2010
Exit differential |  |  | ≤ 0.5'
Exit hydraulic weirs |  |  | Per forebay | Set for forebay >263'
Count station differential |  |  | ≤ 0.3'
Weir crest depth |  |  | 1.0' ± 0.1'
Entrance differential |  |  | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir EW1 |  |  | depth (≥ 8') | AVG | #DIV/0!
Entrance weir EW2 |  |  | No criteria | Weir closed
SOUTH FISHWAY |  |  |  | OOS since 12 Jan. 2010 for annual maintenance. RTS 25 Jan. 2010
Exit differential |  |  | ≤ 0.5'
Hydraulic weir positions |  |  | Per forebay | Set at mid forebay range
Count station differential |  |  | ≤ 0.3'
Weir crest depth |  |  | 1.0' ± 0.1'
South entrance differential |  |  | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir SE1 |  |  | depth (≥ 8') | AVG | #DIV/0!
Collection channel velocity |  |  | 1.5 - 4 fps | AVG
Bay 1 differential |  |  | 1.0' - 2.0' | AVG | #DIV/0!
N.entrance PH(Bay 19)differential |  |  | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir NE1 |  |  | depth (≥ 8') | AVG | #DIV/0!
Entrance weir NE2 |  |  | depth (≥ 8') | AVG | #DIV/0!
JUVENILE PASSAGE |  |  |  | In service with 30% of orifices open at one time and rotated weekly.
Forebay/bypass conduit differential |  | 0 | 4.0' - 5.0' | AVG | 4.5
Submersible traveling screens |  | 0 | visual inspect | Per monthly inspection schedule during juvenile passage season.
Turbine trashrack drawdown |  | 0 | <1.5', wkly
Vert barrier screen drawdown |  | 0 | <1.5', wkly
Spill volume |  | 0 | OOS | 2010 spill season starting on 10 April.
Spill pattern |  | 0 | N/A
Turbine Unit Priority |  | 0 | per FPP
Turbine 1% Efficiency |  | 0 | per FPP
SMOLT MONITORING FACILITY
SMF was dewatered on 30 Nov '09, AM. It will remain OOS for winter maintenance until 1 April '10.
Operation: | 2009 Sampling season ended at 0700 on 9/15. SMF was in bypass and manned 16 hours per day for full flow PIT tag detection from 9/15
through 11/30.
30% of gatewell orifices are open and rotated weekly. JBS in service.
Maintenance:
All flushing/supply water pipes and valves were winterize by Fisheries and JDM crews by 12/4.
JDM planning for repainting of all flushing water supply and drainage pipes in March 2010; including crest gate surface.
Cleaning and painting of FDS completed. JDM (Mechanical) repair of the two way gate rotation problem completed on 11/18.
Leaking expansion joints in the elevated chute fixed by JDS by 1/12.
OTHER ISSUES:
JOHN DAY
Birds: | PH Forebay: 4 cormorants 6 gulls
PH Forebay: 14 cormorants 2 gulls
New and improved tailrace avian lines grid's contract was awarded and its installation is starting soon. Mr. Mackintosh is the project's POC.
New construction: JD North ladder's counting station and control weirs overhaul/ improvements' work started as planned on 17 November '09,
Old weirs and assorted hardware had been already removed and pouring of new weirs started this week. On schedule for 15 March completion
deadline. Also, spillway bay 20 flow deflector is currently under construction; expected date of completion is early March 2010.
Maintenance:
South fish turbine # 3 rehab ongoing - new plan is under discussion with some internal coordination by JDM underway. New ETR is 1 March 2011.
The remaining two turbines will be completed by the end of FY 2012, one after another.
Fishways' automation design is in the planning stage with installation activities by JDE (Electrical) starting as soon as all ordered parts are received.
Calibration: | Conducted 1/16 with all parameters within established limits.
Gatewell drawdown checked 1/16. All within criteria.
Operations:
JD South fishway was dewatered on 1/12. It went well with only few fish encountered and most of them were pushed into tailrace without handling.
RTS 1/25. JDS (structural) will work on a leaking expansion joint this weekend and will re-install the repaired exit debris guard shortly before the ladder
is watered back up on 1/25. JDM(Mechanical) found a problem with AWS fish turbine 1 oil pump's seal, in process of procuring this part. However,
it may take some time and the south ladder may have to operate with only one AWS fish turbine for up to two weeks (through January.)
MUs intake trashracks rake's repair completed on 10/29. In service and ready to go for 2010 season!
STS camera device without the VBS capability. JDE(Electrical) will be fixing/ replacing entire video system with brand new hardware for 2010 season.
New underwater/ replacement camera was tested on 8/20 and what an improvement over the outdated/old technology! Four more will be procured
soon. Waiting for vendor's completion of the five cameras system's design before final procurement.
All remaining fishways' passage equipment is working well and fully meeting FPP criteria.
Research:
Planning and coordinating with contractors for 2010 research season continues. A large hydroacoustic smolt tracking/passage study (PNNL)
will take place at JD and its impacts will need to be coordinated with management and maintenance crews . However, most of its hardware is already in
place and therefore, the hydroacoustic equipment installation in March '10 will be similar to one in '09; only moderate project impact is expected.
PNNL will soon submit a detailed installation/research plan for the project's review and approval.
University of Idaho telemetry crew continues with winter maintenance of lamprey PIT half-duplex antennas. Additionally, they are reinstalling
the adult radio telemetry antennas at both fishways for 2010 adult salmon tracking.

## FishCounts
John Day 2009
| South | North | South | North | South | North
| ChinAdult | ChinAdult | ChinJack | ChinJack | Sthd | Sthd

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fall Backs
Sun
Mon
Tues | [5 empty] | Max:
Wed
Thur | [5 empty] | Min:
Fri
Sat | 40 |  | 6
AVG: | 40 | AVG: | 6 | AVG: | #DIV/0!
| N.Ent | EW1 | S.Ent | SE1 | Bay1 | Bay19 | NE1 | NE2 | JBS Diff
Sun | [8 empty] | 4.5
Sun | [8 empty] | 4.5
Mon | [8 empty] | 4.5
Mon
Tues
Tues
Wed
Wed
Thur
Thur
Fri
Fri
Sat
Sat
AVG: | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 4.5