## SR
FISHWAY STATUS REPORT | [6 empty] | JOHN DAY DAM
Date: |  | 2013-02-05 | [6 empty] | JD/WC Project-Fisheries
Inspection Period: |  | 1/27 thru 2/2/2013 | [6 empty] | P.O. Box 564
Rufus, Oregon 97050
Phone: 541-506-7860
Fishway inspected daily.
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  | 7 | Temperature: |  | 38.2857 | F
|  |  | Out of Criteria | Limit | Comments |  |  | Secchi: | 5.625 | Ft.
NORTH FISHWAY |  |  |  |  | Dewatered/ OOS since 11/5 |  | ETR is mid March 2013.
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1' | [5 empty] | `
Entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | #DIV/0!
SOUTH FISHWAY |  |  |  |  | Dewatered 1/28 for 2 week maintenance outage ETR- 2/11.
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
South entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir SE1 |  |  | 0 | depth (≥ 8') | AVG | #DIV/0!
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | AVG | no velocity measurement's
Bay 1 differential |  |  | 0 | 1.0' - 2.0' | AVG | #DIV/0!
N.entrance PH(Bay 19)differential |  |  | 0 | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir NE1 |  |  | 0 | depth (≥ 8') | AVG | #DIV/0!
Entrance weir NE2 |  |  | 0 | depth (≥ 8') | AVG | #DIV/0!
JUVENILE PASSAGE |  |  |  |  | JBS OOS since 12/16. ETR in late March 2013.
Forebay/bypass conduit differential |  |  | 0 | 4.0' - 5.0' | AVG | na
Submersible traveling screens |  |  | 0 | visual inspect
Turbine trashrack drawdown |  |  | 0 | <1.5', wkly | No discrepancies.
Vert barrier screen drawdown |  |  | 0 | <1.5', wkly | No discrepancies
Spill volume |  |  | 0 | per FPP
Spill pattern |  |  | 0 | per FPP
Turbine Unit Priority |  |  | 0 | per FPP
Turbine 1% Efficiency |  |  | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: | SMF OOS since 11/30/12. ETR is 3/28; the juvenile salmonids' daily sampling starting on 4/1/13.
JBS was regular service for the kelt migrants' protection through 12/15/12. All STSs were removed from gatewells by JD Structural crew by 12/20.
Debris: | NA
Maintenance: Planning for winter maintenance/PM activities continues.
JD Electrical scoping for the SMF CCTV replacement; the original system installed in 1998 is barely usable and its components have been failing
frequently.
Research: None
OTHER ISSUES:
JOHN DAY
Birds: | see web site
123 avian lines are properly installed; two are currently missing after breaking in June.
Planning for reinstallation of all lines for the 2013 passage season underway.
Operations:
2012 fish passage season ended on 11/30. 2013 adult salmonids passage season is starting on 3/1.
JD North Fishway continues OOS; its entrance improvements' construction activities by Slayden underway. ETR is mid March.
JD South fishway successfully dewatered 1/28. 2 juvenile salmonids bagged and released to tailwater in excellent condition. ETR 2/11.
JBS collection channel was dewatered on 1/10; ETR mid March. Planning to seal/ repair leaking expansion joints soon (JD Engineering and Structural.)
MU9 scroll case successfully fished 1/28 & the draft tube 1/29. No fish were salvaged.
New construction:
Contractor / Construction Office are working on bringing of all 6 new JDN AWS pumps into service soon. ETR is mid March.
Slayden continues with the second year of JD North entrance improvements; all their work is on schedule.
JD two TSWs are undergoing repairs/ maintenance by a contractor; they will be a permanent part of JD juvenile fish passage configuration.
Maintenance:
ROV inspection of JD South collection channel's diffuser gratings was performed on 1/29 by Portland's Diving Safety team, Rick and Todd. All pannels
were found properly attached, with all bolts intact. MU 6 intake trashracks were also ROVed to verify their status; they were supprisingly clean and
without any damage to their bars. However, there was a large, uprooted tree found at the bottom of 6 B; but it is too low to affect fish passage.
JBS tainter gate's comprehensive inspection by JD Engineering, on 1/14 revealed no damage; the gate is in excellent condition again :)
MU intake raking crane returned to service on 12/5/12.
STS winter maintenance by JD Mechanical crew is underway.
Gatewell draw down: OOS. ETR in late March 2013.
Calibration: | 2013-01-11 | All JD Fishways' PLCs/ water level sensors were within 0.3' margin of error.
JD Resources/JDF planning repair/replacement of JD North tailwater staff guage
Research:
No fish research or fish counting taking place at JD since October 31.
JD Fisheries involved in PDTs for JD South lamprey trap and in JD North LPS designs; the installations started in January 2013.
JD Fisheries involved in planning for winter maintenance/new equipment installations.

## Birds
S2: No bird
observed
S1: No birds observed
S3:No bird observed
P4:
P3:
P2: No bird
observed
P1: NO birds observed
S4 No bird observed

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fallbacks
Sun | 39 |  | 5.5 |  | ha
Mon | 38 |  | 5.5 |  | na
Tues | 38 |  | 5.5 |  | na
Wed | 37 |  |  |  | na
Thur | 39 |  | 6 |  | na
Fri | 37 |  |  |  | na
Sat | 40 |  |  |  | na
AVG: | 38.2857 | AVG: | 5.625 | AVG | #DIV/0!
|  |  |  | MAX | #DIV/0!
|  |  |  | MIN | #DIV/0!
| NE1 | NE2 | S.Ent | SE1 | N.Ent | JBS Diff | Bay1 | Bay19
Sun | Orifice Flow |  |  |  | OOS | OOS | Orifice Flow
Sun |  |  |  |  | OOS | OOS
Mon | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Mon |  |  |  |  | OOS | OOS
Tues | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Tues |  |  |  |  | OOS | OOS
Wed | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Wed |  |  |  |  | OOS | OOS
Thur | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Thur |  |  |  |  | OOS | OOS
Fri | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Fri |  |  |  |  | OOS | OOS
Sat | OOS | OOS | OOS | OOS | OOS | OOS | Tailwater
Sat |  |  |  |  | OOS | OOS
AVG: | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!