## SR
FISHWAY STATUS REPORT | [7 empty] | JOHN DAY DAM
Date: | 2011-03-28 | [8 empty] | JD/WC Project-Fisheries
Inspection Period: |  | 3/20 - 3/26/11 | [7 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541-506-4860
Fishway inspections twice daily.
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  |  | 14 | Temperature: |  | 42.1429 | F
|  |  | Out of Criteria | Limit | Comments |  |  |  | Secchi: | 3.8571 | Ft.
NORTH FISHWAY |  |  |  |  | Ladder was dewatered 3/21 through 3/28 for emergency crowder window's seal repair.
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for HIGH forebay, normal setting
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
Entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | #DIV/0! | N. ladder out of service
Entrance weir EW1 |  |  | 0 | depth (≥ 8') | AVG | #DIV/0! | N. ladder out of service
Entrance weir EW2 |  |  | 0 | No criteria | Weir closed
SOUTH FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for MID forebay, normal setting
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
South entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.1643
Entrance weir SE1 |  |  | 0 | depth (≥ 8') | AVG | 8.5929
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | AVG
Bay 1 differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.4857
N.entrance PH(Bay 19)differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.5357
Entrance weir NE1 |  |  | 0 | depth (≥ 8') | AVG | 9.2 | Due to outdated control, new automation underway now.
Entrance weir NE2 |  |  | 0 | depth (≥ 8') | AVG | 8.95 | Due to outdated control, new automation underway now.
JUVENILE PASSAGE |  |  |  |  | 1/3 JBS orifices open and rotated daily, 11/29/2010 thru last week in March 2011
Forebay/bypass conduit differential |  |  | 0 | 4.0' - 5.0' | AVG | 4.5643
Submersible traveling screens |  |  | 0 | visual inspect | All STSs were removed on 12/16 through 12/19/10. They will be reinstalled before 1 April
Turbine trashrack drawdown |  |  | 0 | <1.5', wkly
Vert barrier screen drawdown |  |  | 0 | <1.5', wkly
Spill volume |  |  | 0 | On seal | Spill for fish passage starting on 10 April.
Spill pattern |  |  | 0 | On seal
Turbine Unit Priority |  |  | 0 | per FPP
Turbine 1% Efficiency |  |  | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: | OOS until 31 March 2011. First 24 hrs sample will occur on 4/1/11.
Maintenance:
3 and 2 way gates have been already fixed; NOAA engineers recommended the "slack" running belts for their improved performance.
2010 extended operation resulted in the SMF flushing water pipes and valves being frozen/ cracked. All damages have been repaired.
FPOM decided that it is critical to run SMF through November, but we have their permission to shut it down based on a freezing weather forecast.
PSMFC electrical crew completed updates to the SMF control system, they will allow access to various sampling settings in real time over the internet
PMs and repair activities are ongoing:
PDS screen cleaner repairs and maintenance underway.
PDS dewatering screens and their perf plates had been removed from guides and pressure washed by JD Structural.
New protective netting was installed by JD Structural to keep bird predators out and keep fish inside of the Emergency Overflow Channel (an occasional
adult salmon had been observed to jump into the dry drainage tank, once every few years.)
OTHER ISSUES:
JOHN DAY
Birds: | see bird tab
Avian lines contractor is working on site, performing repairs/ modifications. All lines are out of the water and properly tensioned!!!
Contract with USDA Animal Control Unit is being processed for 2011 gull hazing coverage at JD tailrace to minimize predation on juvenile salmonids.
New construction: 15 kV tap's installation by contractor (for the North Ladder's future AWS pumps ) is almost complete.
JD Fisheries participating in JDN entrance improvements' design, surveys and inspections. Construction activities are planned of the next year.
BPA approved additional funding for completion of the JD South AWS turbine 3 rehab. A contractor is expect to be mobilizing and starting work
in mid April. ETR is January 2012.
Maintenance:
One out of six North AWS pumps is OOS due to # 3 gear box failure. It won’t be repaired/ available during 2011 passage season; all six pumps
are scheduled for replacement the next year. (Three pumps are needed for service, two are spare at this time.)
NE 1 and 2 weirs' PLC display failed and is currently under repairs by JD Electrical. Fisheries crew is measuring weir elevations with a tape.
South Fishway's automation work will be completed soon as the funding is dropped in partial amounts.
Calibration: Conducted on 3/18; all were within established limits.
Operations:
Only one adult fishway, JD South was in service during this report period.
J North was dewatered for emergency crowder box's window leak repair on 3/21, Monday. It was returned back to service on 3/28 AM.
After a prolonged outage in 2010, the JD trashrack gentry had been repaired. It is now available for service.
STS camera device 's old video system failed beyond repair at the end of August '10 inspection. JDE(Electrical) is replacing it with brand new
cameras / hardware during this winter outage. RTS is April 2011.
All remaining fishways' passage equipment is working well and fully meeting FPP criteria.
Research:
Planning for 2011 research activities is underway. PNNL crew has already installed all spillway and powerhouse hydrophones, now setting up
computers and testing the monitoring system. They are also setting up their fish collection at JD SMF. The start of PNNL biological evaluations
of TSWs and of comprehensive dam passage monitoring is planned for late April.
U of I continues with adult lamprey PIT detections and with adult salmonids radiotelemetry tracking at both JD ladders.
Approved by Jerry Carroll
Operation Project Manager
John Day Dam

## Birds
S2:
S1: No birds observed
S3:
P4:
P3: 6 cormorants
P2:
P1: NO birds observed
S4:

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fallbacks
Sun | 41 |  | 5
Mon | 42 |  | 4
Tues | 42 |  | 3
Wed | 42 |  | 4
Thur | 42 |  | 4
Fri | 43 |  | 3.5
Sat | 43 |  | 3.5
AVG: | 42.1429 | AVG: | 3.8571 | AVG | #DIV/0!
|  |  |  | MAX | 0
|  |  |  | MIN | 0
| NE1 | NE2 | S.Ent | SE1 | N.Ent | EW1 | JBS Diff | Bay1 | Bay19
Sun | 8.2 | 9.5 | 1.2 | 8.6 |  |  | 4.6 | 1.6 | 1.5
Sun | 8.5 | 9 | 1.2 | 8.5 |  |  | 4.6 | 1.6 | 1.6
Mon | 9.7 | 9.1 | 1.2 | 8.4 |  |  | 4.5 | 1.6 | 1.4
Mon | 9.4 | 8.5 | 1.2 | 8.5 |  |  | 4.5 | 1.4 | 1.7
Tues | 10.5 | 9.4 | 1.1 | 8.8 |  |  | 4.6 | 1.3 | 1.7
Tues | 9.4 | 8.6 | 1.1 | 8.6 |  |  | 4.6 | 1.4 | 1.6
Wed | 8.7 | 9.5 | 1.1 | 8.8 |  |  | 4.6 | 1.4 | 1.3
Wed | 9.1 | 9.8 | 1.2 | 8.6 |  |  | 4.5 | 1.5 | 1.8
Thur | 9.6 | 8.8 | 1.1 | 8.8 |  |  | 4.6 | 1.4 | 1.4
Thur | 8.7 | 9.2 | 1.1 | 8.3 |  |  | 4.4 | 1.4 | 1.1
Fri | 9.3 | 8.5 | 1.3 | 8.8 |  |  | 4.6 | 1.6 | 1.7
Fri | 9.1 | 8.4 | 1.1 | 8.4 |  |  | 4.6 | 1.5 | 1.8
Sat | 9.4 | 8.6 | 1.1 | 8.6 |  |  | 4.6 | 1.4 | 1.5
Sat |  | 8.4 | 1.3 | 8.6 |  |  | 4.6 | 1.7 | 1.4
AVG: | 9.2 | 8.95 | 1.1643 | 8.5929 | #DIV/0! | #DIV/0! | 4.5643 | 1.4857 | 1.5357
Note on C24: G2ODDEG9: weir being worked on
Note on F30: G2ODDEG9: orifice flow for N ladder dewatering.