## SR
FISHWAY STATUS REPORT | [7 empty] | JOHN DAY DAM
Date: | 2011-06-27 | [8 empty] | JD/WC Project-Fisheries
Inspection Period: |  | 6/19 thru 6/25/2011 | [7 empty] | P.O. Box 823
RUFUS , OR 97050
Phone: 541-506-4860
Fishway inspections twice daily.
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  |  | 14 | Temperature: |  | 58.4286 | F
|  |  | Out of Criteria | Limit | Comments |  |  |  | Secchi: | 2.8571 | Ft.
NORTH FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for HIGH forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
Entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.4286
Entrance weir EW1 |  |  | 0 | depth (≥ 8') | AVG | 9.2143
Entrance weir EW2 |  |  | 0 | No criteria | Weir closed
SOUTH FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for MID forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
South entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.3357
Entrance weir SE1 |  |  | 0 | depth (≥ 8') | AVG | 8.7286
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | AVG
Bay 1 differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.6643
N.entrance PH(Bay 19)differential |  |  | 0 | 1.0' - 2.0' | AVG | 2.1571
Entrance weir NE1 |  |  | 0 | depth (≥ 8') | AVG | 8.3929
Entrance weir NE2 |  |  | 0 | depth (≥ 8') | AVG | 8.5786
JUVENILE PASSAGE
Forebay/bypass conduit differential |  |  | 0 | 4.0' - 5.0' | AVG | 4.5786
Submersible traveling screens |  |  | 0 | Video inspt | May's STS video inspection has been delayed due to poor water visibility.
Turbine trashrack drawdown |  |  | 4 | <1.5', wkly | Affected trashracks raked immediately.
Vert barrier screen drawdown |  |  | 0 | <1.5', wkly | All are OK
Spill volume |  |  | 0 | per FPP | Summer 30/40 % block study was cancelled due to excessive flows this year.
Spill pattern |  |  | 0 | per FPP
Turbine Unit Priority |  |  | 0 | per FPP
Turbine 1% Efficiency |  |  | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: | In service since March 30. PSMFC's smolt sampling occurs 7 days a week until September 15.
Maintenance: PDS screen cleaner OOS at ~1530 on 6/23. RTS in manual on 6/24, Friday after JD Maintenance was called that day and attempted
fixing it. More work on auto system will continue the next week during the regular work hours.
JD Fisheries is temporarily cleaning the PDS screens in the available manual mode three times a day until auto mode is fixed.
Per JD OPM the Gatewell drawdown inspections were changed from weekly to daily during the high debris periods. MUs trashracks are being raked on
all units that are 1.3' or higher to prevent exceeding the FPP criteria of 1.5 '.
MU 3 and 4 were raked on Friday, 6/24 due to their gatewells drawdowns more than 1.3', MU 3 was at 1.6' during AM inspection.
Research:
PNNL tagging crew completed their Spring component on 5/30, they tagged a record number of 15,000 smolts since 4/25 (!) The Summer component
was cancelled due to excessive flows this year. PNNL will repeat the biological TSWs evaluations the next year.
Fallbacks | AVG | 93.2857 | MAX | 101 |  | MIN | 80
OTHER ISSUES:
JOHN DAY
Birds: | see bird tab
All 124 avian lines are out of the water and properly tensioned. Four tag lines (furthest downstream) are broken and missing but it is a minor issue.
USDA Animal Control Unit's gull hazing from boats in the JD tailrace started on 4/11. Gulls' predation has been well under control so far this year.
New construction: 15 kV tap's installation by contractor (for the North Ladder's future AWS pumps ) was completed in May.
Construction of a building for the future JD NFL AWS pumps ' electrical substation continues on the pump deck (downstream of Navlock.)
JD Fisheries participating in the JDN entrance improvements' P&S , surveys and inspections. Construction activities are planned of the next IWW.
P&S is almost completed / at 100 % and contract advertising is expected in August.
BPA approved additional funding for the completion of JD South AWS turbine 3 rehab. A contractor has already dismantled the old turbine and
and its components are now being manufactured / overhauled off site. ETR is in January, 2012.
Maintenance:
JD Structural continued raking MU intake trashracks as soon as their differential measure 1.3' or higher, to prevent exceeding the FPP criteria of 1.5'
Work continues on weekends if necessary.
MU 1 C trashrack has a piece of metal sticking out) and it is not possible to rake it. Special FPOM coordination was sent on 6/26 and JD
Management is working towards an immediate diving removal. Until then, MU 1 is the last off, first on as required by FPP,
JD North AWS pumps status has improved to three available: # 1 & 2 are in service and # 5 spare (repaired by 5/19.) JD Maintenance continues with
repairs of # 6;its ETR is estimated for late July/ early August.
All six pumps are scheduled for replacement during the upcoming IWW period, 2011/2012.
NE 1 and 2 weirs' LCD display failed and is currently under repairs by JD Electrical. Fisheries crew is measuring weir elevations with a tape.
Calibration: A calibration was done 6/16/11. All were in criteria. Entrance channel and tailwater staff gauges are still under water so they couldn't
be calibrated.
South Fishway's automation work by JDE continues with estimated activation in late July.
Gate well drawdown: Conducted daily since 6/20. All VBSs OK. All MU trashracks are raked as soon as their differential reaches 1.3' or higher.
Operations:
Both adult fishways were in regular service during this report period. JD North adult ladder meets all FPP criteria with two AWS pumps in service.
JD South entrance weirs N1 & 2 old auto control is increasingly unreliable. New PLC automation is planned for final implementation in July.
May's STS video inspection, scheduled for week of 5/23 has been delayed due to poor water visibility.
Research:
FFU's gull monitoring crew started their observations on 4/11 and will continue through July.
The Summer segment of PNNL biological evaluations of TSWs and overall fish passage monitoring was cancelled due to high flows this year.
PSMFC dam angling for pikeminnow/ removal from JD tailrace BRZ started the 2011 season on 5/3. It is slated to end in September.
ODFW experimental JD dam angling for SMB (bass) started on 5/12. It is slated to end in July.
Adult lamprey trapping at JD NFL and SFL counting stations by CRITFC crews started on 6/20. The traps are checked daily, 7 days a week and the
collected fish are transported to CRITFC holding facilities for future planting in various streams and tributaries.
U of I continues with adult lamprey PIT detections and with adult salmonids radiotelemetry tracking at both JD ladders.
Approved by; Glen Smith
Operation Project Manager
John Day/Willow Creek dams

## FishCounts
John Day 2011
| South | North | South | North | South | North | South | North | South | North
| ChinAdult | ChinAdult | ChinJack | ChinJack | Sthd | Sthd | Sockeye | Sockeye | Lamprey | Lamprey
2011-06-19 | 1168 | 296 | 542 | 180 | 13 | 12 | 276 | 311 | 0 | 0
2011-06-20 | 1385 | 450 | 679 | 372 | 20 | 11 | 914 | 588 | 1 | 0
2011-06-21 | 1084 | 664 | 580 | 278 | 16 | 19 | 916 | 990 | 0 | 0
2011-06-22 | 1146 | 448 | 493 | 265 | 20 | 11 | 1117 | 955 | 0 | 0
2011-06-23 | 950 | 485 | 391 | 203 | 23 | 18 | 925 | 906 | 0 | 0
2011-06-24 | 1499 | 186 | 731 | 197 | 43 | 24 | 1663 | 979 | 1 | 0
2011-06-25 | 1439 | 469 | 722 | 277 | 30 | 28 | 1804 | 1417 | 1 | 0

## Birds
S2:none observed
S1:
S3:none observed
P4: 62 grebes, 6 gulls
P3:
P2: none observed
P1:
S4: Four gulls

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fallbacks
Sun | 57 |  | 3 |  | 94
Mon | 58 |  | 2.5 |  | 101
Tues | 58 |  | 2.5 |  | 97
Wed | 59 |  | 3 |  | 89
Thur | 59 |  | 3 |  | 93
Fri | 59 |  | 3 |  | 99
Sat | 59 |  | 3 |  | 80
AVG: | 58.4286 | AVG: | 2.8571 | AVG | 93.2857
|  |  |  | MAX | 101
|  |  |  | MIN | 80
| NE1 | NE2 | S.Ent | SE1 | N.Ent | EW1 | JBS Diff | Bay1 | Bay19
Sun | 8.1 | 8.7 | 1.2 | 8.4 | 1.4 | 9.2 | 4.6 | 1.7 | 1.4
Sun | 8.7 | 8.5 | 1.3 | 8.6 | 1.5 | 9 | 4.6 | 1.5 | 1.4
Mon | 8.3 | 8.6 | 1.3 | 8.7 | 1.5 | 9.4 | 4.6 | 1.7 | 1.5
Mon | 8.3 | 8.8 | 1.3 | 8.8 | 1.5 | 9.1 | 4.6 | 1.7 | 1.5
Tues | 8.2 | 8.8 | 1.2 | 8.7 | 1.3 | 9.7 | 4.6 | 1.6 | 1.4
Tues | 8.2 | 8.7 | 1.2 | 9.2 | 1.4 | 9.5 | 4.6 | 1.5 | 1.5
Wed | 8.1 | 8.5 | 1.5 | 8.8 | 1.4 | 9.4 | 4.6 | 1.7 | 1.8
Wed | 8.9 | 9.5 | 1.2 | 8.7 | 1.4 | 9.1 | 4.6 | 1.5 | 1.7
Thur | 8.8 | 8.5 | 1.2 | 8.9 | 1.4 | 8.3 | 4.5 | 1.5 | 1.6
Thur | 8.2 | 8.5 | 1.3 | 8.4 | 1.4 | 9.6 | 4.6 | 1.8 | 1.8
Fri | 8.4 | 8.2 | 1.7 | 8.4 | 1.4 | 9.8 | 4.6 | 1.9 | 2
Fri | 8.5 | 8.3 | 1.3 | 8.6 | 1.5 | 8.9 | 4.4 | 1.6 | 8.8
Sat | 8.5 | 8.4 | 1.7 | 8.7 | 1.5 | 9.3 | 4.6 | 1.8 | 1.9
Sat | 8.3 | 8.1 | 1.3 | 9.3 | 1.4 | 8.7 | 4.6 | 1.8 | 1.9
AVG: | 8.3929 | 8.5786 | 1.3357 | 8.7286 | 1.4286 | 9.2143 | 4.5786 | 1.6643 | 2.1571